# Governance correction — 2026-07-10 — ontology is canonical; no root README duplication

- Correction: The NPL root README/project map created on 2026-07-10 was deleted because it duplicated the project ontology/instruction layer.

- Rule: Project-level README/project-map documents must not be created by default. The project ontology and approved schema are the canonical map/rule layer.

- Exception: a local pointer/readme may be created only if explicitly approved and logged as a schema decision.

- Project-specific write/verification logs are allowed because they are audit ledgers, not instruction stores.

- Any change to folder structure, folder purpose, schema, ontology, work-package routing, handover placement, write/verification placement, or project scaffold rules must be logged at Fusion247 level and must be flagged for Claude QA / VerifAIr review.

- Support handover sign-off should be evidence based: a handover meeting with recorded verbal concurrence may satisfy sign-off evidence. Written signatures are not required unless Bellrock policy explicitly requires them.

# Project control placement update — 2026-07-10

Decision candidate for next master template revision:

- Retire `00_Project_Control` from future project scaffolds unless a later review finds a separate control folder is still required.

- Keep project audit/control evidence inside `09_Reporting_QA_Comms` using controlled subfolders:

- `01 Writes` for AI write reports, extraction notes and project write manifests.

- `02 Verifications` for VerifAIr / QA verification reports.

- The write agent must record its write as pending verification. A separate QA/VerifAIr pass must record the verification result.

- Project root should contain only a lightweight README/project map pointing to canonical instructions, not a duplicated operating manual.

Rationale: Keeps project control, QA and communications together, avoids ad-hoc `00` folder duplication, remains token-friendly, and makes recent writes/verifications easy to inspect.

---

# QA remedial update — 2026-07-06

- Remedial 1 applied: moved `F247.project-template.master.current` out of `Work Projects/Bellrock` into neutral project-template storage at `05_Projects/00_Project_Templates/F247.project-template.master.current`.

- Neutral template parent folder URL: https://drive.google.com/drive/folders/17Ae4_agnhreZjO0EmUwD-aA-e0xRNtR8

- Master template folder URL remains: https://drive.google.com/drive/folders/14J3bzqACEPFG-CoCqwI93HU2yZAovv1s

- `_release-control/changelog` and `_release-control/release-notes` now sit under `05_Projects/00_Project_Templates/_release-control`.

- Empty old Bellrock wrapper folders were renamed `ZZ_empty_moved_project-template-master_2026-07-06` and `ZZ_empty_moved_release-control_2026-07-06` for visibility pending later cleanup.

- Remedial 3 applied: BCC/Bristol City Council is not an active project. Any previous BCC/Bristol wording in this ontology was a fictional worked example and must not be treated as project state.

---

# Master project folder set update — 2026-07-06

- Created the physical Drive master project folder tree; later moved to neutral project-template storage.

- Master path: `05_Projects/00_Project_Templates/F247.project-template.master.current`.

- Master folder URL: https://drive.google.com/drive/folders/14J3bzqACEPFG-CoCqwI93HU2yZAovv1s

- This is the current living project template folder set. It is not yet an approved immutable release.

- `_release-control/changelog` and `_release-control/release-notes` were created beside the current template under `05_Projects/00_Project_Templates/_release-control`.

- Future `/create project [alias]` workflows should copy from this master template folder only after confirming the active client/domain and checking for duplicate project aliases.

- Actual Drive folder names created include `09_Handover_Closure`, `comms-plan`, `project-constraints`, `acceptance-tests`, `training-overview`, `uat-overview`, `uat-test-scripts`, `benefits-notes` and `lessons-captured` where shorter names were safer for the live folder creation step.

---

# F247.project-operating-ontology

> Purpose: Repeatable project work map for Fusion247-managed implementation projects. This document defines how project inputs, project folders, work packages, skills, agents, outputs and registers fit together.

---

## Metadata

- Document title: F247.project-operating-ontology

- Status: Active draft

- Created date: 2026-07-05

- Created by: Fusion / ChatGPT, at Warwick's request

- Review status: AI-created; requires Warwick review before becoming the approved project template release

- Knowledge maturity: Strong candidate

- Related agent: [[F247.agent.project-manager-ai]]

- Related templates: [[F247.template.project-folder-structure]] [[F247.template.project-management-readme]]

- Related source: [[build.companyOS.entology]]

- Related principles: [[F247 Brain PRD]] [[F247.implementation.plan]] [[F247.baseline.mvp-v0.1-google-drive-operating-model]]

---

## 1. Why this exists

Fusion247 already has a working Brain structure, control documents, agents, templates and a project folder scaffold. The missing project layer is an ontology: a repeatable map of implementation work that tells AI what kind of work is happening, what source evidence matters, what outputs are expected, which registers must be updated and which human approvals are required.

This document turns the project folder template from a storage structure into a project operating system.

It is not a company OS. Fusion247 is not trying to model every function in a company at this stage. The current scope is narrower and more useful: a Project Implementation OS for Warwick's work projects, especially Bellrock-style enterprise SaaS and CAFM implementations.

---

## 2. Core operating model

The desired MVP workflow is:

```text

Project source input

↓

00_Project_Inbox or named source drop point

↓

/project intake [project_id or alias]

↓

Source classification

↓

Immutable source preservation

↓

Extraction of actions, decisions, risks, issues, requirements, assumptions, changes and open questions

↓

Mapping to project stage, module and work package

↓

Update project artefacts and registers

↓

Generate internal summary, external email draft or next-action brief

↓

Project QA check

↓

Human review and approval where required

```

The first version may be manually triggered. Automation can come later. The important principle is that once a valid input is dropped into the project inbox and the active project is identified, Fusion should know the work path without Warwick needing to retype the full process each time.

---

## 3. Project folder location rule

Work implementation projects should live under:

```text

05_Projects/Work Projects/[client-or-domain]/[project_id] - [project_name]

```

Example:

```text

05_Projects/Work Projects/[client-or-domain]/[project_id] - [project_name]

```

Short aliases may be used in commands only when project metadata maps the alias to one active project folder.

If an alias is ambiguous, Project Manager AI must stop and ask for the correct project boundary.

If a project appears to exist but cannot be found, search likely variants before creating a duplicate. Example search terms should use the known project alias, client name, project name, product/module name and domain.

Project folder creation control rule:

- AI must not create new project folders, subfolders or parallel control structures merely because a destination is unclear.

- Before creating a folder, AI must first check the active project template/folder scaffold and use the existing canonical destination where one exists.

- If the folder is not defined by the project template or the user has not explicitly authorised it, AI must stop and ask before creating it.

- Any approved new folder must be recorded in the project QA/handover note and, where canonical, in the relevant object/document register.

---

## 4. Golden master template rule

The project template must be managed like a releasable product, not an endlessly edited blob.

Use this pattern:

```text

F247.project-template.master.current

F247.project-template.master.v0.1-approved

F247.project-template.master.changelog

F247.project-template.master.release-notes

```

Rules:

- `master.current` is the living candidate used for iteration.

- An approved version such as `v0.1-approved` is the copy source for new projects.

- Approved versions must not be changed directly.

- Improvements go into `master.current`, then become a new approved version after review.

- A new project must be spun up from the latest approved version, not from a half-edited candidate.

This preserves the user's desire for a canonical master while still allowing controlled improvement.

---

## 5. Stage ontology

Every implementation project should be mapped to the following stage categories unless the project metadata defines a justified variant.

### 5.1 Project Initiation

Purpose: Create the project boundary, establish source control, confirm governance, identify stakeholders and define the starting position.

Typical inputs:

- Sales handover

- Contract or scope extract

- Initial customer email

- Internal kickoff notes

- Project assignment note

Typical outputs:

- Project metadata

- Document register

- Project brief

- Stakeholder register

- Initial risk, issue, change, decision and dependency registers

- Open questions log

Registers updated:

- Decision log

- Risk register

- Issue register

- Task register

- Open questions

- Document register

Human approval required for:

- Project name and project_id

- External commitments

- Scope interpretation

### 5.2 Sales, Contract and Scope Handover

Purpose: Translate commercial and contractual source evidence into project delivery boundaries.

Typical inputs:

- Contract

- Statement of work

- Blueprint or scope document

- Sales notes

- Proposal

- Module list

- Commercial assumptions

Typical outputs:

- Scope summary

- Delivery assumptions

- Exclusions and constraints

- Initial module map

- Candidate work package list

- Customer-facing clarification questions

Registers updated:

- Requirements log

- Assumptions log

- Constraints log

- Change log if contract interpretation changes

- Open questions

Human approval required for:

- Any commercial interpretation

- Any statement that could change customer expectations

- Any scope gap or exclusion communication

### 5.3 Discovery

Purpose: Convert customer context and source material into delivery-ready requirements and work package evidence.

Typical inputs:

- Discovery meeting transcript

- Customer documents

- Process maps

- Screenshots

- Emails

- Current system exports

- Warwick's notes

Typical outputs:

- Discovery summary

- Requirements update

- Process notes

- Gap list

- Module-specific work package updates

- Action summary

- Customer email draft

Registers updated:

- Requirements log

- Decision log

- Risk register

- Issue register

- Task register

- Open questions

Human approval required for:

- Requirement acceptance

- Scope changes

- Customer-facing summaries

### 5.4 PRD and Requirements Definition

Purpose: Maintain a project-local requirements baseline without confusing reusable Fusion247 knowledge with project-specific truth.

Typical inputs:

- Discovery outputs

- Contract and scope documents

- Customer confirmation emails

- Approved decisions

- Product/module evidence

Typical outputs:

- Project PRD

- Requirements log

- Acceptance criteria

- Assumptions and constraints

- Traceability to work packages

Registers updated:

- Requirements log

- Decision log

- Change log

- Document register

Human approval required for:

- PRD approval

- Acceptance criteria approval

- Any customer-visible baseline

### 5.5 Work Package Planning

Purpose: Break the project into controlled delivery units that can be planned, configured, trained, tested and closed.

Typical inputs:

- PRD sections

- Module list

- Scope summary

- Discovery notes

- Constraints

- Dependencies

Typical outputs:

- Work package brief

- Work package task list

- Training agenda outline

- UAT outline

- Completion criteria

- Handover requirements

Registers updated:

- Work package index

- Task register

- Dependency log

- Risk and issue registers

- Document register

Human approval required for:

- Work package scope

- Work package acceptance criteria

- Any customer-facing delivery plan

### 5.6 Configuration and Build

Purpose: Track configuration work, decisions, evidence and task progress against the approved work package.

Typical inputs:

- Configuration notes

- Screenshots

- Build decisions

- Product constraints

- Customer feedback

- Test findings

Typical outputs:

- Configuration log

- Build notes

- Decision updates

- Task updates

- Evidence links

- Demo or training preparation notes

Registers updated:

- Task register

- Decision log

- Issue register

- Change log where scope is affected

- Work package completion log

Human approval required for:

- Configuration decisions that change workflow, scope or customer commitments

### 5.7 Data, Integrations and Technical Dependencies

Purpose: Control technical dependencies such as imports, exports, integrations, SSO, environments, data cleansing and system constraints.

Typical inputs:

- Data templates

- Integration notes

- Technical emails

- SSO or environment details

- Import/export results

- Customer IT responses

Typical outputs:

- Technical dependency log

- Data issue list

- Integration action list

- Environment readiness note

- Customer technical summary

Registers updated:

- Dependency log

- Risk register

- Issue register

- Task register

- Decision log

Human approval required for:

- Technical commitments

- Security or access statements

- Any customer-facing explanation of system limitation or responsibility split

### 5.8 Training and Adoption

Purpose: Create training content and adoption support that reflects the actual scoped work package, not generic product training.

Typical inputs:

- Work package brief

- Configuration notes

- Process decisions

- User roles

- Training attendance requirements

- Customer questions

Typical outputs:

- Training plan

- Training agenda

- User guide or quick reference note

- Adoption readiness checklist

- Training follow-up email

Registers updated:

- Task register

- Decision log if training confirms process choices

- Issue register if adoption blockers emerge

- Document register

Human approval required for:

- Final training pack

- Customer-facing training agenda

### 5.9 UAT

Purpose: Test delivery against work package scope, requirements and acceptance criteria.

Typical inputs:

- Requirements log

- Work package brief

- Configuration notes

- Training outputs

- Customer test feedback

- Defect emails

Typical outputs:

- UAT plan

- UAT scripts

- Defect or issue list

- UAT summary

- Acceptance recommendation

Registers updated:

- Issue register

- Task register

- Decision log

- Work package completion log

- Change log if new requests appear during UAT

Human approval required for:

- UAT script approval

- UAT completion

- Acceptance recommendation

### 5.10 Go-Live Readiness

Purpose: Confirm the project or work package is ready to move into live use.

Typical inputs:

- UAT results

- Open issues

- Training completion

- Customer readiness notes

- Support requirements

- Go-live checklist

Typical outputs:

- Go-live readiness checklist

- Cutover or readiness note

- Open issue summary

- Customer go-live email draft

Registers updated:

- Risk register

- Issue register

- Task register

- Decision log

- Dependency log

Human approval required for:

- Go-live recommendation

- Customer-facing go-live confirmation

### 5.11 Support Handover

Purpose: Convert project knowledge into support-ready context and close the loop between delivery and BAU.

Typical inputs:

- Work package completion logs

- Configuration notes

- UAT summary

- Outstanding risks or issues

- Customer support model

- Known limitations

Typical outputs:

- Support handover pack

- Known issues list

- Configuration summary

- Customer success or support briefing

- Closure actions

Registers updated:

- Issue register

- Lessons log

- Task register

- Document register

- Project completion log

Human approval required for:

- Handover pack

- Formal project or work package closure

### 5.12 Closure, Benefits and Lessons Learned

Purpose: Close the project cleanly, capture reusable knowledge and identify improvements for the master template.

Typical inputs:

- Project completion notes

- Customer feedback

- Support handover

- Lessons learned

- Final status report

Typical outputs:

- Closure report

- Lessons learned

- Benefits review note

- Candidate improvements to reusable Fusion247 templates

Registers updated:

- Lessons log

- Project completion log

- Decision log

- Task register

- F247 Work List if reusable improvements are needed

Human approval required for:

- Project closure

- Any reusable lesson promoted into the main Brain

---

## 6. Source intake ontology

Project inputs will usually be one of the following:

### 6.1 Email

Extract:

- Sender and recipients

- Date

- Project or client clues

- Decisions

- Actions

- Questions

- Risks and issues

- Requirements

- Customer commitments

- Required response

Expected outputs:

- Source note

- Action updates

- Draft reply where needed

- Register updates

### 6.2 Teams transcript or meeting transcript

Extract:

- Meeting purpose

- Attendees if available

- Decisions

- Actions and owners

- Requirements

- Risks and issues

- Open questions

- Changes in scope or understanding

- Stage or work package impact

Expected outputs:

- Meeting summary

- Work package updates

- Register updates

- Follow-up email draft

### 6.3 Warwick written note

Extract:

- Intent

- Project context

- Decisions or candidate decisions

- Tasks

- Uncertainties

- Any implied work package or stage

Expected outputs:

- Project note

- Task/register updates

- Clarifying questions where needed

### 6.4 Contract, scope or customer document

Extract:

- Contractual facts

- Deliverables

- Exclusions

- Constraints

- Dependencies

- Acceptance points

- Ambiguities

Expected outputs:

- Scope summary

- Requirements and assumptions updates

- Candidate work packages

- Open questions

### 6.5 Screenshot, export or evidence file

Extract:

- What the evidence shows

- Related module or process

- Issue or requirement supported

- Date and source context

Expected outputs:

- Evidence note

- Link to affected requirement, issue or work package

---

## 7. Project commands

### 7.1 Create project

Preferred command:

```text

/create project [project alias or name]

```

Behaviour:

- Search for existing project aliases and likely duplicates first.

- If no existing project is found, create or propose the folder under `05_Projects/Work Projects/[client-or-domain]/[project_id] - [project_name]`.

- Create project metadata and document register.

- Create empty core registers.

- Do not create a PRD or work package with invented facts.

- Record missing inputs as open questions.

### 7.2 Update project

Preferred command:

```text

/update project [project_id or alias]

```

Behaviour:

- Confirm the active project folder.

- Read project metadata and document register.

- Process new source inputs from the project inbox or named source.

- Preserve raw source evidence.

- Update the correct project artefacts and registers.

- Generate draft summaries or communications.

- Run project QA checks before closeout.

### 7.3 Intake project source

Preferred command:

```text

/project intake [project_id or alias]

```

Behaviour:

- Process one or more new inputs only.

- Classify the source type.

- Map the input to stage, work package and registers.

- Produce a concise processing report.

---

## 8. Folder to ontology mapping

Use the project folder scaffold as the project-local operating boundary. Canonical for the actual stage list, subfolder names and rationale: GL-F247-001-project-entity-schema section 8 (00_System/Governance) and the Structural Spec tab of F247 Drive Object Registry (00_System/Indexes). Enhanced to a 13-stage structure 2026-07-09, active candidate pending validation against a real project; do not restate the stage list here.

The stage-to-register mapping in sections 5, 9, 10 and 11 of this ontology remains this document's own canonical content and is unaffected by the folder rename.

---

## 9. Work package ontology

Each work package should follow this lifecycle:

```text

Not Started

Draft Scope

Ready for Review

Approved

In Progress

Blocked

Ready for UAT

UAT Complete

Ready for Handover

Closed

```

Each work package should contain or link to:

- Work package brief

- Source summary

- Requirements and acceptance criteria

- Configuration notes

- Decisions and changes affecting the package

- Task list

- Training agenda

- UAT script

- Completion log

- Support handover notes

- Open risks, issues and dependencies

Work package rule:

- No work package may be marked approved unless it traces back to source evidence, PRD or scope, acceptance criteria and a current task/register state.

---

## 10. AI role boundaries

### Project Manager AI

Owns project structure, work package alignment, project documents, project register maintenance and project closeout support.

### CategorisAIr

Classifies source inputs and routes them into the correct project inbox, source folder, knowledge note or register destination. For project-specific inputs, CategorisAIr must keep truth inside the active project folder unless reusable knowledge is explicitly promoted.

### VerifiAIr

Checks project outputs for source traceability, folder boundary, metadata quality, register consistency, false assumptions and missing approval points.

### ResearchAIr

May support decision-grade research if the project needs external research, but must not replace project-local evidence.

### Fusion / OrchestratAIr

Routes the command, confirms the active project boundary and coordinates the agent behaviour. It should reference this ontology rather than copy it into `/Hey Fusion.md`.

---

## 11. Project QA checklist

Before closing a project update, check:

- Active project_id and folder are confirmed.

- No duplicate project folder has been created.

- Raw sources were preserved or clearly identified.

- Living artefacts link back to evidence.

- Actions, decisions, risks, issues, requirements and changes were routed to the correct registers.

- Any customer-facing output is still draft unless Warwick approves it.

- No facts were imported from another project without explicit approval.

- Work package updates trace to scope, requirements or source evidence.

- Open questions are logged rather than silently converted into assumptions.

- Document register and completion logs are updated where relevant.

- Project source extraction runs must leave a QA/handover note in the project `09_Reporting_QA_Comms` folder, recording source, target artefact/branch, rows or documents changed, uncertainties, exceptions and verification focus.

---

## 12. MVP vertical slice

The first useful pilot should be one vertical slice:

```text

Project Inbox

↓

Source Preservation

↓

Intake Extraction

↓

Work Package Update

↓

Registers Update

↓

Draft Summary

↓

QA Check

```

Recommended pilot project/module: one Bellrock implementation module or workstream where there is enough source evidence to test the pattern without inventing missing facts.

---

## 13. Do not build yet

Do not automate source capture, dashboarding, semantic search, custom Kanban, hosted backend, Telegram routing or Codex execution from this ontology until the manual project intake loop has worked cleanly.

The current goal is not clever automation. The current goal is a repeatable project operating path that works when triggered manually.

---

## 14. Open questions

- Should `00_Project_Inbox` be inserted into all future project scaffolds as a top-level folder before `00_Project_Control`, or should it sit inside `00_Project_Control`?

- Should short aliases be held in project metadata only, or also in a central project alias register?

- Should the approved template be a Google Drive folder copy, a set of Google Docs templates, or both during the Drive-first MVP phase?

- Resolved 2026-07-06: no active BCC/Bristol project folder exists in Drive; earlier BCC wording was a fictional example and has been removed as project state.

---

## 15. Backlinks

[[Fusion247]] [[Fusion247 Brain]] [[Project Manager AI]] [[CategorisAIr]] [[VerifiAIr]] [[Project Management]] [[PMP]] [[PRINCE2]] [[CPMAI]] [[Bellrock]] [[Implementation Projects]] [[Work Packages]] [[Project Ontology]]

---

## Root Orphan Prevention Rule (Added 2026-07-08)

No CV or cover letter .docx file may remain in Google Drive root.

When building a native .docx via the docx skill:

- Create the file locally and save to /mnt/user-data/outputs.

- Upload the .docx directly to the relevant application folder in Drive (e.g. CV/applications/[company]-[yyyy-mm]/).

- Do NOT upload to Drive root as a temporary staging point.

- After uploading to the application folder, verify the file is present before proceeding.

- If a .docx file is found in root, move it immediately to the correct application folder and delete the root copy.

This prevents CV/cover letter files from becoming orphaned and clogging the Drive root. Root is not a working directory.