# F247 AsdAIr Microsite App — Workpackage Plan

Project ID: F247-ASDAIR-MICROSITE-001

Project name: AsdAIr Microsite App

Status: Draft workpackage plan

Created: 2026-07-07

Owner: Warwick

Governance agent: Project ManagAIr

Active project folder: 05_Projects/Project Fusion247/F247 AsdAIr Microsite App

## Delivery principle

Build something visible first.

This project should avoid disappearing into architecture debate. The first working release should be a simple page Mum can use and Warwick can see producing structured output.

## Scope boundary

In scope:

- simple shopping request website

- accessible elderly-friendly UI

- Warwick admin/catalogue maintenance page

- SQLite storage

- Markdown export

- JSON export

- VPS-ready deployment

- optional Claude Chrome handoff prompt generation

Out of scope for MVP:

- automated Asda login

- automated checkout

- payment handling

- direct Asda API/scraping dependency

- updating AsdAIr prompt files

- altering /Hey Fusion

- adding this to the Fusion247 PRD or main implementation plan

## WP0 — Project setup and governance

Goal: Create controlled project folder and starting artefacts.

Deliverables:

- project folder scaffold

- README

- workpackage plan

- governance review

- reference map to AsdAIr sample material

Acceptance criteria:

- project is visible under 05_Projects

- boundary is documented

- Project ManagAIr review exists

- no AsdAIr prompt files are changed

Status: created / draft

## WP1 — Visible clickable prototype

Goal: Build a static or server-rendered first screen that Mum can actually see and click.

Deliverables:

- homepage labelled Mum's Shopping or similar

- item list with large plus/minus controls

- Use usual shop button

- free-text box for extras

- Send list to Warwick button

- confirmation screen

Acceptance criteria:

- runs locally

- works on mobile/tablet-sized screen

- no Asda login or checkout wording

- understandable to an 83-year-old user

Status: not started

## WP2 — SQLite catalogue and request capture

Goal: Store items and submitted shopping requests properly.

Deliverables:

- SQLite database

- items table

- shopping_requests table

- shopping_request_items table

- simple seed script using sample AsdAIr data

Acceptance criteria:

- regular items can be loaded from seed data

- quantities are stored correctly

- free-text extras are stored

- previous request can be viewed by Warwick

Status: not started

## WP3 — Warwick admin page

Goal: Let Warwick maintain the item catalogue without editing code.

Deliverables:

- admin login / PIN

- add item

- edit item

- deactivate item

- set default quantity

- set category

- set notes / product hint

Acceptance criteria:

- Warwick can add and change regular items

- deactivated items do not show on Mum's main screen

- app can import/paste favourites captured from Claude Chrome later

Status: not started

## WP4 — Markdown and JSON export

Goal: Produce durable outputs that can later be read by AsdAIr/Fusion247 without relying on app state only.

Deliverables:

- Markdown export for each submitted list

- JSON export for each submitted list

- exports grouped by date/request ID

Acceptance criteria:

- Markdown output resembles existing Asda List - YYYY-MM-DD pattern

- JSON output is machine-readable

- exported files include source, timestamp, person, items, quantities and free text

Status: not started

## WP5 — Claude Chrome handoff prompt

Goal: Generate a handoff prompt Warwick can paste into Claude Chrome for basket preparation.

Deliverables:

- handoff prompt text file per request

- clear instruction to use Asda Favourites/Regulars first

- clear instruction not to place the order

- list of required return outputs: added, not found, needs decision, total, notes

Acceptance criteria:

- Warwick can copy prompt into Claude Chrome

- prompt respects AsdAIr standing safety boundaries

- no direct Asda automation required

Status: not started

## WP6 — VPS deployment

Goal: Put the app somewhere Warwick can access and test on real devices.

Deliverables:

- VPS deployment notes

- systemd service or equivalent

- reverse proxy notes, likely Caddy or Nginx

- basic environment config

- simple backup approach for SQLite and exports

Acceptance criteria:

- app runs on VPS

- accessible through private URL or temporary domain

- PIN protection enabled

- database and export folder can be backed up

Status: not started

## WP7 — Future AsdAIr / Brain integration review

Goal: Decide how, if at all, this plugs into AsdAIr and Fusion247 Brain after the visible MVP works.

Deliverables:

- integration options note

- decision log entry only if Warwick approves an integration path

Acceptance criteria:

- no premature integration

- no Brain PRD changes unless Warwick explicitly reframes the project

- AsdAIr remains reference-only until integration is approved

Status: parked / TBD