## README
NPL Concerto - Project Registers
Purpose: single register workbook for the NPL Concerto implementation (Bellrock). One tab per register. Populated by the transcript/email intake pipeline (F247.prompt.transcript-extraction v0.1).
Rules: append-only rows. Never silently edit history. Status changes update the status column and note the updating source. Supersession uses supersedes/superseded_by links. Every row carries source_ref + anchor back to the immutable raw source.
ID scheme: NPL-D-xxx decisions, NPL-A-xxx actions, NPL-R-xxx risks/issues, NPL-C-xxx config changes, NPL-Q-xxx open questions, NPL-M-xxx milestones, SRC-xxx sources, NPL-U-xxx uncertainty.
Idempotency: check the Sources tab before processing a file. Already listed = do not re-process.
Project folder: 05_Projects/Work Projects/Bellrock/[project_id] - NPL Concerto Implementation (project_id to be confirmed). Raw sources: 01_Sources_Immutable.
Created: 2026-07-08 by Claude via Zapier Google Sheets.

## Decisions
decision_id | date | decision | rationale | decider | status | supersedes_links | implications | source_ref | anchor
NPL-D-001 | 2026-07-08 | Subcontractors will never be onboarded to Concerto/Orchestrate; represent them as supplier operatives under the Smart Managed Services contractor | NPL policy: no system access without NPL email + SSO. Supplier-operative model gives allocation visibility without access. Warwick explicitly flagged this to capture for the decision log | Warwick (mechanism) / Tony (endorsed) | agreed | - | Drives NPL-A-007/008 subbie upload; supplier data model | SRC-001 | Warwick @ 38:52-39:30
NPL-D-002 | 2026-07-08 | Upload all subcontractor business names into the system, with no access | NPL know the full subcontractor base; helps Jason (scheduler) plan workload | Tony | agreed | - | Feeds NPL-A-008 | SRC-001 | Tony @ 39:56-40:16
NPL-D-003 | 2026-07-08 | Emailing jobs to subcontractors from the system: declined | Option floated by Warwick and immediately refused | Tony | rejected | - | - | SRC-001 | 41:40-42:02
NPL-D-004 | 2026-07-08 | External Contractors resource-team route superseded by supplier-portal / supplier-operative model | Warwick reversed his own prior setup; supplier model separates internal vs subbie work more cleanly | Warwick | superseded | superseded by NPL-D-001 | Redundant resource team cleanup not agreed - see NPL-Q-002 | SRC-001 | Warwick @ 43:47-44:43
NPL-D-005 | 2026-07-08 | PPM Not Completed closure action rejected; incomplete dailies close as PPM complete with remedials | A remedial will always exist per Tony; confirmed again near close | Tony | rejected | - | Vanilla closure actions unchanged | SRC-001 | Tony @ 23:49; Warwick @ 1:20:31
NPL-D-006 | 2026-07-08 | Daily plant-room inspections remain individual daily jobs, each with risk assessment | A requirement for site to record completion, despite admin burden; also lets engineers raise remedials off the daily task | Tony | agreed | - | Engineer workload - see NPL-R-006 | SRC-001 | Tony @ 22:16
NPL-D-007 | 2026-07-08 | Run PPM job creation manually for first 2-3 months; defer automated workflow rules | Jobs created in live are irreversible (NPL-R-005); catch errors first; enable auto later via support ticket | Warwick recommendation; no objection | agreed in principle | - | Post-go-live revisit ~2-3 months | SRC-001 | Warwick @ 16:13-18:35
NPL-D-008 | 2026-07-08 | Allocation model: weekly planning meetings; internal jobs allocated Friday for the following week; subcontractor jobs 1-3 months ahead on a rolling monthly basis | Concerto cannot auto-allocate jobs to teams (NPL-R-009); contractors hard to book in | Tony | agreed in principle | - | Operating model; Jason (scheduler) central | SRC-001 | Tony @ 58:07; 1:00:32
NPL-D-009 | 2026-07-08 | Modular Maintenance resource team added (created live in session) | Roaming maintenance team across a large estate; easier planning | Tony | agreed - structure pending | - | See NPL-A-020 / NPL-Q-006 / NPL-C-005 | SRC-001 | Tony @ 1:15:26; Warwick @ 1:18:22
NPL-D-010 | 2026-07-08 | Permit Team resource team retained; archive halted | Future team of ~7 may review the whole permit situation | Tony | retained - confirm final state | - | See NPL-Q-003 / NPL-C-006 | SRC-001 | 1:17:31-1:18:22
NPL-D-011 | 2026-07-08 | Explore reducing 12 risk questions to a single yes/no risk-awareness confirmation referencing a named SOP (e.g. Risk Assessment Smart 001) | Engineer adoption risk; prior serious injury on site involving another contractor; Tony: risk awareness not risk assessment; desired: answering No returns task to help desk | Tony (owner) | under consideration | - | NPL-A-011; NPL-Q-005 | SRC-001 | 1:25:52-1:29:57
NPL-D-012 | 2026-07-08 | Preset text for completion/hold reasons adopted in principle | New Concerto functionality; contract-aligned selectable wording drops into audit trail; avoids free-text quality issues | All | agreed in principle | - | Applies to PPM and reactive | SRC-001 | Warwick @ 1:10:27-1:12:11
NPL-D-013 | 2026-07-08 | Policy/guidance link on Orchestrate start screen: parked | Shared multi-contractor NPL instance (ILS named); NPL-wide vs Smart-specific policy ownership unresolved | Tony | parked | - | NPL-A-012 / NPL-Q-007 | SRC-001 | 1:29:57-1:32:08
NPL-D-014 | 2026-07-08 | PPM data deadline working assumption: ideal within 1 week (before UAT); absolute backstop end of July (post-UAT, pre-go-live live data load) | No formal date agreed yet; PPM training expected next week with UAT immediately after. NOTE: Copilot summary inverted this logic | Warwick (proposed) | working assumption | - | NPL-A-004 | SRC-001 | Warwick @ 4:43-6:00

## Actions
action_id | date_captured | action | owner | due_date | status | related_ids | source_ref | anchor | latest_update
NPL-A-001 | 2026-07-08 | Define mechanism for informing Nick (NPL IT) when a new starter needs adding to the tenant entry group for Concerto SSO access | not stated - likely lands with Adam after NPL-A-003 | not stated | to do | NPL-R-002; NPL-Q-001 | SRC-001 | Warwick @ 2:11-3:00
NPL-A-002 | 2026-07-08 | Define process for downgrading/removing permissions when people leave or change teams (sysadmins especially) | not stated | not stated | to do | NPL-R-003; NPL-C-002 | SRC-001 | Warwick @ 3:00-4:24
NPL-A-003 | 2026-07-08 | Speak to Adam about picking up IT-liaison / no.2 sysadmin role (Travers nomination) | Tony | 2026-07-09 | to do | NPL-A-001/002 | SRC-001 | Tony @ 4:25
NPL-A-004 | 2026-07-08 | Final PPM data pass - send any remaining data updates | Ashley | ideal ~2026-07-15 (pre-UAT); hard stop 2026-07-31 | to do | NPL-D-014 | SRC-001 | Warwick @ 5:00-6:00
NPL-A-005 | 2026-07-08 | Obtain SFG20 API key + schema/secret (likely holder Craig, possibly Jason); then configure | Ashley/Tony obtain; Warwick configure | ahead of further meetings | to do | NPL-R-001; NPL-Q-008 | SRC-001 | 27:43-28:42
NPL-A-006 | 2026-07-08 | Create supplier Smart External Contractor in live, copy down to sandbox | Warwick | not stated | to do - possibly superseded | NPL-D-001/004; NPL-Q-002; NPL-C-003 | SRC-001 | Warwick @ 15:23-16:01; 33:00 | Creation started in session; completion unconfirmed
NPL-A-007 | 2026-07-08 | Send Ashley the user template sheet for uploading subcontractors as supplier operatives; Bellrock runs the upload | Warwick | needed for second data pass | to do | NPL-D-001 | SRC-001 | Warwick @ 40:16-40:56
NPL-A-008 | 2026-07-08 | Collate subcontractor names list and map to the operative column of the PPM activity data | Ashley | with second data pass | to do | NPL-D-001/002 | SRC-001 | 44:43-45:01
NPL-A-009 | 2026-07-08 | Second data pass: assign discipline resource teams (electrical/mechanical/fabric) to maintenance-team jobs; subcontractor jobs to With Contractor | Ashley | with second data pass | to do | NPL-D-008 | SRC-001 | Ashley @ 31:56-32:47
NPL-A-010 | 2026-07-08 | Investigate whether auto job-creation workflow rule can be conditional on previous day completed, and what happens when a day is missed | Warwick | not stated | to do | NPL-D-007; NPL-Q-004 | SRC-001 | Warwick @ 18:35-19:55
NPL-A-011 | 2026-07-08 | Rethink risk-assessment step: one yes/no question wired to No returns task to help desk; discuss with team | Tony | not stated | to do | NPL-D-011; NPL-Q-005 | SRC-001 | Tony @ 1:29:30-1:29:57
NPL-A-012 | 2026-07-08 | Decide policy-link ownership: NPL-wide maintenance risk policy in Orchestrate vs per-contractor | Tony | not stated | to do | NPL-D-013; NPL-Q-007 | SRC-001 | Tony @ 1:31:38
NPL-A-013 | 2026-07-08 | Investigate Operative or Subcontractor option on PPM create-jobs screen - what drives it; wanted for splitting weekly internal runs from long-range subbie runs | Warwick | not stated | to do | NPL-D-008 | SRC-001 | 1:01:56-1:02:45
NPL-A-014 | 2026-07-08 | Check form settings / administration for hidden operative-level filter on job creation | Warwick | not stated | to do | NPL-A-013 | SRC-001 | Warwick @ 1:04:22-1:04:30
NPL-A-015 | 2026-07-08 | Investigate multiples/stacking of automated job-creation workflow rules | Warwick | not stated | to do | NPL-D-007 | SRC-001 | Warwick @ 16:50-17:10
NPL-A-016 | 2026-07-08 | Investigate engineer self-assignment of related/remedial jobs and interaction with PPM remedials-helpdesk triage step | Warwick | not stated | to do | - | SRC-001 | Warwick @ 24:35-25:53
NPL-A-017 | 2026-07-08 | Turn OFF Consumable Order action on PPM jobs (no stock module) | Warwick | not stated | to do | - | SRC-001 | Warwick @ 55:19-55:45
NPL-A-018 | 2026-07-08 | Investigate duplicate Place Job On Hold actions in the PPM action set | Warwick | not stated | to do | - | SRC-001 | Warwick @ 56:07
NPL-A-019 | 2026-07-08 | Re-apply / turn on create-jobs permission in LIVE (prod) FM help desk before next copy-down strips the sandbox fix | Warwick | before next copy-down | to do | NPL-C-001; NPL-R-008 | SRC-001 | Warwick @ 1:33:35 | Silent-failure risk if missed
NPL-A-020 | 2026-07-08 | Work through modular maintenance team structure (single vs electrical/mechanical split) and membership; Ashley handles upload/changes | Tony and Ashley | 2026-07-09 | to do | NPL-D-009; NPL-Q-006 | SRC-001 | Tony @ 1:15:26-1:16:35
NPL-A-021 | 2026-07-08 | Re-run the teams/workforce walkthrough with/for Jason (scheduler) | Warwick | not stated | to do | NPL-D-008 | SRC-001 | Warwick @ 1:19:15

## Risks_Issues
raid_id | type | description | cause_driver | impact | owner | mitigation_discussed | status | source_ref | anchor
NPL-R-001 | risk | SFG20 integration unresolved - the big hairy elephant in the room; go-live impact unknown | Depends on what vendor side (Facilities IQ / Beza - spelling low confidence) will permit; commercial deal needed | Go-live date and scope | Escalated: Travers / Alison / Bellrock senior | Escalated above project level; checklist aspect slotted in later one way or another; NPL-A-005 keeps setup moving | open | SRC-001 | Warwick @ 5:55-8:15
NPL-R-002 | risk | New-starter access gap: sysadmins create Concerto users but without Nick adding them to tenant entry group SSO login fails; no informing mechanism since Tugba left | Live incident: Jason Lewis could not access Orchestrate despite correct account setup | Recurring access failures during rollout; transitional - all NPL email holders in group at go-live | not stated | NPL-A-001 mechanism; NPL-A-003 Adam as IT liaison | open | SRC-001 | Warwick @ 0:36-3:00
NPL-R-003 | risk | Orphaned elevated permissions when people change teams (leavers auto-deactivate; movers do not) | Tugba still had sysadmin access post-departure; SSO route means Smart sysadmins own permissions, not IT (conscious decision) | Inappropriate access - best practice issue not catastrophic | not stated | NPL-A-002 process | open | SRC-001 | Warwick @ 3:00-4:24
NPL-R-004 | risk | Batch-closing: if daily inspections generated too far ahead engineers can close a whole week in one sitting | Ashley described the pattern; Tony confirmed weekly closing happens today | Compliance/audit integrity of daily checks | not stated | Short creation horizon for dailies (24-48h rule later); NPL-D-007 manual-first; per-type visibility variance NPL-Q-009 | open | SRC-001 | Ashley @ 11:38-12:45; Tony @ 20:44
NPL-R-005 | risk | Job creation is irreversible in live - once created they cannot be got back | Concerto platform behaviour | Mass bad-data event if automation enabled prematurely | Warwick | NPL-D-007 manual for first 2-3 months | mitigated by decision | SRC-001 | Warwick @ ~17:30
NPL-R-006 | risk | Engineer resistance to 12 mandatory risk questions per job - compliance fatigue on daily repeat jobs | Andy pushback in reactive session; Warwick: engineers are not gonna like you | Data quality and adoption | Tony | NPL-D-011 single-question SOP-reference pattern; NPL-A-011 | open | SRC-001 | Warwick @ 1:25:50-1:28:58
NPL-R-007 | risk | Shared multi-contractor NPL instance constrains Smart-specific config (e.g. policy link) - ILS also uses the app | Tony raised | Limits NPL-D-013 and any Smart-specific app content | Tony | NPL-wide policy as the route; parked NPL-A-012 | open | SRC-001 | Tony @ 1:31:05-1:31:30
NPL-R-008 | risk | Sandbox-live copy-down can silently strip config divergence - the C-001 sandbox fix will be lost if live not updated first | Warwick self-identified at close | Recurrence of the exact permission bug just fixed | Warwick | NPL-A-019 | open | SRC-001 | Warwick @ 1:33:35
NPL-R-009 | risk | Concerto limitation: no team-level job visibility in Orchestrate - jobs must be manually assigned to a named operative in Concerto Web before appearing in the app; team buckets requested of Concerto and refused; per-team status workaround = administrative hydra | Product limitation confirmed twice; drove Ashley visible disappointment | Manual triage overhead; dependency on supervisors/Jason and weekly planning | accepted constraint | NPL-D-008 operating model; roles-as-operatives pattern offered but not adopted; supervisors use Concerto Web on tablet/laptop | accepted | SRC-001 | Warwick @ 49:11-52:07; 52:28-53:53; 1:14:12

## Config_Changes
config_id | date | change | system_environment | made_by | follow_through | source_ref | anchor
NPL-C-001 | 2026-07-08 | Security profile System Administrator: added Can Create Jobs For The Help Desk (fixed Ashley missing Create Jobs option on PPM Scheduler) | Concerto - SANDBOX | Warwick | Replicate in live before next copy-down - NPL-A-019 | SRC-001 | 26:46-28:57
NPL-C-002 | 2026-07-08 | Tugba access downgraded from system admin to end user (done shortly before meeting, reported here) | Concerto | Warwick | Trigger for NPL-A-002 process | SRC-001 | Warwick @ 2:40-3:20
NPL-C-003 | 2026-07-08 | Smart External Contractor supplier creation STARTED in session; derailed into contractor-vs-supplier confusion; completion not confirmed on transcript | Concerto - sandbox (session context) | Warwick | Confirm whether created; reconcile with NPL-A-006 and NPL-D-001 - see NPL-U-001 | SRC-001 | Warwick @ 33:00-33:35
NPL-C-004 | 2026-07-08 | Demo supplier operative (~Smart Subby One, exact name garbled) created under Smart Managed Services contractor to demonstrate NPL-D-001 | Concerto - sandbox | Warwick | Demo/test data - keep or cleanup decision not taken | SRC-001 | Warwick @ 36:34-38:52
NPL-C-005 | 2026-07-08 | Modular Maintenance resource team created; two operatives added | Concerto - environment not stated (sandbox implied) | Warwick | Structure refinement NPL-A-020; live replication not discussed | SRC-001 | Warwick @ 1:18:22-1:19:15
NPL-C-006 | 2026-07-08 | Permit Team resource team: archive initiated then halted after Tony objection | Concerto - help desk resource teams | Warwick | Confirm final state - NPL-Q-003 | SRC-001 | 1:17:31-1:18:22
NPL-C-007 | 2026-07-08 | Travel-time options turned off in Orchestrate (reported as already done) - engineer actions now start job / place on hold / complete | Orchestrate | Warwick | None | SRC-001 | Warwick @ ~1:20:00

## Open_Questions
q_id | question | parked_with | unblocked_by | status | source_ref | anchor
NPL-Q-001 | Who owns the new-starter/leaver comms process to Nick (NPL IT)? | unassigned | Tony-Adam conversation (NPL-A-003) | open | SRC-001 | Warwick @ 2:11-4:24
NPL-Q-002 | Is the Smart External Contractor supplier still required given the supplier-operative landing (NPL-D-001)? | Warwick | Warwick confirming intended final supplier structure | open | SRC-001 | 15:23 vs 35:23-36:14 vs 38:52
NPL-Q-003 | Permit Team final state: archived from help-desk resource teams or fully retained? | Warwick | Check in sandbox | open | SRC-001 | 1:17:31-1:18:22
NPL-Q-004 | What should happen to a missed daily inspection (mark missed / block next / nothing)? Tony operational view: still gets closed off, 99% sure, usually because pair found and fixed an issue mid-round | Warwick | NPL-A-010 investigation | open | SRC-001 | 19:23-21:36
NPL-Q-005 | Is answer-No-returns-task-to-help-desk existing or future Concerto functionality? | Warwick/Tony | Product clarification | open | SRC-001 | Tony @ 1:29:45
NPL-Q-006 | Modular maintenance: one team or electrical/mechanical split? | Tony and Ashley | NPL-A-020 session 9 July | open | SRC-001 | Ashley @ 1:18:36
NPL-Q-007 | Can the risk policy be NPL-wide (one link) vs per-contractor (clunky)? | Tony | NPL-A-012 | open | SRC-001 | 1:31:05-1:32:08
NPL-Q-008 | Is Craig actually the SFG20 API key holder? Might be Craig or Jason | Ashley/Tony | NPL-A-005 | open | SRC-001 | 28:13-28:19
NPL-Q-009 | Per-type visibility variance (45/60/90 day horizons by PPM type): raised with Concerto last Friday, no satisfactory answer; steer was control via help desk. Standing issue to keep highlighted | Warwick | Concerto product response | open | SRC-001 | Warwick @ 10:00-11:17; Ashley @ 11:23-13:15
NPL-Q-010 | Untraceable dummy job with PPM reference guidance text surfaced in Orchestrate demo - provenance unknown | Ashley | Check sandbox data | open - low priority | SRC-001 | 1:25:00-1:25:34

## Milestones
milestone_id | date | item | committed_by | notes_conditional_logic | source_ref | anchor
NPL-M-001 | w/c 2026-07-13 | PPM training (UAT follows immediately after training) | Warwick (expected) | Date inferred from meeting date + next week | SRC-001 | Warwick @ 5:30
NPL-M-002 | ~2026-07-15 | Ideal final PPM data submission (before UAT) | Ashley (target) | Ideal not formal - see NPL-D-014 | SRC-001 | Warwick @ 5:50
NPL-M-003 | 2026-07-31 | Absolute PPM data backstop - post-UAT, pre-go-live live data load | Warwick (proposed) | One more bite of the cherry before go-live | SRC-001 | Warwick @ 6:00
NPL-M-004 | 2026-07-20 | Reporting and dashboards session with Dave Carr (Bellrock reporting specialist) | Warwick | Scheduled | SRC-001 | Warwick @ 1:06:10
NPL-M-005 | 2026-07-09 | Tony-Adam conversation re IT liaison / no.2 sysadmin | Tony | NPL-A-003 | SRC-001 | Tony @ 4:25
NPL-M-006 | 2026-07-09 | Tony and Ashley modular maintenance team session | Tony | NPL-A-020 | SRC-001 | Tony @ 1:15:26
NPL-M-007 | TBC | Go-live - date not stated this meeting; SFG20 (NPL-R-001) is the acknowledged unknown against it | - | - | SRC-001 | Warwick @ 7:56-8:15
NPL-M-008 | go-live + 2-3 months | Revisit enabling automated job-creation workflow rules | Warwick/support ticket route | Per NPL-D-007; Warwick may have rolled off by then | SRC-001 | Warwick @ 18:00-18:35

## Entities
entity_id | name | type | org | role_notes | aliases_asr_confidence | disambiguation
NPL-E-001 | Warwick Allan | person | Bellrock | Implementation lead / PIM | - | -
NPL-E-002 | Ashley Niven | person | Smart Managed Services | Built PPM schedules/activities; sysadmin user; owns data passes | - | -
NPL-E-003 | Tony Sims | person | Smart Managed Services | Operational manager; site process decision-maker | - | -
NPL-E-004 | Jason (scheduler) | person | Smart Managed Services | Technical scheduler; will monitor PPM help desk and chase/reallocate; possibly on this call silent | - | TWO JASONS - do not conflate with Jason Lewis
NPL-E-005 | Jason Lewis | person | NPL (likely) | Double-barrelled surname incl Lewis; subject of the Orchestrate access failure (NPL-R-002) | - | TWO JASONS - do not conflate with scheduler Jason
NPL-E-006 | Travers | person | not stated (NPL or Smart senior) | Nominated Adam as no.2 sysadmin; requested Jason Lewis account; party to SFG20 talks with Alison | - | Org unresolved - NPL-U-004
NPL-E-007 | Adam (sysadmin nominee) | person | not stated | Travers nominated no.2 system admin; to take IT liaison (NPL-A-003) | - | TWO ADAMS - not the Bellrock MD
NPL-E-008 | Adam (Bellrock MD) | person | Bellrock | Managing Director; referenced SFG20 in daily journals | - | TWO ADAMS - not the sysadmin nominee
NPL-E-009 | Nick | person | NPL IT | Tenant entry group / SSO; role mapping; requested session day before | - | -
NPL-E-010 | Tugba | person | departed project | Previously managed user migration; access downgraded (NPL-C-002); departure = root cause of IT-liaison gap | - | -
NPL-E-011 | Alison | person | likely Bellrock (medium confidence) | Party to SFG20 conversations | - | -
NPL-E-012 | Dave Carr | person | Bellrock | Reporting/dashboard specialist; runs 20 July session | - | -
NPL-E-013 | Craig | person | Smart/NPL (not stated) | Probable SFG20 API key/schema holder - unconfirmed (NPL-Q-008) | - | -
NPL-E-014 | Andy | person | Smart (engineer) | Challenged risk-assessment No behaviour in prior reactive session | - | -
NPL-E-015 | Bob | HYPOTHETICAL | - | Worked example for operative absence scenarios only - NOT a real person | - | Exclude from headcounts
NPL-E-016 | NPL | org | - | Client / site owner; SSO policy owner (drives NPL-D-001) | ASR often MPL (high confidence correction) | -
NPL-E-017 | Smart Managed Services | org | - | Maintenance contractor; exists in Concerto as both contractor (supplier portal) and help-desk operation | - | -
NPL-E-018 | Bellrock | org | - | Implementer | ASR once Bell Ruth (high confidence) | -
NPL-E-019 | ILS | org | - | Another contractor on the NPL Concerto instance (NPL-R-007) | - | -
NPL-E-020 | John O'Connor | org | - | Subcontractor used as live example of batch job creation per supplier | - | -
NPL-E-021 | Facilities IQ / Beza | org | - | SFG20 vendor side | Beza garbled - LOW confidence, verify before external use | -
NPL-E-022 | SFG20 | system/standard | - | Maintenance standards library; source of discipline list; integration pending (NPL-R-001) | ASR variants SF220 / SFD / SFG 20 (high confidence) | -
NPL-E-023 | Concerto | system | Bellrock | CAFM platform; Concerto Web; sandbox + live/prod (FM help desk); known UI bug in Workforce Teams: add-a-new-user-accounts label should read add-a-new-team | - | -
NPL-E-024 | Orchestrate | system | Bellrock | Engineer mobile app; jobs visible only after assignment to named operative; supplier portal is separate | - | -

## Sources
source_id | date_processed | filename | source_type | event_date | duration | immutable_location | extraction_packet | items_extracted | processed_by
SRC-001 | 2026-07-08 | NPL___Concerto_-_Planned_Helpdesk_Playback_Session.vtt (+ docx rendering) | Teams meeting transcript (VTT canonical) | 2026-07-08 09:07 BST (filename stamp 10:07:59 - TZ discrepancy flagged) | 1h 34m 12s | to file: [project]/01_Sources_Immutable/meeting-transcripts/ | 2026-07-08-NPL-PPM-Playback-extraction.md | 14 decisions / 21 actions / 9 risks / 7 config / 10 questions / 8 milestones / 24 entities / 11 uncertainties | Claude - F247.prompt.transcript-extraction v0.1 via Zapier Sheets

## Uncertainty
u_id | item | why_uncertain | resolve_by | status | related_ids
NPL-U-001 | Smart External Contractor supplier - unresolved final state | Agreed 15:23; creation started 33:00; pivoted to Smart Managed Services + supplier operatives (NPL-D-001); Tony rejected renaming; completion never confirmed | Warwick: check sandbox supplier list and confirm intended model | open | NPL-A-006 / NPL-C-003 / NPL-Q-002
NPL-U-002 | Permit Team final state | Archive initiated, objection, clarification, no explicit close | Check sandbox | open | NPL-C-006 / NPL-Q-003
NPL-U-003 | Owners for NPL-A-001/002 never assigned | Likely lands with Adam after NPL-A-003 - inference not record | Tony-Adam conversation outcome | open | NPL-A-001/002/003
NPL-U-004 | Travers and Adam-nominee organisations not stated | NPL vs Smart unclear; two-Adams and two-Jasons collision risk | Warwick knowledge or next meeting | open | NPL-E-006/007
NPL-U-005 | Beza (SFG20 vendor name) | Low-confidence ASR | Verify before writing into external documents | open | NPL-E-021
NPL-U-006 | Jason (scheduler) presence on the call | Implied by garbled Ashley turn; no captured speech | Warwick recollection | open | NPL-E-004
NPL-U-007 | Environment for NPL-C-004/005 (demo operative, modular team) | Sandbox implied by session context, not stated; live replication undiscussed | Check both environments | open | NPL-C-004/005
NPL-U-008 | No-returns-to-help-desk: existing vs future functionality | Tony phrasing suggests future; unconfirmed | Concerto product clarification | open | NPL-Q-005
NPL-U-009 | Recording gap - final 10-15 min (system admin bits) deliberately unrecorded | Any decisions/actions from that segment are outside this packet | Warwick notes for that segment | open | SRC-001
NPL-U-010 | Timestamp discrepancy 09:07 header vs 10:07:59 filename | Assume BST/UTC | Confirm before citing times externally | open | SRC-001
NPL-U-011 | Name of demo supplier operative garbled (Smart Sub E1 / Smart Subby One) | ASR noise | Verify in sandbox before cleanup | open | NPL-C-004