## README
NPL Concerto - Project Registers
Purpose: single register workbook for the NPL Concerto implementation (Bellrock). One tab per register. Populated by the transcript/email intake pipeline (F247.prompt.transcript-extraction v0.1).
Rules: append-only rows. Never silently edit history. Status changes update the status column and note the updating source. Supersession uses supersedes/superseded_by links. Every row carries source_ref + anchor back to the immutable raw source.
ID scheme: NPL-D-xxx decisions, NPL-A-xxx actions, NPL-R-xxx risks/issues, NPL-C-xxx config changes, NPL-Q-xxx open questions, NPL-M-xxx milestones, SRC-xxx sources, NPL-U-xxx uncertainty.
Idempotency: check the Sources tab before processing a file. Already listed = do not re-process.
Project folder: 05_Projects/Work Projects/Bellrock/[project_id] - NPL Concerto Implementation (project_id to be confirmed). Raw sources: 01_Sources_Immutable.
Created: 2026-07-08 by Claude via Zapier Google Sheets.

## Decisions
decision_id | date | decision | rationale | decider | status | supersedes_links | implications | source_ref | anchor | work_package_id | work_package_name
NPL-D-001 | 2026-07-08 | Subcontractors will never be onboarded to Concerto/Orchestrate; represent them as supplier operatives under the Smart Managed Services contractor | NPL policy: no system access without NPL email + SSO. Supplier-operative model gives allocation visibility without access. Warwick explicitly flagged this to capture for the decision log | Warwick (mechanism) / Tony (endorsed) | agreed | - | Drives NPL-A-007/008 subbie upload; supplier data model | SRC-001 | Warwick @ 38:52-39:30
NPL-D-002 | 2026-07-08 | Upload all subcontractor business names into the system, with no access | NPL know the full subcontractor base; helps Jason (scheduler) plan workload | Tony | agreed | - | Feeds NPL-A-008 | SRC-001 | Tony @ 39:56-40:16
NPL-D-003 | 2026-07-08 | Emailing jobs to subcontractors from the system: declined | Option floated by Warwick and immediately refused | Tony | rejected | - | - | SRC-001 | 41:40-42:02
NPL-D-004 | 2026-07-08 | External Contractors resource-team route superseded by supplier-portal / supplier-operative model | Warwick reversed his own prior setup; supplier model separates internal vs subbie work more cleanly | Warwick | superseded | superseded by NPL-D-001 | Redundant resource team cleanup not agreed - see NPL-Q-002 | SRC-001 | Warwick @ 43:47-44:43
NPL-D-005 | 2026-07-08 | PPM Not Completed closure action rejected; incomplete dailies close as PPM complete with remedials | A remedial will always exist per Tony; confirmed again near close | Tony | rejected | - | Vanilla closure actions unchanged | SRC-001 | Tony @ 23:49; Warwick @ 1:20:31
NPL-D-006 | 2026-07-08 | Daily plant-room inspections remain individual daily jobs, each with risk assessment | A requirement for site to record completion, despite admin burden; also lets engineers raise remedials off the daily task | Tony | agreed | - | Engineer workload - see NPL-R-006 | SRC-001 | Tony @ 22:16
NPL-D-007 | 2026-07-08 | Run PPM job creation manually for first 2-3 months; defer automated workflow rules | Jobs created in live are irreversible (NPL-R-005); catch errors first; enable auto later via support ticket | Warwick recommendation; no objection | agreed in principle | - | Post-go-live revisit ~2-3 months | SRC-001 | Warwick @ 16:13-18:35
NPL-D-008 | 2026-07-08 | Allocation model: weekly planning meetings; internal jobs allocated Friday for the following week; subcontractor jobs 1-3 months ahead on a rolling monthly basis | Concerto cannot auto-allocate jobs to teams (NPL-R-009); contractors hard to book in | Tony | agreed in principle | - | Operating model; Jason (scheduler) central | SRC-001 | Tony @ 58:07; 1:00:32
NPL-D-009 | 2026-07-08 | Modular Maintenance resource team added (created live in session) | Roaming maintenance team across a large estate; easier planning | Tony | agreed - structure pending | - | See NPL-A-020 / NPL-Q-006 / NPL-C-005 | SRC-001 | Tony @ 1:15:26; Warwick @ 1:18:22
NPL-D-010 | 2026-07-08 | Permit Team resource team retained; archive halted | Future team of ~7 may review the whole permit situation | Tony | retained - confirm final state | - | See NPL-Q-003 / NPL-C-006 | SRC-001 | 1:17:31-1:18:22
NPL-D-011 | 2026-07-08 | Explore reducing 12 risk questions to a single yes/no risk-awareness confirmation referencing a named SOP (e.g. Risk Assessment Smart 001) | Engineer adoption risk; prior serious injury on site involving another contractor; Tony: risk awareness not risk assessment; desired: answering No returns task to help desk | Tony (owner) | under consideration | - | NPL-A-011; NPL-Q-005 | SRC-001 | 1:25:52-1:29:57
NPL-D-012 | 2026-07-08 | Preset text for completion/hold reasons adopted in principle | New Concerto functionality; contract-aligned selectable wording drops into audit trail; avoids free-text quality issues | All | agreed in principle | - | Applies to PPM and reactive | SRC-001 | Warwick @ 1:10:27-1:12:11
NPL-D-013 | 2026-07-08 | Policy/guidance link on Orchestrate start screen: parked | Shared multi-contractor NPL instance (ILS named); NPL-wide vs Smart-specific policy ownership unresolved | Tony | parked | - | NPL-A-012 / NPL-Q-007 | SRC-001 | 1:29:57-1:32:08
NPL-D-014 | 2026-07-08 | PPM data deadline working assumption: ideal within 1 week (before UAT); absolute backstop end of July (post-UAT, pre-go-live live data load) | No formal date agreed yet; PPM training expected next week with UAT immediately after. NOTE: Copilot summary inverted this logic | Warwick (proposed) | working assumption | - | NPL-A-004 | SRC-001 | Warwick @ 4:43-6:00
NPL-D-015 | 2026-07-10 | Permit module/menu has been renamed to Booking My Contractor | Warwick stated the renamed module/tab is the user-facing route for site users booking contractor permits | Warwick | implemented | - | User-facing naming and SOP/training should refer to Booking My Contractor | SRC-002 | Warwick @ 00:01:06 | WP-014 | Permit To Work
NPL-D-016 | 2026-07-10 | Smart internal permit requests should normally be raised from jobs/reactives/PPMs via the G002 Permit to Work Request action, not the general Booking My Contractor route | Tony clarified Smart's operational route; Warwick demonstrated the job-linked request pulls job/date/description context | Tony / Warwick | agreed | - | Training must distinguish scientist/site-user route from Smart maintenance route | SRC-002 | Tony @ 00:01:43; Warwick @ 00:02:02 | WP-014 | Permit To Work
NPL-D-017 | 2026-07-10 | SSA143 is de-scoped for current electronic permit delivery and should be suppressed rather than deleted | Tony confirmed; Warwick suppressed/confirmed suppression so the type is not selectable while remaining re-enableable later | Tony / Warwick | agreed | - | If NPL later finds an electronic process for SSA143 it can be re-enabled | SRC-002 | Warwick @ 00:12:11; Tony @ 00:12:33 | WP-014 | Permit To Work
NPL-D-018 | 2026-07-10 | Excavation Permit to Dig must be retained/re-enabled | Tony and Carolyn confirmed excavation is still needed after it had been crossed out/suppressed | Tony / Carolyn | agreed | - | Permit type and associated risk/rules need to include excavation | SRC-002 | Tony @ 00:14:07; Carolyn @ 00:48:04 | WP-014 | Permit To Work
NPL-D-019 | 2026-07-10 | HV electrical work should be separated from LV electrical work and route through high-risk handling | Carolyn asked about HV; Tony wanted hard-copy/limited access controls; Warwick created HV as separate high-risk example | Tony / Carolyn / Warwick | agreed in principle | - | Requires high-risk route/team/actions and internal process definition | SRC-002 | Carolyn @ 00:14:17; Warwick @ 00:29:03 | WP-014 | Permit To Work
NPL-D-020 | 2026-07-10 | Use one default permit workflow but differentiate handling through profiles, teams, routes and actions | Warwick explained Permit has one workflow; profile/team/action configuration changes what is available and who can act | Warwick explanation; Tony accepted | operating constraint | - | High-risk and M&E can differ by actions/roles, not wholly separate workflows | SRC-002 | Warwick @ 00:27:43; 01:53:20 | WP-014 | Permit To Work
NPL-D-021 | 2026-07-10 | Every external contractor visit requires a General Works Permit; additional high-risk work also requires the relevant specific permit | Tony stated all contractors need general works and high-risk permits are additional; Warwick linked risks accordingly | Tony / Carolyn / Warwick | agreed | - | Risk-to-permit mappings must always include General Works plus applicable high-risk permit | SRC-002 | Tony @ 00:42:35; Warwick @ 00:45:00 | WP-014 | Permit To Work
NPL-D-022 | 2026-07-10 | Selecting General Works and a high-risk risk does not create duplicate General Works Permits | Warwick tested the scenario live after Ashley queried duplicate general permits; only one General Works Permit appeared | Warwick / Ashley | confirmed in session | - | Duplicate-general-permit concern closed unless future testing contradicts | SRC-002 | Ashley @ 00:50:08; Warwick @ 00:51:47 | WP-014 | Permit To Work
NPL-D-023 | 2026-07-10 | Permit expiry after 12 hours moves the permit to Expired status rather than closing it | Warwick explained status behaviour; Carolyn's concern was monitoring rather than the label itself | Warwick / Carolyn | confirmed | - | Requires dashboard/email/report monitoring of Expired permits | SRC-002 | Warwick @ 00:23:42; Carolyn @ 00:24:47 | WP-014 | Permit To Work
NPL-D-024 | 2026-07-10 | Issued permits should be closed, not cancelled, if the contractor leaves site or the work is stopped after issue | Tony corrected the process: once issued, the permit is closed rather than cancelled/deleted | Tony | agreed | - | Cancel action should only apply before issue; post-issue lifecycle uses Close | SRC-002 | Tony @ 01:31:18 | WP-014 | Permit To Work
NPL-D-025 | 2026-07-10 | Issued permits are legal/controlled records and should not be amended after issue | Warwick confirmed nobody can tweak an issued permit; Tony confirmed legal-document logic | Warwick / Tony | agreed | - | Engineer substitutions or scope changes after issue require management process/re-evaluation/new permit | SRC-002 | Warwick @ 01:27:58; Tony @ 01:28:13 | WP-014 | Permit To Work
NPL-D-026 | 2026-07-10 | Internal Smart engineers generally do not need General Works permits; subcontractors do | Ashley clarified planned maintenance use case: Smart's own engineers only need high-risk permits, but subcontractors require general permits | Ashley / Tony | agreed | - | PPM permit flags require operational judgement on internal vs subcontractor work | SRC-002 | Ashley @ 01:47:00 | WP-014 | Permit To Work
NPL-D-027 | 2026-07-10 | Smart supplier naming should be corrected to Smart Managed Solutions and a separate Smart Managed External Contractors supplier/list should be used for contractor permit selection | Tony corrected Services/Solutions wording and proposed a separate contractor supplier list; Warwick accepted the approach and discussed non-login records | Tony / Warwick | agreed in principle | - | Creates duplicate/parallel contractor list but improves tick-box permit selection | SRC-002 | Tony @ 01:45:45; 01:50:09 | WP-014 | Permit To Work
NPL-D-028 | 2026-07-10 | Separate follow-up session should cover Permit actions/questionnaires in more depth; broader permit training should be scheduled for 2026-07-15 10:00 | Current session did not cover actions fully; Tony suggested using a Thursday morning session and agreed the training slot | Tony / Warwick | agreed in principle | - | See NPL-A-037 and NPL-M-013/NPL-M-014 | SRC-002 | Warwick @ 01:52:23; Tony @ 01:54:10; Warwick @ 01:56:20 | WP-014 | Permit To Work

## Actions
action_id | date_captured | action | owner | due_date | status | related_ids | source_ref | anchor | latest_update | work_package_id | work_package_name
NPL-A-001 | 2026-07-08 | Define mechanism for informing Nick (NPL IT) when a new starter needs adding to the tenant entry group for Concerto SSO access | not stated - likely lands with Adam after NPL-A-003 | not stated | to do | NPL-R-002; NPL-Q-001 | SRC-001 | Warwick @ 2:11-3:00
NPL-A-002 | 2026-07-08 | Define process for downgrading/removing permissions when people leave or change teams (sysadmins especially) | not stated | not stated | to do | NPL-R-003; NPL-C-002 | SRC-001 | Warwick @ 3:00-4:24
NPL-A-003 | 2026-07-08 | Speak to Adam about picking up IT-liaison / no.2 sysadmin role (Travers nomination) | Tony | 2026-07-09 | to do | NPL-A-001/002 | SRC-001 | Tony @ 4:25
NPL-A-004 | 2026-07-08 | Final PPM data pass - send any remaining data updates | Ashley | ideal ~2026-07-15 (pre-UAT); hard stop 2026-07-31 | to do | NPL-D-014 | SRC-001 | Warwick @ 5:00-6:00
NPL-A-005 | 2026-07-08 | Obtain SFG20 API key + schema/secret (likely holder Craig, possibly Jason); then configure | Ashley/Tony obtain; Warwick configure | ahead of further meetings | to do | NPL-R-001; NPL-Q-008 | SRC-001 | 27:43-28:42
NPL-A-006 | 2026-07-08 | Create supplier Smart External Contractor in live, copy down to sandbox | Warwick | not stated | to do - possibly superseded | NPL-D-001/004; NPL-Q-002; NPL-C-003 | SRC-001 | Warwick @ 15:23-16:01; 33:00 | Creation started in session; completion unconfirmed
NPL-A-007 | 2026-07-08 | Send Ashley the user template sheet for uploading subcontractors as supplier operatives; Bellrock runs the upload | Warwick | needed for second data pass | to do | NPL-D-001 | SRC-001 | Warwick @ 40:16-40:56
NPL-A-008 | 2026-07-08 | Collate subcontractor names list and map to the operative column of the PPM activity data | Ashley | with second data pass | to do | NPL-D-001/002 | SRC-001 | 44:43-45:01
NPL-A-009 | 2026-07-08 | Second data pass: assign discipline resource teams (electrical/mechanical/fabric) to maintenance-team jobs; subcontractor jobs to With Contractor | Ashley | with second data pass | to do | NPL-D-008 | SRC-001 | Ashley @ 31:56-32:47
NPL-A-010 | 2026-07-08 | Investigate whether auto job-creation workflow rule can be conditional on previous day completed, and what happens when a day is missed | Warwick | not stated | to do | NPL-D-007; NPL-Q-004 | SRC-001 | Warwick @ 18:35-19:55
NPL-A-011 | 2026-07-08 | Rethink risk-assessment step: one yes/no question wired to No returns task to help desk; discuss with team | Tony | not stated | to do | NPL-D-011; NPL-Q-005 | SRC-001 | Tony @ 1:29:30-1:29:57
NPL-A-012 | 2026-07-08 | Decide policy-link ownership: NPL-wide maintenance risk policy in Orchestrate vs per-contractor | Tony | not stated | to do | NPL-D-013; NPL-Q-007 | SRC-001 | Tony @ 1:31:38
NPL-A-013 | 2026-07-08 | Investigate Operative or Subcontractor option on PPM create-jobs screen - what drives it; wanted for splitting weekly internal runs from long-range subbie runs | Warwick | not stated | to do | NPL-D-008 | SRC-001 | 1:01:56-1:02:45
NPL-A-014 | 2026-07-08 | Check form settings / administration for hidden operative-level filter on job creation | Warwick | not stated | to do | NPL-A-013 | SRC-001 | Warwick @ 1:04:22-1:04:30
NPL-A-015 | 2026-07-08 | Investigate multiples/stacking of automated job-creation workflow rules | Warwick | not stated | to do | NPL-D-007 | SRC-001 | Warwick @ 16:50-17:10
NPL-A-016 | 2026-07-08 | Investigate engineer self-assignment of related/remedial jobs and interaction with PPM remedials-helpdesk triage step | Warwick | not stated | to do | - | SRC-001 | Warwick @ 24:35-25:53
NPL-A-017 | 2026-07-08 | Turn OFF Consumable Order action on PPM jobs (no stock module) | Warwick | not stated | to do | - | SRC-001 | Warwick @ 55:19-55:45
NPL-A-018 | 2026-07-08 | Investigate duplicate Place Job On Hold actions in the PPM action set | Warwick | not stated | to do | - | SRC-001 | Warwick @ 56:07
NPL-A-019 | 2026-07-08 | Re-apply / turn on create-jobs permission in LIVE (prod) FM help desk before next copy-down strips the sandbox fix | Warwick | before next copy-down | to do | NPL-C-001; NPL-R-008 | SRC-001 | Warwick @ 1:33:35 | Silent-failure risk if missed
NPL-A-020 | 2026-07-08 | Work through modular maintenance team structure (single vs electrical/mechanical split) and membership; Ashley handles upload/changes | Tony and Ashley | 2026-07-09 | to do | NPL-D-009; NPL-Q-006 | SRC-001 | Tony @ 1:15:26-1:16:35
NPL-A-021 | 2026-07-08 | Re-run the teams/workforce walkthrough with/for Jason (scheduler) | Warwick | not stated | to do | NPL-D-008 | SRC-001 | Warwick @ 1:19:15
NPL-A-022 | 2026-07-10 | Collate Smart contractor company names plus engineer/user list for supplier/operative setup | Tony / Ashley | by end of week | to do | NPL-D-027; NPL-C-021 | SRC-002 | Tony @ 00:04:15-00:04:41 |  | WP-014 | Permit To Work
NPL-A-023 | 2026-07-10 | Create or configure Smart external/subcontractor dropdown/list so Smart-used contractors can be selected for permits | Warwick / Bellrock with Smart input | not stated | to do | NPL-D-027 | SRC-002 | Tony @ 00:07:00; Warwick @ 01:51:46 |  | WP-014 | Permit To Work
NPL-A-024 | 2026-07-10 | Update SOP/training guidance so scientist/site-user route uses NPL External Contractor and explains how to handle RAMS/job-specific documents | Smart / NPL process owner | before user training/go-live | to do | NPL-D-016; NPL-R-011 | SRC-002 | Warwick @ 00:06:49; 00:10:15 |  | WP-014 | Permit To Work
NPL-A-025 | 2026-07-10 | Re-enable or recreate Excavation Permit to Dig and associated risk/rule mapping | Warwick | done in session / verify | in progress | NPL-D-018; NPL-C-011 | SRC-002 | Warwick @ 00:17:33; Carolyn @ 00:48:04 | Verify final naming before go-live | WP-014 | Permit To Work
NPL-A-026 | 2026-07-10 | Define HV permit internal process, including hard-copy handling and who can authorise/issue | Tony / Carolyn / Smart | not stated | to do | NPL-D-019; NPL-R-017; NPL-Q-017 | SRC-002 | Tony @ 00:14:47-00:16:10 |  | WP-014 | Permit To Work
NPL-A-027 | 2026-07-10 | Configure high-risk profile/team/route for HV and other specialist permits | Warwick | done in session / verify | in progress | NPL-D-019; NPL-C-014 | SRC-002 | Warwick @ 00:32:48-00:37:20 |  | WP-014 | Permit To Work
NPL-A-028 | 2026-07-10 | Tidy permit risk wording and capitalisation before go-live | Warwick | not stated | to do | NPL-C-018; NPL-U-020 | SRC-002 | Warwick @ 00:49:34 |  | WP-014 | Permit To Work
NPL-A-029 | 2026-07-10 | Speak to devs / investigate why some Permit form records cannot be deleted or saved unless linked to a form | Warwick / Bellrock dev | not stated | to do | NPL-R-020 | SRC-002 | Warwick @ 01:13:04 |  | WP-014 | Permit To Work
NPL-A-030 | 2026-07-10 | Identify any additional permit types, room/location rules, equipment-type rules or PPM-type rules required | Tony / Ashley / Carolyn | by month end | to do | NPL-Q-016 | SRC-002 | Warwick @ 00:55:54; 00:56:52 |  | WP-014 | Permit To Work
NPL-A-031 | 2026-07-10 | Create appropriate roof/area/room records and link assets/equipment where Working at Height rules should be triggered by location | Ashley / Smart data owner | not stated | to do | NPL-Q-018 | SRC-002 | Warwick @ 01:05:34; Ashley @ 01:06:04 |  | WP-014 | Permit To Work
NPL-A-032 | 2026-07-10 | Review the reactive risk assessment form/questionnaire because 12 questions on every job may be excessive | Tony / Smart | not stated | to do | NPL-D-011; NPL-R-006 | SRC-002 | Tony @ 01:18:39 | This links back to previous reactive/PPM risk discussion | WP-014 | Permit To Work
NPL-A-033 | 2026-07-10 | Build and link remaining Permit forms/form parts for each permit type, including authorisation and acceptance sections | Warwick | over next week | to do | NPL-C-022 | SRC-002 | Warwick @ 01:19:31 | Includes Working at Height, Permit to Dig, LV/HV and related form parts | WP-014 | Permit To Work
NPL-A-034 | 2026-07-10 | If required, create an action from Permit Pending back to Evaluation so authorised-not-issued permits can be recalled for edits before issue | Warwick / Smart decision needed | not stated | proposed | NPL-R-018; NPL-Q-014 | SRC-002 | Warwick @ 01:23:55 | Workaround for status-based edit control limitation | WP-014 | Permit To Work
NPL-A-035 | 2026-07-10 | Document management process for last-minute engineer substitutions and whether to edit pending permit or issue a new permit | Smart / NPL permit process owner | before go-live/training | to do | NPL-D-025; NPL-R-017 | SRC-002 | Ashley @ 01:25:43; Carolyn @ 01:38:07 |  | WP-014 | Permit To Work
NPL-A-036 | 2026-07-10 | Book follow-up session for Permit actions/questionnaires with Warwick, Tony, Ashley and relevant permit admins | Warwick / Tony | next Thursday morning if available | to do | NPL-D-028 | SRC-002 | Tony @ 01:54:10 |  | WP-014 | Permit To Work
NPL-A-037 | 2026-07-10 | Send Permit training invite for Wednesday 15 July 10:00, 90 minutes, to Travers, Tony, Jason, Gainsborough, Craig Wakefield and Kerry; Tony/Ashley to cascade to Zelea and Ashley | Warwick; Tony/Ashley cascade | 2026-07-15 10:00 | to do | NPL-M-013 | SRC-002 | Warwick @ 01:56:20; Tony @ 01:57:12 | Check Ashley included in every training session | WP-014 | Permit To Work
NPL-A-038 | 2026-07-10 | Correct Smart Managed Services to Smart Managed Solutions in live so next copy-down captures the naming | Warwick | done in session / verify | in progress | NPL-D-027; NPL-C-021 | SRC-002 | Tony @ 01:45:45; Warwick @ 01:45:53 | Environment noted as live by Warwick; verify | WP-014 | Permit To Work
NPL-A-039 | 2026-07-10 | Create non-login name-tag accounts/operatives for contractors once Smart provides the list | Bellrock / Warwick | after list received | to do | NPL-D-027 | SRC-002 | Warwick @ 01:51:46 |  | WP-014 | Permit To Work
NPL-A-040 | 2026-07-10 | Send the session recording/transcript to attendees | Warwick | not stated | to do | SRC-002 | SRC-002 | Warwick @ 01:11:28 |  | WP-014 | Permit To Work

## Risks_Issues
raid_id | type | description | cause_driver | impact | owner | mitigation_discussed | status | source_ref | anchor | work_package_id | work_package_name
NPL-R-001 | risk | SFG20 integration unresolved - the big hairy elephant in the room; go-live impact unknown | Depends on what vendor side (Facilities IQ / Beza - spelling low confidence) will permit; commercial deal needed | Go-live date and scope | Escalated: Travers / Alison / Bellrock senior | Escalated above project level; checklist aspect slotted in later one way or another; NPL-A-005 keeps setup moving | open | SRC-001 | Warwick @ 5:55-8:15
NPL-R-002 | risk | New-starter access gap: sysadmins create Concerto users but without Nick adding them to tenant entry group SSO login fails; no informing mechanism since Tugba left | Live incident: Jason Lewis could not access Orchestrate despite correct account setup | Recurring access failures during rollout; transitional - all NPL email holders in group at go-live | not stated | NPL-A-001 mechanism; NPL-A-003 Adam as IT liaison | open | SRC-001 | Warwick @ 0:36-3:00
NPL-R-003 | risk | Orphaned elevated permissions when people change teams (leavers auto-deactivate; movers do not) | Tugba still had sysadmin access post-departure; SSO route means Smart sysadmins own permissions, not IT (conscious decision) | Inappropriate access - best practice issue not catastrophic | not stated | NPL-A-002 process | open | SRC-001 | Warwick @ 3:00-4:24
NPL-R-004 | risk | Batch-closing: if daily inspections generated too far ahead engineers can close a whole week in one sitting | Ashley described the pattern; Tony confirmed weekly closing happens today | Compliance/audit integrity of daily checks | not stated | Short creation horizon for dailies (24-48h rule later); NPL-D-007 manual-first; per-type visibility variance NPL-Q-009 | open | SRC-001 | Ashley @ 11:38-12:45; Tony @ 20:44
NPL-R-005 | risk | Job creation is irreversible in live - once created they cannot be got back | Concerto platform behaviour | Mass bad-data event if automation enabled prematurely | Warwick | NPL-D-007 manual for first 2-3 months | mitigated by decision | SRC-001 | Warwick @ ~17:30
NPL-R-006 | risk | Engineer resistance to 12 mandatory risk questions per job - compliance fatigue on daily repeat jobs | Andy pushback in reactive session; Warwick: engineers are not gonna like you | Data quality and adoption | Tony | NPL-D-011 single-question SOP-reference pattern; NPL-A-011 | open | SRC-001 | Warwick @ 1:25:50-1:28:58
NPL-R-007 | risk | Shared multi-contractor NPL instance constrains Smart-specific config (e.g. policy link) - ILS also uses the app | Tony raised | Limits NPL-D-013 and any Smart-specific app content | Tony | NPL-wide policy as the route; parked NPL-A-012 | open | SRC-001 | Tony @ 1:31:05-1:31:30
NPL-R-008 | risk | Sandbox-live copy-down can silently strip config divergence - the C-001 sandbox fix will be lost if live not updated first | Warwick self-identified at close | Recurrence of the exact permission bug just fixed | Warwick | NPL-A-019 | open | SRC-001 | Warwick @ 1:33:35
NPL-R-009 | risk | Concerto limitation: no team-level job visibility in Orchestrate - jobs must be manually assigned to a named operative in Concerto Web before appearing in the app; team buckets requested of Concerto and refused; per-team status workaround = administrative hydra | Product limitation confirmed twice; drove Ashley visible disappointment | Manual triage overhead; dependency on supervisors/Jason and weekly planning | accepted constraint | NPL-D-008 operating model; roles-as-operatives pattern offered but not adopted; supervisors use Concerto Web on tablet/laptop | accepted | SRC-001 | Warwick @ 49:11-52:07; 52:28-53:53; 1:14:12
NPL-R-010 | risk | Supplier/operative model for Permit to Work is still partly unsettled between supplier dropdown, non-login operative records and free-text engineer fields | Smart/NPL need contractor names visible in permits but Smart also exists as internal maintenance team; duplicate list may be required | Maintaining two lists creates admin overhead; free text reduces control and audit quality | Warwick / Tony | Use separate Smart Managed External Contractors supplier/list if accepted; otherwise use typed engineer details | open | SRC-002 | Warwick @ 01:45:26-01:51:59 | WP-014 | Permit To Work
NPL-R-011 | risk | Hard-coded mandatory Permit fields and document attachment labels cannot be changed to Smart/NPL wording | Concerto vanilla fields include job-specific documentation/PPE fields and cannot be removed or renamed by configuration | Users may misunderstand where to attach RAMS or what information is mandatory | Smart / Warwick | Cover in SOP/training; use custom fields where possible | open | SRC-002 | Warwick @ 00:08:25-00:10:27 | WP-014 | Permit To Work
NPL-R-012 | risk | Permit application and attached questionnaire/forms can duplicate RAMS/document information | Platform behaviour when questionnaires/forms are attached to permits; Warwick has raised it with dev | Duplicate data capture could frustrate users and create inconsistent records | Warwick / Bellrock dev | Known dev pipeline item; keep process lean in configuration | open | SRC-002 | Warwick @ 00:08:25; 01:15:07 | WP-014 | Permit To Work
NPL-R-013 | issue | 12-hour permit expiry conflicts with multi-day work and the earlier one-per-duration concept | Permits can expire after 12 hours but some contractor jobs span days; stakeholders debated daily vs multi-day permit management | Unresolved process could create compliance gaps or administrative nightmare | Smart / NPL process owner | Define management process; daily re-assessment/check-in may be needed; new permit if conditions/personnel change | open | SRC-002 | Carolyn @ 01:33:38; Zelea @ 01:34:41; Tony @ 01:35:27 | WP-014 | Permit To Work
NPL-R-014 | risk | Expired permits may not be acted upon quickly if dashboard/email/report ownership is not defined | Permits move to Expired status, not Closed; notifications depend on configured recipients/reports | Contractors could remain on site or permits remain unmanaged after expiry | Smart / NPL Controller of Works | Use dashboard, e-mail notifications or scheduled expired-permits report | open | SRC-002 | Warwick @ 00:23:42-00:25:30; Carolyn @ 00:24:47 | WP-014 | Permit To Work
NPL-R-015 | risk | Permit rules may over-trigger or under-trigger because rules are at room/location/equipment type/PPM type rather than individual asset level | Ashley/Carolyn explored asset/equipment scenarios; individual asset-level specificity was unclear or unavailable | Help desk may see too many permit flags or miss specific asset-based hazards | Ashley / Warwick | Use area/room such as Roof, PPM type, equipment type or location workaround; confirm asset-level capability | open | SRC-002 | Ashley @ 01:02:59; Warwick @ 01:05:34 | WP-014 | Permit To Work
NPL-R-016 | risk | Issued permits cannot be amended, so last-minute personnel substitutions require a disciplined process | Permit is issued to named competent people; issued permit is not editable | Incompetent/unverified person could work under a permit if process is bypassed | Smart / NPL permit team | Edit before issue while Permit Pending; if issued or personnel/scope changes, re-evaluate or issue new permit | open | SRC-002 | Ashley @ 01:25:43; Warwick @ 01:27:42-01:28:17; Tony @ 01:37:55 | WP-014 | Permit To Work
NPL-R-017 | risk | Permit has one workflow only, so specialist processes such as HV cannot have fully separate workflows | Concerto Permit module supports one workflow with different action sets, profiles, teams and routes | High-risk/HV requirements may need workarounds rather than ideal process design | Warwick / Smart | Use High Risk profile, High Risk Team, roles and action sets; document hard-copy steps | open | SRC-002 | Warwick @ 00:27:43-00:29:03; 01:53:20 | WP-014 | Permit To Work
NPL-R-018 | risk | Permit Admin vs Authorised Person edit controls cannot currently be reduced exactly as Tony requested | System does not support limiting permit admin edits to only certain statuses in the desired way | Authorisation/edit segregation may not match NPL control expectations | Warwick / Bellrock product | Possible workaround: action from Permit Pending back to Evaluation; capture as development point | open | SRC-002 | Tony @ 01:22:52; Warwick @ 01:23:07-01:24:31 | WP-014 | Permit To Work
NPL-R-019 | risk | PPM permit flags do not enforce permit creation | Rules are alerts/notifications on help desk; someone still has to raise the permit | Required permits could be missed if help desk triage ignores flags | Jason / Smart scheduler / supervisors | Training and operating procedure must state how PPM flags are triaged | open | SRC-002 | Warwick @ 01:01:36-01:02:09; 01:48:19 | WP-014 | Permit To Work
NPL-R-020 | issue | Permit form section has a delete/save quirk or bug | Warwick noted forms cannot be deleted/saved unless linked to a form first | Configuration cleanup can be awkward and may leave suppressed legacy records | Warwick / Bellrock dev | Investigate and/or suppress records instead of deleting | open | SRC-002 | Warwick @ 01:13:04 | WP-014 | Permit To Work
NPL-R-021 | risk | Configuration was demonstrated across live and sandbox contexts, creating environment certainty risk | Warwick switched between live and sandbox/preview; some changes were described as live, others implied or demo only | Config could be missed in the final environment or lost on copy-down | Warwick | Verify final live vs sandbox state after session | open | SRC-002 | Warwick @ 00:22:29; 01:43:48; 01:45:53 | WP-014 | Permit To Work
NPL-R-022 | risk | General Works minimum selection wording may still confuse users even though field is mandatory | Ashley worried users may not select General Works or may select too many; mandatory selection helps but wording still matters | Wrong risk selection could drive wrong permit outputs | Smart / Warwick | Reword General Works as minimum needed / clearer wording before training | open | SRC-002 | Ashley @ 00:50:08-00:54:34 | WP-014 | Permit To Work
NPL-R-023 | issue | PPM questionnaires/checklists route remains TBD pending SFG20 resolution | Warwick noted PPM questionnaires/forms exist but how SFG20 checklists get there is still to be decided | PPM checklist implementation remains dependent on unresolved SFG20/PPM path | Warwick / Bellrock / Smart | Track against existing SFG20 dependency and revisit when integration approach is fixed | open | SRC-002 | Warwick @ 01:17:36 | WP-014 | Permit To Work

## Config_Changes
config_id | date | change | system_environment | made_by | follow_through | source_ref | anchor | work_package_id | work_package_name
NPL-C-001 | 2026-07-08 | Security profile System Administrator: added Can Create Jobs For The Help Desk (fixed Ashley missing Create Jobs option on PPM Scheduler) | Concerto - SANDBOX | Warwick | Replicate in live before next copy-down - NPL-A-019 | SRC-001 | 26:46-28:57
NPL-C-002 | 2026-07-08 | Tugba access downgraded from system admin to end user (done shortly before meeting, reported here) | Concerto | Warwick | Trigger for NPL-A-002 process | SRC-001 | Warwick @ 2:40-3:20
NPL-C-003 | 2026-07-08 | Smart External Contractor supplier creation STARTED in session; derailed into contractor-vs-supplier confusion; completion not confirmed on transcript | Concerto - sandbox (session context) | Warwick | Confirm whether created; reconcile with NPL-A-006 and NPL-D-001 - see NPL-U-001 | SRC-001 | Warwick @ 33:00-33:35
NPL-C-004 | 2026-07-08 | Demo supplier operative (~Smart Subby One, exact name garbled) created under Smart Managed Services contractor to demonstrate NPL-D-001 | Concerto - sandbox | Warwick | Demo/test data - keep or cleanup decision not taken | SRC-001 | Warwick @ 36:34-38:52
NPL-C-005 | 2026-07-08 | Modular Maintenance resource team created; two operatives added | Concerto - environment not stated (sandbox implied) | Warwick | Structure refinement NPL-A-020; live replication not discussed | SRC-001 | Warwick @ 1:18:22-1:19:15
NPL-C-006 | 2026-07-08 | Permit Team resource team: archive initiated then halted after Tony objection | Concerto - help desk resource teams | Warwick | Confirm final state - NPL-Q-003 | SRC-001 | 1:17:31-1:18:22
NPL-C-007 | 2026-07-08 | Travel-time options turned off in Orchestrate (reported as already done) - engineer actions now start job / place on hold / complete | Orchestrate | Warwick | None | SRC-001 | Warwick @ ~1:20:00
NPL-C-008 | 2026-07-10 | Permit module/menu/tab renamed to Booking My Contractor | Concerto Permit module - environment not explicitly stated | Warwick | Use this label in SOP/training | SRC-002 | Warwick @ 00:01:06 | WP-014 | Permit To Work
NPL-C-009 | 2026-07-10 | Custom permit request fields added: contractor name, lead engineer, engineer 1/2/3, vehicle registration, emergency/planned works, work sponsor/in person | Concerto Permit request form | Warwick | Validate final labels/order before training | SRC-002 | Warwick @ 00:02:42-00:03:28 | WP-014 | Permit To Work
NPL-C-010 | 2026-07-10 | SSA143 and several out-of-scope vanilla permit types suppressed/de-scoped | Concerto Permit types | Warwick | SSA143 can be re-enabled later if NPL develops electronic route | SRC-002 | Warwick @ 00:12:11-00:13:14 | WP-014 | Permit To Work
NPL-C-011 | 2026-07-10 | Excavation Permit to Dig re-enabled/created with 12-hour expiry | Concerto Permit types - live implied after Warwick said he would do it in live | Warwick | Verify final formal wording and associated forms/rules | SRC-002 | Warwick @ 00:17:33-00:23:04 | WP-014 | Permit To Work
NPL-C-012 | 2026-07-10 | HV electrical permit created separately from LV electrical permit with 12-hour expiry | Concerto Permit types | Warwick | Link to High Risk profile/team/actions and review hard-copy process | SRC-002 | Warwick @ 00:29:03-00:30:00 | WP-014 | Permit To Work
NPL-C-013 | 2026-07-10 | Non-M&E profile renamed to High Risk | Concerto Permit profiles | Warwick | Use for HV/high-risk routing | SRC-002 | Warwick @ 00:32:28-00:33:04 | WP-014 | Permit To Work
NPL-C-014 | 2026-07-10 | High Risk Team created and linked to High Risk profile/HV electrical route | Concerto Permit teams/routes | Warwick | Confirm membership and final route coverage | SRC-002 | Warwick @ 00:34:47-00:37:20 | WP-014 | Permit To Work
NPL-C-015 | 2026-07-10 | Permit Team membership updated with Tony, Ashley and Carolyn/Kerry as available users; Nick not enabled in that area yet | Concerto Permit team | Warwick | Verify membership and Nick enablement if needed | SRC-002 | Warwick @ 00:34:27-00:34:47 | WP-014 | Permit To Work
NPL-C-016 | 2026-07-10 | Authorised Person role updated to add Ashley and Carolyn/Kerry | Concerto Permit roles | Warwick | Verify exact role membership and spelling | SRC-002 | Warwick @ 00:37:29-00:38:25 | WP-014 | Permit To Work
NPL-C-017 | 2026-07-10 | General Works Permit created and General Works risk linked to General Works Permit plus specific high-risk permits | Concerto Permit types/risks/rules | Warwick | Validate every risk-to-permit mapping | SRC-002 | Warwick @ 00:43:49-00:45:13 | WP-014 | Permit To Work
NPL-C-018 | 2026-07-10 | Permit risk list configured to include General Works, Lifting Operations, Hot Works, Working at Height, Confined Space, HV electrical, LV electrical, and excavation/digging | Concerto Permit risks | Warwick | Formalise wording/capitalisation before go-live | SRC-002 | Warwick @ 00:47:39-00:49:34 | WP-014 | Permit To Work
NPL-C-019 | 2026-07-10 | 00 TBD PPE item suppressed from Permit PPE list | Concerto Permit personal equipment list | Warwick | Confirm no TBD appears on issued permits | SRC-002 | Warwick @ 01:09:57-01:11:05 | WP-014 | Permit To Work
NPL-C-020 | 2026-07-10 | Permit Admin role created as an empty/example role for form-editing discussion | Concerto Permit roles | Warwick | Decide whether to use or remove/suppress after process design | SRC-002 | Warwick @ 01:22:24-01:22:52 | WP-014 | Permit To Work
NPL-C-021 | 2026-07-10 | Smart Managed Services/Solutions supplier naming discussed and Smart Managed External Contractors supplier/list started or proposed | Concerto Supplier/Permit selection - live/sandbox mixed | Warwick / Tony | Verify final supplier records in live and sandbox | SRC-002 | Tony @ 01:45:45-01:51:46 | WP-014 | Permit To Work
NPL-C-022 | 2026-07-10 | Permit questionnaire/form parts exist for Hot Work, Hot Work Authorisation and Hot Work Acceptance; remaining forms need build/linking | Concerto Questionnaires and Permit Forms | Warwick | Build remaining permit-specific forms and release questionnaires for use | SRC-002 | Warwick @ 01:15:48-01:19:31 | WP-014 | Permit To Work

## Open_Questions
q_id | question | parked_with | unblocked_by | status | source_ref | anchor | work_package_id | work_package_name
NPL-Q-001 | Who owns the new-starter/leaver comms process to Nick (NPL IT)? | unassigned | Tony-Adam conversation (NPL-A-003) | open | SRC-001 | Warwick @ 2:11-4:24
NPL-Q-002 | Is the Smart External Contractor supplier still required given the supplier-operative landing (NPL-D-001)? | Warwick | Warwick confirming intended final supplier structure | open | SRC-001 | 15:23 vs 35:23-36:14 vs 38:52
NPL-Q-003 | Permit Team final state: archived from help-desk resource teams or fully retained? | Warwick | Check in sandbox | open | SRC-001 | 1:17:31-1:18:22
NPL-Q-004 | What should happen to a missed daily inspection (mark missed / block next / nothing)? Tony operational view: still gets closed off, 99% sure, usually because pair found and fixed an issue mid-round | Warwick | NPL-A-010 investigation | open | SRC-001 | 19:23-21:36
NPL-Q-005 | Is answer-No-returns-task-to-help-desk existing or future Concerto functionality? | Warwick/Tony | Product clarification | open | SRC-001 | Tony @ 1:29:45
NPL-Q-006 | Modular maintenance: one team or electrical/mechanical split? | Tony and Ashley | NPL-A-020 session 9 July | open | SRC-001 | Ashley @ 1:18:36
NPL-Q-007 | Can the risk policy be NPL-wide (one link) vs per-contractor (clunky)? | Tony | NPL-A-012 | open | SRC-001 | 1:31:05-1:32:08
NPL-Q-008 | Is Craig actually the SFG20 API key holder? Might be Craig or Jason | Ashley/Tony | NPL-A-005 | open | SRC-001 | 28:13-28:19
NPL-Q-009 | Per-type visibility variance (45/60/90 day horizons by PPM type): raised with Concerto last Friday, no satisfactory answer; steer was control via help desk. Standing issue to keep highlighted | Warwick | Concerto product response | open | SRC-001 | Warwick @ 10:00-11:17; Ashley @ 11:23-13:15
NPL-Q-010 | Untraceable dummy job with PPM reference guidance text surfaced in Orchestrate demo - provenance unknown | Ashley | Check sandbox data | open - low priority | SRC-001 | 1:25:00-1:25:34
NPL-Q-011 | Should the Expired status be renamed, or is the process/reporting around expired permits sufficient? | Carolyn / Tony | Decision by permit process owner | open | SRC-002 | Tony @ 00:26:15; Carolyn @ 00:26:36 | WP-014 | Permit To Work
NPL-Q-012 | How should 12-hour expiry work for multi-day permits: daily permits, one permit with daily check-in/out, or another process? | Smart / NPL | Documented permit management process | open | SRC-002 | Carolyn @ 01:33:38; Tony @ 01:35:27 | WP-014 | Permit To Work
NPL-Q-013 | When a different engineer attends than originally expected, when can the pending permit be edited and when is a new permit required? | Smart / NPL | Policy on competence/accreditation recheck and issued-permit amendments | open | SRC-002 | Ashley @ 01:25:43; Carolyn @ 01:36:20 | WP-014 | Permit To Work
NPL-Q-014 | Can Permit Admin and Authorised Person edit powers be split by status in a way that meets NPL control expectations? | Warwick / Bellrock product | Confirm product capability or implement action-based workaround | open | SRC-002 | Tony @ 01:22:52; Warwick @ 01:23:55 | WP-014 | Permit To Work
NPL-Q-015 | Will Smart maintain two operative/contractor lists for permit selection, or use Smart Managed Solutions plus typed engineer names? | Tony / Ashley | Final supplier/list administration decision | open | SRC-002 | Warwick @ 01:49:30-01:51:59 | WP-014 | Permit To Work
NPL-Q-016 | Which additional permit types and which room/location/equipment/PPM rules need to be configured before go-live? | Tony / Ashley / Carolyn | Month-end rule/config review | open | SRC-002 | Warwick @ 00:55:54-00:56:52 | WP-014 | Permit To Work
NPL-Q-017 | What is the final HV hard-copy and authorisation process, and how much of it should be represented electronically? | Tony / Carolyn | Smart/NPL process definition | open | SRC-002 | Tony @ 00:14:47-00:16:10; Warwick @ 00:27:43 | WP-014 | Permit To Work
NPL-Q-018 | Can permits be triggered at individual asset level, or only by asset/equipment type, PPM type and location? | Ashley / Warwick | Product check and core-data workaround decision | open | SRC-002 | Ashley @ 01:02:59; Warwick @ 01:05:34 | WP-014 | Permit To Work
NPL-Q-019 | What is the exact final spelling/name for the Smart supplier records: Smart Managed Solutions and Smart Managed External Contractors? | Tony / Warwick | Verify supplier records in system | open | SRC-002 | Tony @ 01:45:45; 01:50:56 | WP-014 | Permit To Work
NPL-Q-020 | Who exactly should receive the 15 July permit training invite and who will cascade it to Zelea/Ashley? | Warwick / Tony / Ashley | Final invite list and calendar send | open | SRC-002 | Warwick @ 01:57:12-01:57:35 | WP-014 | Permit To Work
NPL-Q-021 | How will PPM checklists become questionnaires/forms once SFG20 resolves? | Warwick / Bellrock | SFG20/PPM implementation approach | open | SRC-002 | Warwick @ 01:17:36 | WP-014 | Permit To Work

## Milestones
milestone_id | date | item | committed_by | notes_conditional_logic | source_ref | anchor | work_package_id | work_package_name
NPL-M-001 | w/c 2026-07-13 | PPM training (UAT follows immediately after training) | Warwick (expected) | Date inferred from meeting date + next week | SRC-001 | Warwick @ 5:30
NPL-M-002 | ~2026-07-15 | Ideal final PPM data submission (before UAT) | Ashley (target) | Ideal not formal - see NPL-D-014 | SRC-001 | Warwick @ 5:50
NPL-M-003 | 2026-07-31 | Absolute PPM data backstop - post-UAT, pre-go-live live data load | Warwick (proposed) | One more bite of the cherry before go-live | SRC-001 | Warwick @ 6:00
NPL-M-004 | 2026-07-20 | Reporting and dashboards session with Dave Carr (Bellrock reporting specialist) | Warwick | Scheduled | SRC-001 | Warwick @ 1:06:10
NPL-M-005 | 2026-07-09 | Tony-Adam conversation re IT liaison / no.2 sysadmin | Tony | NPL-A-003 | SRC-001 | Tony @ 4:25
NPL-M-006 | 2026-07-09 | Tony and Ashley modular maintenance team session | Tony | NPL-A-020 | SRC-001 | Tony @ 1:15:26
NPL-M-007 | TBC | Go-live - date not stated this meeting; SFG20 (NPL-R-001) is the acknowledged unknown against it | - | - | SRC-001 | Warwick @ 7:56-8:15
NPL-M-008 | go-live + 2-3 months | Revisit enabling automated job-creation workflow rules | Warwick/support ticket route | Per NPL-D-007; Warwick may have rolled off by then | SRC-001 | Warwick @ 18:00-18:35
NPL-M-009 | 2026-07-12 approx / end of week | Smart contractor company names plus engineer/user list to be collated | Tony / Ashley | End of week stated in session; date inferred from current week | SRC-002 | Tony @ 00:04:15-00:04:41 | WP-014 | Permit To Work
NPL-M-010 | 2026-07-31 | Additional permit-type and rule requirements to be identified by month end | Smart / NPL | Warwick left action with them by month end | SRC-002 | Warwick @ 00:55:54 | WP-014 | Permit To Work
NPL-M-011 | w/c 2026-07-13 | Warwick to build/link remaining Permit forms over the next week | Warwick | Exact completion date not stated | SRC-002 | Warwick @ 01:19:31 | WP-014 | Permit To Work
NPL-M-012 | 2026-07-16 morning | Follow-up session for Permit actions/questionnaires with small group | Tony / Warwick | Next Thursday morning from 2026-07-10 context; confirm calendar | SRC-002 | Tony @ 01:54:10 | WP-014 | Permit To Work
NPL-M-013 | 2026-07-15 10:00 | Permit training session, 90 minutes | Warwick | Invite to Tony/Ashley/cascade group; Tony unavailable morning but said should not stop everyone else | SRC-002 | Warwick @ 01:56:20 | WP-014 | Permit To Work

## Entities
entity_id | name | type | org | role_notes | aliases_asr_confidence | disambiguation
NPL-E-001 | Warwick Allan | person | Bellrock | Implementation lead / PIM | - | -
NPL-E-002 | Ashley Niven | person | Smart Managed Services | Built PPM schedules/activities; sysadmin user; owns data passes | - | -
NPL-E-003 | Tony Sims | person | Smart Managed Services | Operational manager; site process decision-maker | - | -
NPL-E-004 | Jason (scheduler) | person | Smart Managed Services | Technical scheduler; will monitor PPM help desk and chase/reallocate; possibly on this call silent | - | TWO JASONS - do not conflate with Jason Lewis
NPL-E-005 | Jason Lewis | person | NPL (likely) | Double-barrelled surname incl Lewis; subject of the Orchestrate access failure (NPL-R-002) | - | TWO JASONS - do not conflate with scheduler Jason
NPL-E-006 | Travers | person | not stated (NPL or Smart senior) | Nominated Adam as no.2 sysadmin; requested Jason Lewis account; party to SFG20 talks with Alison | - | Org unresolved - NPL-U-004
NPL-E-007 | Adam (sysadmin nominee) | person | not stated | Travers nominated no.2 system admin; to take IT liaison (NPL-A-003) | - | TWO ADAMS - not the Bellrock MD
NPL-E-008 | Adam (Bellrock MD) | person | Bellrock | Managing Director; referenced SFG20 in daily journals | - | TWO ADAMS - not the sysadmin nominee
NPL-E-009 | Nick | person | NPL IT | Tenant entry group / SSO; role mapping; requested session day before | - | -
NPL-E-010 | Tugba | person | departed project | Previously managed user migration; access downgraded (NPL-C-002); departure = root cause of IT-liaison gap | - | -
NPL-E-011 | Alison | person | likely Bellrock (medium confidence) | Party to SFG20 conversations | - | -
NPL-E-012 | Dave Carr | person | Bellrock | Reporting/dashboard specialist; runs 20 July session | - | -
NPL-E-013 | Craig | person | Smart/NPL (not stated) | Probable SFG20 API key/schema holder - unconfirmed (NPL-Q-008) | - | -
NPL-E-014 | Andy | person | Smart (engineer) | Challenged risk-assessment No behaviour in prior reactive session | - | -
NPL-E-015 | Bob | HYPOTHETICAL | - | Worked example for operative absence scenarios only - NOT a real person | - | Exclude from headcounts
NPL-E-016 | NPL | org | - | Client / site owner; SSO policy owner (drives NPL-D-001) | ASR often MPL (high confidence correction) | -
NPL-E-017 | Smart Managed Services | org | - | Maintenance contractor; exists in Concerto as both contractor (supplier portal) and help-desk operation | - | -
NPL-E-018 | Bellrock | org | - | Implementer | ASR once Bell Ruth (high confidence) | -
NPL-E-019 | ILS | org | - | Another contractor on the NPL Concerto instance (NPL-R-007) | - | -
NPL-E-020 | John O'Connor | org | - | Subcontractor used as live example of batch job creation per supplier | - | -
NPL-E-021 | Facilities IQ / Beza | org | - | SFG20 vendor side | Beza garbled - LOW confidence, verify before external use | -
NPL-E-022 | SFG20 | system/standard | - | Maintenance standards library; source of discipline list; integration pending (NPL-R-001) | ASR variants SF220 / SFD / SFG 20 (high confidence) | -
NPL-E-023 | Concerto | system | Bellrock | CAFM platform; Concerto Web; sandbox + live/prod (FM help desk); known UI bug in Workforce Teams: add-a-new-user-accounts label should read add-a-new-team | - | -
NPL-E-024 | Orchestrate | system | Bellrock | Engineer mobile app; jobs visible only after assignment to named operative; supplier portal is separate | - | -
NPL-E-025 | Carolyn Dark | person | NPL / Smart context unclear | Permit/control-of-works stakeholder; ASR/participants also refer to Kerry/Carrie | Kerry/Carrie/Carolyn - medium confidence same person in this source | Do not conflate with other Kerry until confirmed
NPL-E-026 | Zelea Codreanu | person | NPL context unclear | Permit/check-in/check-out stakeholder; referenced as Zee/Zay/Z | Zee/Zay/Z - high confidence same person
NPL-E-027 | Smart Managed Solutions | org/supplier | Smart | Corrected supplier name raised by Tony; previously Warwick said Services | Smart Managed Services is likely wrong in this context | Verify final supplier record spelling
NPL-E-028 | Smart Managed External Contractors | org/supplier/list | Smart | Proposed separate supplier/list for Smart-used contractors in Permit selection | Smart contractors / smart external contractors | Final exact name to confirm
NPL-E-029 | James | person | not stated | Referenced as possible HV/hard-copy signer/person with limited access | - | Insufficient context; do not treat as confirmed system user
NPL-E-030 | Lewis | person | Bellrock/product/dev likely | Warwick said he needs Lewis to finish something relating to equipment/rules | - | Role/org inferred; verify
NPL-E-031 | Permit Admin | role | Concerto Permit module | Example/possible role created to discuss edit controls | - | Not a person
NPL-E-032 | High Risk Team | team | Concerto Permit module | Team/route created for high-risk/HV permit handling | - | System team, not org unit

## Sources
source_id | date_processed | filename | source_type | event_date | duration | immutable_location | extraction_packet | items_extracted | processed_by
SRC-001 | 2026-07-08 | NPL___Concerto_-_Planned_Helpdesk_Playback_Session.vtt (+ docx rendering) | Teams meeting transcript (VTT canonical) | 2026-07-08 09:07 BST (filename stamp 10:07:59 - TZ discrepancy flagged) | 1h 34m 12s | to file: [project]/01_Sources_Immutable/meeting-transcripts/ | 2026-07-08-NPL-PPM-Playback-extraction.md | 14 decisions / 21 actions / 9 risks / 7 config / 10 questions / 8 milestones / 24 entities / 11 uncertainties | Claude - F247.prompt.transcript-extraction v0.1 via Zapier Sheets
SRC-002 | 2026-07-10 | NPL _ Concerto - Permit to Work Training Session.vtt | Teams meeting transcript (VTT canonical) | 2026-07-10 per Warwick today; Drive modified 2026-07-09 21:47 UTC / 22:47 BST | 1h 58m 37s | BRK-NPL-001/01_Sources_Immutable/meeting-transcripts/NPL _ Concerto - Permit to Work Training Session.vtt | 2026-07-10-NPL-PTW-Training-extraction | 14 decisions / 19 actions / 14 risks/issues / 15 config / 11 questions / 5 milestones / 8 entities / 9 uncertainties | Project ManagAIr via ChatGPT - F247.skill.process-project-source-extraction v0.2

## Uncertainty
u_id | item | why_uncertain | resolve_by | status | related_ids
NPL-U-001 | Smart External Contractor supplier - unresolved final state | Agreed 15:23; creation started 33:00; pivoted to Smart Managed Services + supplier operatives (NPL-D-001); Tony rejected renaming; completion never confirmed | Warwick: check sandbox supplier list and confirm intended model | open | NPL-A-006 / NPL-C-003 / NPL-Q-002
NPL-U-002 | Permit Team final state | Archive initiated, objection, clarification, no explicit close | Check sandbox | open | NPL-C-006 / NPL-Q-003
NPL-U-003 | Owners for NPL-A-001/002 never assigned | Likely lands with Adam after NPL-A-003 - inference not record | Tony-Adam conversation outcome | open | NPL-A-001/002/003
NPL-U-004 | Travers and Adam-nominee organisations not stated | NPL vs Smart unclear; two-Adams and two-Jasons collision risk | Warwick knowledge or next meeting | open | NPL-E-006/007
NPL-U-005 | Beza (SFG20 vendor name) | Low-confidence ASR | Verify before writing into external documents | open | NPL-E-021
NPL-U-006 | Jason (scheduler) presence on the call | Implied by garbled Ashley turn; no captured speech | Warwick recollection | open | NPL-E-004
NPL-U-007 | Environment for NPL-C-004/005 (demo operative, modular team) | Sandbox implied by session context, not stated; live replication undiscussed | Check both environments | open | NPL-C-004/005
NPL-U-008 | No-returns-to-help-desk: existing vs future functionality | Tony phrasing suggests future; unconfirmed | Concerto product clarification | open | NPL-Q-005
NPL-U-009 | Recording gap - final 10-15 min (system admin bits) deliberately unrecorded | Any decisions/actions from that segment are outside this packet | Warwick notes for that segment | open | SRC-001
NPL-U-010 | Timestamp discrepancy 09:07 header vs 10:07:59 filename | Assume BST/UTC | Confirm before citing times externally | open | SRC-001
NPL-U-011 | Name of demo supplier operative garbled (Smart Sub E1 / Smart Subby One) | ASR noise | Verify in sandbox before cleanup | open | NPL-C-004
NPL-U-012 | Source event date/time | User called it today's PTW session, but Drive modified timestamp is 2026-07-09 21:47 UTC and created 2026-07-09 23:31 UTC | Confirm calendar meeting date/time if external reporting required | open | SRC-002
NPL-U-013 | Final Smart supplier/operative model for permits | Two viable options discussed: maintain duplicate contractor list for tick-box selection or type engineer names under Smart Managed Solutions | Tony/Ashley final administration choice | open | NPL-D-027 / NPL-Q-015
NPL-U-014 | 12-hour expiry vs multi-day permit management | Stakeholders debated one permit for duration vs daily reassessment; no final operating process agreed | Smart/NPL permit SOP decision | open | NPL-R-013 / NPL-Q-012
NPL-U-015 | HV hard-copy / electronic process boundary | Tony raised access/hard-copy concerns; HV can be started electronically but internal approval process not fully defined | Tony/Carolyn process definition | open | NPL-D-019 / NPL-Q-017
NPL-U-016 | Config environment certainty | Warwick moved between live, sandbox and preview; some changes explicitly live, others implied or demo only | Check final live and sandbox configuration | open | NPL-R-021 / NPL-C-008:C-022
NPL-U-017 | Asset-level rule granularity | Transcript suggests type/location/PPM-level rules; individual asset-level capability remained unclear | Product check / core data test | open | NPL-Q-018
NPL-U-018 | Carolyn/Kerry/Carrie and Zelea/Zay/Z aliases | ASR/user names vary across transcript; likely same participants but final spelling should be checked | Participant/call invite list | open | NPL-E-025 / NPL-E-026
NPL-U-019 | Forms deletion/suppression bug cause | Warwick observed awkward behaviour but root cause/product status not resolved | Dev/product confirmation | open | NPL-R-020 / NPL-A-029
NPL-U-020 | Demo wording 'to dig a hole' | Used in live discussion as non-technical risk wording; likely humorous/demo terminology not final governance wording | Rename to formal wording before go-live | open | NPL-C-018 / NPL-A-028