## write_manifest
write_id | timestamp_uk | actor | agent_role | operation_type | source_ref | source_file | target_artifact | target_url | branch_or_original | summary | rows_added | files_created | files_moved | folders_created | qa_write_note_url | verification_status | verified_by | verified_at | verification_notes | exceptions | rollback_notes
NPL-WRITE-001 | 2026-07-10 Europe/London | ChatGPT | Project ManagAIr execution | project_source_extraction | SRC-002 | NPL _ Concerto - Permit to Work Training Session.vtt | NPL Concerto - Project Registers - PTW session extraction branch - 2026-07-10 | https://docs.google.com/spreadsheets/d/1iEerUK8TOhAlWYSKJHEx2S6DXfmFBp3r6qyT33z28OA/edit | branch copy only; original register not edited | Processed PTW VTT into duplicated register branch using F247.skill.process-project-source-extraction; added SRC-002 and typed rows across decisions, actions, risks/issues, config changes, questions, milestones, entities and uncertainty; moved source to immutable meeting transcripts. | 14 decisions; 19 actions; 14 risks/issues; 15 config; 11 questions; 5 milestones; 8 entities; 9 uncertainties; 1 source row | Extraction note; write/verification log | VTT moved from inbox to 01_Sources_Immutable/meeting-transcripts; extraction note moved to 09_Reporting_QA_Comms/01 Writes | meeting-transcripts; 01 Writes; 02 Verifications | https://docs.google.com/document/d/1mGsKmGrk-vJz63SWijhXl5T0_Gg4YlUuZzmxtOBiKJg/edit | pending_verification |  |  | VerifAIr/QA should check duplicate branch against QA write note and source transcript; append verification row in verification_log. | Initial population attempt failed because I assumed sheetId 0; retried with actual sheetId 1450696035. | Rollback path: discard duplicate branch; original NPL register was not modified.
NPL-WRITE-002 | 2026-07-10 Europe/London | ChatGPT | Project ManagAIr / Fusion governance update | project_structure_control_update | Warwick instruction 2026-07-10 | Conversation instruction: move from 00 control concept to 09/01 Writes and 09/02 Verifications | BRK-NPL-001 project structure, README, extraction note, F247 skill, F247 ontology, F247 decision log | https://docs.google.com/spreadsheets/d/18S19ZZRxzEVJJZy3dG8hdAUHuO4PO35BJQ5B52gUVGg/edit | project-local plus Fusion control docs | Created 09/01 Writes and 09/02 Verifications; moved PTW write note to 01 Writes; created/populated NPL write/verification log; created root README project map; updated extraction note; updated extraction skill, project operating ontology and decision log with master-template candidate change. | 0 register rows; 1 write-log row | 01 Writes folder; 02 Verifications folder; NPL Project Write and Verification Log; README - BRK-NPL-001 Project Map | PTW extraction note moved from 09 root to 09/01 Writes | 01 Writes; 02 Verifications | https://docs.google.com/document/d/1mGsKmGrk-vJz63SWijhXl5T0_Gg4YlUuZzmxtOBiKJg/edit | pending_verification |  |  | VerifAIr should verify folder placement, README scope, and that Fusion control docs contain the candidate master-template update. | Initial write-log population attempt failed due wrong default sheetId assumption; corrected after metadata read. | No rollback needed unless Warwick rejects 09-based control pattern; then remove folders/readme/log and revert control doc updates.
NPL-WRITE-003 | 2026-07-10 Europe/London | ChatGPT | Project ManagAIr / Fusion governance correction | duplicate_instruction_store_removal | Warwick correction 2026-07-10 | Conversation instruction: root README duplicates ontology and should not exist | README - BRK-NPL-001 Project Map; NPL Project Write and Verification Log; F247 ontology/decision log | https://docs.google.com/spreadsheets/d/18S19ZZRxzEVJJZy3dG8hdAUHuO4PO35BJQ5B52gUVGg/edit | project-local plus Fusion control docs | Deleted root README because it duplicated ontology/project map instructions; retained project-specific write/verification log as audit ledger only; renamed log sheet readme tab to log_schema to avoid instruction-store confusion; logged Fusion-level schema/ontology correction. | 1 write-log row | None | None | None |  | pending_verification |  |  | VerifAIr should confirm no project root README remains, ontology remains canonical, and project log is treated as audit ledger not instruction source. | None | If root project map is later needed, recreate only by explicit ontology/schema decision, not ad hoc.

## verification_log
verification_id | timestamp_uk | verifier | agent_role | write_id | source_ref | qa_write_note_url | target_artifact | verification_scope | result | findings | exceptions | follow_up_required | verification_note_url
NPL-VERIFY-001 | 2026-07-10 Europe/London | Claude | External QA (F247.skill.update-qa-claude) | NPL-WRITE-001 | SRC-002 | https://docs.google.com/document/d/1mGsKmGrk-vJz63SWijhXl5T0_Gg4YlUuZzmxtOBiKJg/edit | NPL Concerto - Project Registers - PTW session extraction branch - 2026-07-10 (1iEerUK8TOhAlWYSKJHEx2S6DXfmFBp3r6qyT33z28OA) | Branch isolation; original register integrity; row ranges and counts; WP-014 tagging; five focus risks; uncertainties U-012 to U-020; supplier naming capture; training milestones. Transcript fidelity NOT re-verified line-by-line against the VTT. | PASS with observations | Original register unmodified: last modified 2026-07-09 21:39 UTC, before branch creation 23:38; Sources holds only SRC-001; Decisions end D-014, Risks end R-009, Uncertainty ends U-011. Branch holds all and only the new SRC-002 rows: D-015 to D-028, A-022 to A-040, R-010 to R-023, C-008 to C-022, Q-011 to Q-021, M-009 to M-013, E-025 to E-032, U-012 to U-020; counts match write note exactly, no gaps or duplicates. WP-014 tagging present on all sampled new rows. Focus risks (12h expiry, supplier/operative model, non-editable issued permits, PPM flag non-enforcement, live/sandbox certainty) all captured with anchors and cross-links. Supplier naming (Smart Managed Solutions / Smart Managed External Contractors) and 15 July 10:00 training plus 16 July follow-up session recorded as open items pending Warwick confirmation. | Branch adds work_package columns that the original register lacks; merge-back must add or map them first. Native Drive create_file failed twice; verification note created via Zapier Docs, whose create action injected placeholder content that was immediately replaced with the real text via batchUpdate. | Warwick: resolve U-012 to U-020 (especially U-016 environment certainty) before external reliance; verify final supplier record spellings; confirm 15 July invite list and 16 July session calendar. Governance: decide whether project-local write log needs a Brain Session Log pointer; decide branch merge-back/promotion and registry update. NPL-WRITE-002 and NPL-WRITE-003 remain pending_verification, out of scope here. | https://docs.google.com/document/d/1LajWtgF28yIySsoRNOBjRZFKccowWk1ofWhE8peiBP0/edit

## log_schema
NPL Project Write and Verification Log
Purpose | Append-only project audit ledger for AI/project writes and VerifAIr QA checks.
write_manifest | AI/project write operations. Writer marks verification_status as pending_verification only.
verification_log | QA/VerifAIr verification records. The writer must not verify its own write.
Folder rule | This log lives in 09_Reporting_QA_Comms/01 Writes. Verification reports should live in 09_Reporting_QA_Comms/02 Verifications.