## Decisions
decision_id | date | decision | rationale | decider | status | supersedes | superseded_by | implications | source_ref
NPL-D-001 | 2026-07-08 | Subcontractors will never be onboarded to Concerto/Orchestrate; represent them as supplier operatives under the Smart Managed Services contractor record | NPL will never grant SSO/system access to non-NPL email addresses; supplier operatives give allocation visibility without access. Explicitly flagged 'to capture for the decision log' | Warwick (mechanism, per NPL policy); Tony endorsed | agreed |  |  | Subbie upload via user template sheet (NPL-A-007/008); jobs managed via help desk, closing action auto-closes supplier portal order | S001 ¦ Warwick @ 38:52-39:30; Tony @ 39:56
NPL-D-002 | 2026-07-08 | Upload all subcontractor business names into the system with no access | NPL know the whole subcontractor base - no confidentiality obstacle; enables Jason (scheduler) to plan workload | Tony | agreed |  |  | Feeds NPL-A-007/008 | S001 ¦ Tony @ 39:56-40:16
NPL-D-003 | 2026-07-08 | Emailing jobs to subcontractors from the system: declined | Floated by Warwick; immediate rejection by Smart | Tony | rejected |  |  | Subbie comms remain outside the system | S001 ¦ Warwick/Tony @ 41:40-42:02
NPL-D-004 | 2026-07-08 | 'External Contractors' resource-team route for subbies superseded by supplier-portal/supplier-operative model | Warwick's own prior setup; now judged less elegant than supplier-operative separation ('future me is thinking...') | Warwick | superseded | prior config (resource team route) | NPL-D-001 | Redundant External Contractors resource team remains - cleanup not agreed (UNC-01 related) | S001 ¦ Tony/Ashley @ 43:26; Warwick @ 43:47-44:43
NPL-D-005 | 2026-07-08 | 'PPM Not Completed' closure action: rejected. Closure via 'PPM complete with remedials' | A remedial will always exist where checks weren't finished; confirmed again at close of meeting | Tony | rejected |  |  | Vanilla closure actions stand: PPM complete / PPM complete with remedials | S001 ¦ Warwick @ 22:51-23:55; Tony @ 23:49; Warwick @ 1:20:31
NPL-D-006 | 2026-07-08 | Daily plant-room inspections remain individual daily jobs, each with risk assessment, despite admin burden | 'It's a requirement for site that we record that we're doing it'; also lets engineers raise remedials off the daily task | Tony | agreed |  |  | Engineer admin load accepted (see NPL-R-006) | S001 ¦ Warwick @ 21:36-22:14; Tony @ 22:16
NPL-D-007 | 2026-07-08 | Run PPM job creation manually for first ~2-3 months; defer automated workflow-rule creation | Jobs created in live are irreversible; manual running catches errors. Auto mode can be enabled later via support ticket | Warwick recommendation; no objection | agreed in principle |  |  | Post-go-live revisit ~2-3 months in | S001 ¦ Warwick @ 16:13-18:35
NPL-D-008 | 2026-07-08 | Allocation operating model: weekly planning meetings; internal jobs allocated Friday for following week; subcontractor jobs allocated 1-3 months ahead on rolling monthly basis | Balances sickness/holiday volatility (internal) against long contractor lead times | Tony; Ashley concurred | agreed in principle |  |  | Smart internal operating model; supports NPL-R-009 mitigation | S001 ¦ Tony @ 58:07-58:41; @ 59:59-1:00:53
NPL-D-009 | 2026-07-08 | Add a Modular Maintenance resource team (created live in session) | Roaming estate-wide maintenance team is a distinct planning unit on an unusual site | Tony | agreed - refinement pending |  |  | Structure (single vs electrical/mechanical split) open - NPL-Q-006; membership work NPL-A-020 | S001 ¦ Tony @ 1:15:26-1:16:14; Warwick @ 1:18:22-1:19:15
NPL-D-010 | 2026-07-08 | Permit Team resource team retained; archive halted | Future ~7-person team may review the whole permit situation | Tony objection; Warwick halted | retained (final state to confirm) |  |  | See UNC-02 | S001 ¦ Warwick @ 1:17:31-1:18:22; Tony @ 1:17:40
NPL-D-011 | 2026-07-08 | Risk assessment step: keep mandatory-to-answer questions for now; explore reducing 12 questions to a single yes/no risk-awareness confirmation referencing a named SOP | Driver: serious injury incident on site (another contractor) with no stop/pause mechanism; engineer resistance to 12 clicks per job. Desired: 'no' returns task to help desk. Framed as 'risk awareness, not risk assessment' | Tony (owner of rethink) | under consideration |  |  | NPL-A-011; feasibility of return-to-helpdesk = NPL-Q-005 | S001 ¦ Tony @ 1:25:52-1:29:57; Warwick @ 1:26:30-1:28:58
NPL-D-012 | 2026-07-08 | Preset text for completion/on-hold reasons: adopt in principle | New Concerto functionality; contract-aligned selectable wording drops into audit trail; avoids free-text quality problems. Applies to PPM and reactive | Warwick proposed; Tony receptive | agreed in principle |  |  | Wording to align to NPL contractual requirements | S001 ¦ Warwick @ 1:10:27-1:12:11; Tony @ 1:12:14
NPL-D-013 | 2026-07-08 | Policy/guidance hyperlink on Orchestrate start screen: parked | Technically possible but NPL instance is shared by multiple contractors (ILS named); per-contractor links 'clunky'; Warwick's view: should be an NPL-wide policy | Tony to consider | parked |  |  | NPL-A-012 | S001 ¦ Warwick @ 1:29:57-1:30:50; Tony @ 1:31:05-1:31:38
NPL-D-014 | 2026-07-08 | PPM data deadline (working assumption - not formally agreed): ideal = final data within ~1 week, before UAT; absolute backstop = end of July, post-UAT pre-go-live live-data load | 'We've not agreed a date yet'; PPM training expected next week, UAT immediately after. NOTE: Copilot summary inverted this logic | Warwick | proposed |  |  | NPL-A-004 (Ashley's final data pass) | S001 ¦ Warwick @ 4:43-6:00

## Actions
action_id | date_raised | action | owner | due_date | status | dependency | related_ids | source_ref
NPL-A-001 | 2026-07-08 | Define mechanism for informing Nick (NPL IT) when a new starter needs adding to tenant entry group for Concerto SSO access | not stated (likely lands with Adam post NPL-A-003) | not stated | to do | NPL-A-003 | NPL-R-002 | S001 ¦ Warwick @ 2:11-3:00
NPL-A-002 | 2026-07-08 | Define process for downgrading/removing permissions when people leave or change teams (sysadmins especially) | not stated (NPL/Smart admin owners) | not stated | to do |  | NPL-R-003 | S001 ¦ Warwick @ 3:00-4:24
NPL-A-003 | 2026-07-08 | Speak to Adam about picking up IT-liaison / no.2 sysadmin mantle (Travers nomination) | Tony | 2026-07-09 | to do |  | NPL-R-002; NPL-R-003 | S001 ¦ Tony @ 4:25
NPL-A-004 | 2026-07-08 | Final PPM data pass: send remaining data updates | Ashley | ideal ~2026-07-15 (before UAT); hard stop end July | to do | NPL-D-014 | NPL-D-014 | S001 ¦ Warwick @ 5:00-6:00
NPL-A-005 | 2026-07-08 | Obtain SFG20 API key + schema/secret (likely holder Craig, possibly Jason); pass to Warwick to configure | Ashley & Tony (obtain); Warwick (configure) | ahead of further meetings | to do | NPL-Q-008 | NPL-R-001 | S001 ¦ Warwick @ 27:43-28:42
NPL-A-006 | 2026-07-08 | Create supplier 'Smart External Contractor' in live, copy down to sandbox | Warwick | not stated | to do - possibly superseded by NPL-D-001 model; started in session, completion unconfirmed | NPL-Q-002 | NPL-D-001; NPL-C-003; UNC-01 | S001 ¦ Warwick @ 15:23-16:01; @ 33:00-33:35
NPL-A-007 | 2026-07-08 | Send Ashley the user template sheet for uploading subcontractors as supplier operatives; Bellrock to run the upload | Warwick | needed for second data pass | to do |  | NPL-D-001; NPL-D-002 | S001 ¦ Warwick @ 40:16-40:56
NPL-A-008 | 2026-07-08 | Collate list of subcontractor names; map to operative column of PPM activity data | Ashley | with second data pass | to do | NPL-A-007 | NPL-D-001; NPL-D-002 | S001 ¦ Warwick @ 44:43-45:01
NPL-A-009 | 2026-07-08 | Second data pass: assign discipline resource teams (electrical/mechanical/fabric) to maintenance-team jobs; subcontractor jobs to With Contractor | Ashley | with second data pass | to do |  |  | S001 ¦ Ashley @ 31:56-32:47
NPL-A-010 | 2026-07-08 | Investigate: can auto job-creation workflow rule be conditional on previous day's job completed; define behaviour when a day is missed | Warwick | not stated | to do |  | NPL-D-007; NPL-Q-004 | S001 ¦ Warwick @ 18:35-19:55
NPL-A-011 | 2026-07-08 | Rethink risk-assessment step: single yes/no question wired to 'no returns task to help desk'; discuss with team | Tony | not stated | to do | NPL-Q-005 | NPL-D-011; NPL-R-006 | S001 ¦ Tony @ 1:29:30-1:29:57
NPL-A-012 | 2026-07-08 | Decide policy-link ownership: NPL-wide maintenance risk policy vs per-contractor links in Orchestrate | Tony | not stated | to do |  | NPL-D-013; NPL-R-007 | S001 ¦ Tony @ 1:31:38
NPL-A-013 | 2026-07-08 | Investigate 'Operative or Subcontractor' option on PPM create-jobs screen - what drives it; potential clean split of weekly internal vs long-range subbie job runs | Warwick | not stated | to do |  | NPL-D-008 | S001 ¦ Ashley @ 1:00:53-1:01:19; Warwick @ 1:01:56-1:02:45
NPL-A-014 | 2026-07-08 | Check form settings/administration for hidden operative-level filter on job creation | Warwick | not stated | to do |  | NPL-A-013 | S001 ¦ Warwick @ 1:04:22-1:04:30
NPL-A-015 | 2026-07-08 | Investigate multiples/stacking of automated job-creation workflow rules (daily + other frequencies coexisting) | Warwick | not stated | to do |  | NPL-D-007 | S001 ¦ Warwick @ 16:50-17:10
NPL-A-016 | 2026-07-08 | Investigate engineer self-assignment of related/remedial jobs and interaction with PPM remedials-helpdesk triage step | Warwick | not stated | to do |  |  | S001 ¦ Warwick @ 24:35-25:53
NPL-A-017 | 2026-07-08 | Turn OFF 'Consumable order' action on PPM jobs (no stock module) | Warwick | not stated | to do |  |  | S001 ¦ Warwick @ 55:19-55:45
NPL-A-018 | 2026-07-08 | Investigate duplicate 'Place job on hold' actions in PPM action set | Warwick | not stated | to do |  |  | S001 ¦ Warwick @ 56:07
NPL-A-019 | 2026-07-08 | Re-apply create-jobs permission in LIVE (prod) FM help desk so next copy-down doesn't strip the sandbox fix | Warwick | before next copy-down | to do - silent-failure risk | NPL-C-001 | NPL-R-008 | S001 ¦ Warwick @ 1:33:35
NPL-A-020 | 2026-07-08 | Work through Modular Maintenance team structure (single vs electrical/mechanical split) and membership; Ashley to handle upload/changes | Tony & Ashley | 2026-07-09 | to do | NPL-Q-006 | NPL-D-009; NPL-C-005 | S001 ¦ Tony @ 1:15:26-1:16:35
NPL-A-021 | 2026-07-08 | Re-run teams/workforce walkthrough with/for Jason (scheduler) - deferred in session | Warwick | not stated | to do |  |  | S001 ¦ Warwick @ 1:19:15

## Risks_Issues
raid_id | type | description | driver | impact | owner | mitigation | status | source_ref

## Config_Changes
config_id | date | change | system_environment | made_by | follow_through | status | source_ref

## Open_Questions
question_id | question | parked_with | unblocked_by | status | source_ref

## Milestones
milestone_id | date | item | owner | conditions_notes | source_ref

## Entities
entity_id | name | type | org | role | aliases | notes | confidence

## Stakeholder_Notes
note_id | date | person | observation | resolution | source_ref

## Uncertainty
unc_id | item | why_uncertain | resolve_by | status | source_ref

## Sources
source_id | date_processed | filename | source_type | event_date | raw_location | packet_location | items_extracted | status