## Rocketlane
IndexIn Concerto | Phase/Task ID | Dependent | Workpackage Manager | Task | Start Day | Duration | Assignee | Effort (Hours) | Effort Split | Task Value | Phase Value | Effort Days | Billable | Category | Milestone | Private | Key Event | Dynamic Trigger
| 1 |  |  | Mobilisation & Initiation | [13 empty] | TEC_BMA_CON_ECPS_PROS_CON
| 1.1 |  |  | Governance Setup |  |  | Project Manager | [5 empty] | No | Project Mangement | No | No | New Project Start | TEC_BMA_CON_ECPS_PROS_CON
| 1.1.1 |  |  | Project Teams Identified | 1 | 1 | Project Manager | [5 empty] | No | Project Mangement | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
| 1.1.2 |  |  | Client Charter Sign Off | 1 | 1 | Project Manager/Customer | [5 empty] | No | Project Mangement | No | No |  | TEC_BMA_CON_ECPS_PROS_CON
| 1.2 |  |  | Commercial & Handover |  |  | Project Manager | [5 empty] | No | Project Mangement | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
| 1.2.1 |  |  | Sales Handover | 1 |  | Project Manager/PS Team Lead | [5 empty] | No | Project Mangement | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
| 1.2.2 |  |  | Baseline Agreed | 1 | 5 | Project Manager/PS Team Lead | [5 empty] | No | Project Mangement | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
| 1.2.3 |  |  | Pre Mobilisation Call | 6 | 1 | Project Manager/PS Team Lead/Customer | [5 empty] | No | Project Mangement | No | No |  | TEC_BMA_CON_ECPS_PROS_CON
1 | 1.3 |  |  | System Spin Up |  |  | PS Team Lead | [5 empty] | No | Project Mangement | No | No |  | TEC_BMA_CON_ECPS_PROS_CON
2 | 1.3.1 |  |  | Create Environments | 6 | 2 | Support | [5 empty] | No | Project Mangement | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
3 | 1.3.2 |  |  | Clear down data | 6 | 2 | Support | [5 empty] | No | Project Mangement | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
4 | 1.3.3 |  |  | BrandingCustomisation | 8 | 2 | PS Team Lead | [5 empty] | No | Project Mangement | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
5 | 1.3.4 |  |  | ModuleLicense Configuration | 8 | 2 | PS Team Lead | [5 empty] | No | Project Mangement | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
9 | 1.4 |  |  | Formal Project Kick Off |  |  | Project Manager/PS Team Lead | [5 empty] | No | Project Mangement | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
11 | 1.4.1 |  |  | Implementation Plan Issued | 9 | 5 | Project Manager/PS Team Lead | [5 empty] | No | Project Mangement | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
12 | 1.4.2 |  |  | Implementation Plan Sign Off | 14 | 1 | Project Manager/PS Team Lead/Customer | [5 empty] | No | Project Mangement | No | No |  | TEC_BMA_CON_ECPS_PROS_CON
| 1.5 |  | Andrew Austerberry | Project Scope & Process Mapping |  |  | Project Manager/PS Team Lead/Customer | [5 empty] | No | Project Mangement | No | No |  | TEC_BMA_CON_ECPS_PROS_CON
14 | 1.5.1 |  | Andrew Austerberry | Onsite Process Mapping |  |  | Project Manager/PS Team Lead/Customer | [5 empty] | No | Project Mangement | No | No |  | TEC_BMA_CON_ECPS_PROS_CON
15 | 1.5.1.1 |  | Andrew Austerberry | Core Data | 15 | 5 | [6 empty] | No | Project Mangement | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
16 | 1.5.1.2 |  | Andrew Austerberry | Reactive | 15 | 5 | [6 empty] | No | Project Mangement | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
17 | 1.5.1.3 |  | Andrew Austerberry | Planned | 15 | 5 | [6 empty] | No | Project Mangement | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
18 | 1.5.1.4 |  | Andrew Austerberry | Projects & Programmes | 15 | 5 | [6 empty] | No | Project Mangement | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
19 | 1.5.1.5 |  | Andrew Austerberry | Supplier Portal | 15 | 5 | [6 empty] | No | Project Mangement | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
20 | 1.5.1.6 |  | Andrew Austerberry | Surveys | 15 | 5 | [6 empty] | No | Project Mangement | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
| 1.6 |  | Andrew Austerberry | Scoping Documentation |  |  | Project Manager/PS Team Lead | [5 empty] | No | Project Mangement | No | No |  | TEC_BMA_CON_ECPS_PROS_CON
| 1.6.1 |  | Andrew Austerberry | Scope & HighLevel Processes Issued | 21 | 1 | [6 empty] | No | Project Mangement | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
| 1.6.2 |  | Andrew Austerberry | Processes Reviewed | 22 | 5 | [6 empty] | No | Project Mangement | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
| 1.6.3 |  | Andrew Austerberry | ProcessScope Signed Off | 27 | 1 | [6 empty] | No | Project Mangement | No | Yes | Process Scope Sign Off | TEC_BMA_CON_ECPS_PROS_CON
| 2 |  |  | Project Management & Consultancy | [13 empty] | TEC_BMA_CON_ECPS_PROS_CON
| 2.1 |  | Andrew Austerberry | Workpackages Booked | 1 | 1 | Project Manager | 7h 30m |  |  |  | 1 | No | Project Management | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
| 2.2 |  |  | Project Managememnt | 1 | 365 | Project Manager | 90h |  |  |  | 12 | Yes | Project Management | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
| 2.2.1 |  |  | Recurring PM Monthly Task |  |  |  | 0 |  |  |  | 0 | No |  | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
| 2.3 |  |  | Project Administration | 1 | 365 | Project Manager | 45h |  |  |  | 6 | Yes | Project Management | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
| 2.3.1 |  |  | Recurring PM Admin Task |  |  |  | 0 |  |  |  | 0 | No |  | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
| 2.4 |  |  | General Consultancy | 28 | 365 | Implementation/Team Leader | 0 |  |  |  | 0 | Yes | Consultancy | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
| 2.4.1 |  |  | Recurring Monthly WIP Report | 28 | 365 | Team Leader | 0 |  |  |  | 0 | No | Project Management
| 2.5 |  |  | Project Governance | 28 | 365 | Project Manager/Team Leader/Customer | 0 |  |  |  | 0 | No | Project Governance | No | No |  | TEC_BMA_CON_ECPS_PROS_CON
| 2.5.1 |  |  | Decision Log | 28 | 365 |  | 0 |  |  |  | 0 | No | Project Governance | No | No |  | TEC_BMA_CON_ECPS_PROS_CON
| 2.5.2 |  |  | Issue Log | 28 | 365 |  | 0 |  |  |  | 0 | No | Project Governance | No | No |  | TEC_BMA_CON_ECPS_PROS_CON
| 2.5.3 |  |  | RAID Log | 28 | 365 |  | 0 |  |  |  | 0 | No | Project Governance | No | Yes |  | TEC_BMA_CON_ECPS_PROS_CON
| 2.5.4 |  |  | ChangeVariation Requests | 28 | 365 |  | 0 |  |  |  | 0 | No | Project Governance | No | No |  | TEC_BMA_CON_ECPS_PROS_CON
26 | 3 |  | Andrew Austerberry | Core Data |  | 49 |  | 52.5 |  |  |  | 7 | [5 empty] | TEC_BAS_CON_CDPS_PROS_CON
26 | 3.1 |  |  | Work Package Management (CORE DATA) |  |  | Implementation | 0 | 100 |  |  | 0 | No | Work Package Management | No | No |  | TEC_BAS_CON_CDPS_PROS_CON
| 3.1.1 |  |  | Core Data WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 | 0 |  | 7 | 0 | No | Work Package Management | No | Yes |  | TEC_BAS_CON_CDPS_PROS_CON
| 3.1.2 |  |  | Core Data Specification Agreed | 1 | 5 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | TEC_BAS_CON_CDPS_PROS_CON
| 3.1.3 |  |  | Core Data Chat | 1 | 49 | Customer/Implementation/Project Manager | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | TEC_BAS_CON_CDPS_PROS_CON
| 3.2 |  |  | Core Data Consultancy |  |  | Implementation | 7h 30m | 100 |  |  | 1 | Yes | Consultancy | Yes | No |  | TEC_BAS_CON_CDPS_PROS_CON
27 | 3.2.1 |  | Andrew Austerberry | Core Data Overview Session | 1 | 1 | Customer/Implementation | 0 |  | 1 |  |  | No | Consultancy | No | No | Core Data WP Start | TEC_BAS_CON_CDPS_PROS_CON
| 3.3 |  | Andrew Austerberry | Core Data Data Management |  |  | Implementation/Data Management | 37h 30m | 20/80 |  |  | 5 | Yes | Data Management | Yes | No |  | TEC_BAS_CON_CDPS_PROS_CON
28 | 3.3.1 |  | Core Data | Core Data Data Mapping Session | 5 | 1 | Implementation/Customer | 0 | 0 | 1 |  | 0 |  | Data Management | No | No |  | TEC_BAS_CON_CDPS_PROS_CON
29 | 3.3.1 |  | Andrew Austerberry | Core Data Test Data Collation | 5 | 15 | Customer | 0 | 0 |  |  | 0 | No | Data Management | No | No | Core Data Test Data Start | TEC_BAS_CON_CDPS_PROS_CON
34 | 3.3.2 |  | Andrew Austerberry | Core Data Test Data Validation & Load |  |  | Data Management | 0 | 0 | 1 |  | 0 | No | Data Management | No | No | Core Data Test Data End | TEC_BAS_CON_CDPS_PROS_CON
35 | 3.3.2.1 |  | Andrew Austerberry | Core Data Test Data Load | 22 | 2 |  | 0 | 0 |  |  | 0 | Yes | Data Management | No | No |  | TEC_BAS_CON_CDPS_PROS_CON
36 | 3.3.2.2 |  | Andrew Austerberry | Core Data Test Data Playback Session | 25 | 1 | Customer/Implementation | 0 | 0 | 1 |  | 0 | Yes | Data Management | No | No |  | TEC_BAS_CON_CDPS_PROS_CON
37 | 3.3.3 |  | Andrew Austerberry | Core Data Full Data Collation | 25 | 10 | Customer | 0 | 0 |  |  | 0 | No | Data Management | No | No | Core Data Full Data Start | TEC_BAS_CON_CDPS_PROS_CON
40 | 3.3.5 |  | Andrew Austerberry | Core Data Full Data Validation & Load |  |  |  | 0 | 0 | 1 |  | 0 | No | Data Management | No | No | Core Data Full Data End | TEC_BAS_CON_CDPS_PROS_CON
| 3.3.5.1 |  | Andrew Austerberry | Core Data Load Test Data | 35 | 3 | Data Management | 0 | 0 |  |  | 0 | No | Data Management | No | Yes |  | TEC_BAS_CON_CDPS_PROS_CON
| 3.3.4 |  | Core Data | Core Data Full Data Playback Session | 41 | 1 | Customer/Implementation | 0 | 0 | 1 |  | 0 | Yes | Data Management | No | No |  | TEC_BAS_CON_CDPS_PROS_CON
| 3.4 |  |  | Documents Bolt On |  |  | Data Management | 15h | 0 |  |  | 0 | Yes | Data Management | No | No | Documents Bolt On Start | ?
| 3.4.1 |  |  | Documents Bolt On Overview | 38 | 1 | Data Management | 0 | 0 | 1 |  | 0 | Yes | Data Management | No | No |  | ?
| 3.4.2 |  |  | Documents Bolt On Data Management |  |  | Data Management | 0 | 0 | 1 |  | 0 | Yes | Data Management | No | No |  | ?
| 3.4.2.1 |  |  | Set Up SFTP | 39 | 1 |  | 0 | 0 |  |  | 0 | Yes | Data Management | No | No |  | ?
| 3.4.2.2 |  |  | Agree folder structure for document / photo import | 39 | 1 |  | 0 | 0 |  |  | 0 | Yes | Data Management | No | No |  | ?
| 3.4.2.3 |  |  | Import documents and photos and link to sites | 39 | 1 |  | 0 | 0 |  |  | 0 | Yes | Data Management | No | No |  | ?
| 3.4.3 |  |  | Documents Bolt On DT&I | 40 | 1 | Development | 0 | 0 |  |  | 0 | Yes | Data Management | No | No |  | ?
| 5.4 |  |  | Core Data Training |  |  | Product Enablement | 3h 45m | 100 |  |  | 0.5 | Yes | Training | Yes | No |  | TEC_BAS_CON_CDPS_PROS_CON
| 5.4.1 |  | Andrew Austerberry | Core Data Training Session | 43 | 1 | Product Enablement/Customer | 0 | 0 | 0.5 |  | 0 | No | Training | No | No |  | TEC_BAS_CON_CDPS_PROS_CON
| 3.5 |  |  | Core Data Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | TEC_BAS_CON_CDPS_PROS_CON
46 | 3.5.1 |  | Andrew Austerberry | Core Data UAT | 44 | 5 | Customer/Implementation | 0 | 0 |  |  | 0 | No | UAT | No | No | Core Data UAT Start | TEC_BAS_CON_CDPS_PROS_CON
49 | 3.5.2 |  | Andrew Austerberry | Core Data Sign Off | 49 | 1 | Customer/Project Manager | 0 | 0 | 0.5 |  | 0 | 0 | Sign Off | Yes | No | Core Data WP End | TEC_BAS_CON_CDPS_PROS_CON
| 4.3.4 |  | Andrew Austerberry | Core Data Hyper Care | 50 | 1 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Hyper Care | No | No |  | TEC_BAS_CON_CDPS_PROS_CON
| 4 |  | Andrew Austerberry | Advanced Authentication |  | 22 |  | 22.5 |  | 3 |  | 3 | [5 empty] | TEC_BAS_CON_ADAU_PROS_CON
| 4.1 |  |  | Work Package Management (ADV AUTH) |  |  | OnBoarding | 0 | 100 |  |  | 0 | No | Work Package Management | No | No |  | TEC_BAS_CON_ADAU_PROS_CON
| 4.1.1 |  |  | Advanced Authentication WP Hardbooked and Budget | 1 | 1 | OnBoarding/Project Manager | 0 | 0 |  | 3 | 0 | No | Work Package Management | No | Yes |  | TEC_BAS_CON_ADAU_PROS_CON
| 4.1.2 |  |  | Advanced Authentication Specification Agreed | 1 | 5 | Customer/OnBoarding | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | TEC_BAS_CON_ADAU_PROS_CON
| 4.1.3 |  |  | Advanced Authentication Chat | 1 | 22 | Customer/Implementation/Project Manager | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | TEC_BAS_CON_ADAU_PROS_CON
| 4.2 |  |  | Advanced Authentication Consultancy |  |  | OnBoarding | 7h 30m | 100 |  |  | 1 | Yes | Consultancy | Yes | No |  | TEC_BAS_CON_ADAU_PROS_CON
| 4.2.1 |  | Andrew Austerberry | Advanced Authentication Overview Session | 1 | 1 | Customer/OnBoarding | 0 |  | 1 |  | 0 | No | Consultancy | No | No | Adv Auth WP Start | TEC_BAS_CON_ADAU_PROS_CON
| 4.3 |  | Andrew Austerberry | Advanced Authentication Data Management |  |  | OnBoarding | 0 | 100 |  |  | 0 | Yes | Data Management | Yes | No |  | TEC_BAS_CON_ADAU_PROS_CON
| 4.3.1 |  | Andrew Austerberry | Collate Advanced Authentication Data | 2 | 10 | Customer | 0 |  |  |  | 0 | No | Data Management | No | No | Adv Auth Data Start | TEC_BAS_CON_ADAU_PROS_CON
| 4.4 |  | Andrew Austerberry | Advanced Authentication Configuration |  |  | OnBoarding | 11h 15m | 0 |  |  | 1.5 | Yes | Configuration | Yes | No | Adv Auth Data End | TEC_BAS_CON_ADAU_PROS_CON
| 4.4.1 |  |  | Configure Concerto | 13 | 2 |  | 0 | 0 | 0.75 |  | 0 | No | Configuration | No | Yes |  | TEC_BAS_CON_ADAU_PROS_CON
| 4.4.2 |  | Andrew Austerberry | Deploy in Octopus | 13 | 2 |  | 0 | 0 | 0.75 |  | 0 | No | Configuration | No | Yes |  | TEC_BAS_CON_ADAU_PROS_CON
| 4.3 |  |  | Advanced Authentication Close |  |  | OnBoarding | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | TEC_BAS_CON_ADAU_PROS_CON
| 4.3.1 |  | Andrew Austerberry | Advanced Authentication UAT | 16 | 5 | Customer/OnBoarding | 0 | 0 |  |  | 0 | No | UAT | No | No | Adv Auth UAT Start | TEC_BAS_CON_ADAU_PROS_CON
| 4.3.2 |  | Andrew Austerberry | Advanced Authentication Sign Off | 21 | 1 | Customer/Project Manager | 0 | 0 | 0.5 |  | 0 | No | Sign Off | Yes | No | Adv Auth WP End | TEC_BAS_CON_ADAU_PROS_CON
| 4.3.3 |  | Andrew Austerberry | Advanced Authentication Go Live | 22 | 1 | Customer/OnBoarding | 0 | 0 |  |  | 0 | No | Go Live | No | No | Adv Auth Go Live | TEC_BAS_CON_ADAU_PROS_CON
| 4.3.4 |  | Andrew Austerberry | Advanced Authentication Hyper Care | 22 | 5 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Hyper Care | No | No |  | TEC_BAS_CON_ADAU_PROS_CON
50 | 5 |  | Andrew Austerberry | Estates Full |  | 48 |  | 56.25 |  | 7.5 |  | 7.5 | [5 empty] | TEC_PSE_CON_RE_PROS_CON
50 | 5.1 |  |  | Work Package Management (EST FULL) |  |  | Implementation | 0 | 100 |  |  | 0 | No | Work Package Management | No | No |  | TEC_PSE_CON_RE_PROS_CON
| 5.1.1 |  |  | Estates Full WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 | 0 |  | 7.5 | 0 | No | Work Package Management | No | Yes |  | TEC_PSE_CON_RE_PROS_CON
| 5.1.2 |  |  | Estates Full Specification Agreed | 1 | 5 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | TEC_PSE_CON_RE_PROS_CON
| 5.1.3 |  |  | Estates Full Chat | 1 | 48 | Customer/Implementation/Project Manager | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | TEC_PSE_CON_RE_PROS_CON
| 5.2 |  |  | Estates Full Consultancy |  |  | Implementation | 7h 30m | 0 |  |  | 1 | Yes | Consultancy | Yes | No |  | TEC_PSE_CON_RE_PROS_CON
51 | 5.2.1 |  | Andrew Austerberry | Estates Full Overview Session | 1 | 1 | Customer/Implementation | 0 | 0 | 1 |  | 0 | No | Consultancy | No | No | Estates Full WP Start | TEC_PSE_CON_RE_PROS_CON
| 5.3 |  | Andrew Austerberry | Estates Full Data Management |  |  | Implementation/Data Management | 37h 30m | 20/80 |  |  | 5 | Yes | Data Management | Yes | No |  | TEC_PSE_CON_RE_PROS_CON
52 | 5.3.1 |  | Andrew Austerberry | Estates Full Test Data Collation | 1 | 15 | Customer | 0 | 0 |  |  | 0 | No | Data Management | No | No | Estates Full Test Data Start | TEC_PSE_CON_RE_PROS_CON
56 | 5.3.2 |  | Andrew Austerberry | Estates Full Test Data Validation & Load |  |  |  | 0 | 0 | 2 |  | 0 | No | Data Management | No | No | Estates Full Test Data End | TEC_PSE_CON_RE_PROS_CON
| 5.3.2.1 |  | Andrew Austerberry | Transaction Party Data | 16 | 1 |  | 0 | 0 |  |  | 0 | No | Data Management | No | Yes |  | TEC_PSE_CON_RE_PROS_CON
| 5.3.2.2 |  |  | Occupation Data | 16 | 1 |  | 0 | 0 |  |  | 0 | No | Data Management | No | Yes
| 5.3.2.3 |  |  | Rentable Units Data | 16 | 1 |  | 0 | 0 |  |  | 0 | No | Data Management | No | Yes
| 5.3.2.4 |  |  | Ownership Data | 16 | 1 |  | 0 | 0 |  |  | 0 | No | Data Management | No | Yes
| 5.3.2.5 |  |  | Disposals Data | 16 | 1 |  | 0 | 0 |  |  | 0 | No | Data Management | No | Yes
| 5.3.2.6 |  |  | Valuation Data | 16 | 1 |  | 0 | 0 |  |  | 0 | No | Data Management | No | Yes
| 5.3.2.7 |  |  | Rateable Values | 16 | 1 |  | 0 | 0 |  |  | 0 | No | Data Management | No | Yes
57 | 5.3.3 |  | Andrew Austerberry | Estate Full Test Data Playback Session | 20 | 1 | Customer/Data Management | 0 | 0 | 1 |  | 0 | Yes | Data Management | No | No |  | TEC_PSE_CON_RE_PROS_CON
58 | 5.3.4 |  | Andrew Austerberry | Estate Full Full Data Collation | 21 | 10 | Customer | 0 | 0 |  |  | 0 | No | Data Management | No | No | Estates Full - Full Data Start | TEC_PSE_CON_RE_PROS_CON
| 5.3.5 |  | Andrew Austerberry | Estate Full Final Data Validation & Load |  |  |  | 0 | 0 | 1 |  | 0 | Yes | Data Management | No | No | Estates Full - Full Data End | TEC_PSE_CON_RE_PROS_CON
62 | 5.3.5.1 |  | Andrew Austerberry | Estates Full Data Load | 31 | 1 | Data Management | 0 | 0 |  |  | 0 | No | Data Management | No | Yes |  | TEC_PSE_CON_RE_PROS_CON
| 5.3.6 |  |  | Full Data Playback Session | 33 | 1 | Customer/Data Management | 0 | 0 | 1 |  | 0 | Yes | Data Management | No | No |  | TEC_PSE_CON_RE_PROS_CON
| 5.4 |  |  | Estates Full Training |  |  | Product Enablement | 7h 30m | 50/50 |  |  | 1 | Yes | Training | Yes | No |  | TEC_PSE_CON_RE_PROS_CON
63 | 5.4.1 |  | Andrew Austerberry | Estates Training Session | 35 | 1 | Product Enablement/Customer | 0 | 0 | 0.5 |  | 0 | No | Training | No | No |  | TEC_PSE_CON_RE_PROS_CON
64 | 5.4.2 |  | Andrew Austerberry | Estates Reporting Training Session | 40 | 1 | Product Enablement/Customer | 0 | 0 | 0.5 |  | 0 | No | Training | No | No |  | TEC_PSE_CON_RE_PROS_CON
| 5.5 |  |  | Estates Full Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | No | No |  | TEC_PSE_CON_RE_PROS_CON
66 | 5.5.1 |  | Andrew Austerberry | Estates Full UAT | 42 | 5 | Customer/Implementation | 0 | 0 |  |  | 0 | Yes | UAT | No | No | Estates Full UAT Start | TEC_PSE_CON_RE_PROS_CON
69 | 5.5.2 |  | Andrew Austerberry | Estates Full Sign Off | 47 | 1 | Customer/Project Manager | 0 | 0 | 0.5 |  | 0 | No | Sign Off | Yes | No | Estates Full WP End | TEC_PSE_CON_RE_PROS_CON
70 | 5.5.3 |  | Andrew Austerberry | Estates Full Go Live | 48 | 1 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Go Live | No | No | Estates Full Go Live | TEC_PSE_CON_RE_PROS_CON
| 5.5.4 |  | Andrew Austerberry | Estates Full Hyper Care | 48 | 5 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Hyper Care | No | No |  | TEC_PSE_CON_RE_PROS_CON
| 5.5.5 |  | Est | Estates Full Hand Over to Support | 53 | 1 | Implementation/Support | 0 | 0 |  |  | 0 | No | Support | No | No |  | TEC_PSE_CON_RE_PROS_CON
89 | 6 |  | Andrew Austerberry | Case Management |  | 8 |  | 15 |  | 2 |  | 2 | [5 empty] | TEC_BAS_CON_ACMBO_PROS_CON
89 | 6.1 |  |  | Work Package Management (CASE MAN) |  |  | Implementation | 0 | 100 |  |  | 0 | No | Work Package Management | No | No |  | TEC_BAS_CON_ACMBO_PROS_CON
| 6.1.1 |  |  | Case Management WP Hardbooked and Budget | 53 | 1 | Implementation/Project Manager | 0 | 0 |  | 2 | 0 | No | Work Package Management | No | Yes |  | TEC_BAS_CON_ACMBO_PROS_CON
| 6.1.2 |  |  | Case Management Specification Agreed | 53 | 5 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | TEC_BAS_CON_ACMBO_PROS_CON
| 6.1.3 |  |  | Case Management Chat | 1 | 8 | Customer/Implementation/Project Manager | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | TEC_BAS_CON_ACMBO_PROS_CON
| 6.2 |  |  | Case Management Consultancy |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Consultancy | Yes | No |  | TEC_BAS_CON_ACMBO_PROS_CON
89 | 6.2.1 |  | Andrew Austerberry | Case Management Overview Session | 53 | 1 | Customer/Implementation | 0 | 0 | 0.5 |  |  | No | Consultancy | No | No | Case Management WP Start | TEC_BAS_CON_ACMBO_PROS_CON
91 | 6.3 |  | Andrew Austerberry | Case Management Configuration |  |  | Data Management | 7h 30m | 100 | 1 |  | 1 | Yes | Configuration | Yes | No |  | TEC_BAS_CON_ACMBO_PROS_CON
| 6.3.1 |  | Andrew Austerberry | Case Management | 54 | 1 |  | 0 | 0 |  |  |  | No | Configuration | No | Yes |  | TEC_BAS_CON_ACMBO_PROS_CON
| 6.3.2 |  |  | Template Document Queries | 54 | 1 |  | 0 | 0 |  |  |  | No | Configuration | No | Yes |  | TEC_BAS_CON_ACMBO_PROS_CON
| 6.3.3 |  |  | Query Creation | 54 | 1 |  | 0 | 0 |  |  |  | No | Configuration | No | Yes |  | TEC_BAS_CON_ACMBO_PROS_CON
| 6.4 |  |  | Case Management Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | TEC_BAS_CON_ACMBO_PROS_CON
93 | 6.4.1 |  | Andrew Austerberry | Case Mangement UAT | 55 | 5 | Customer/Implementation | 0 | 0 |  |  | 0 | Yes | UAT | No | No | Case Management UAT Start | TEC_BAS_CON_ACMBO_PROS_CON
95 | 6.4.2 |  | Andrew Austerberry | Case Management Sign Off | 60 | 1 | Customer/Project Manager | 0 | 0 | 0.5 |  | 0 | No | Sign Off | Yes | No | Case Management WP End | TEC_BAS_CON_ACMBO_PROS_CON
96 | 6.4.3 |  | Andrew Austerberry | Case Management Go Live | 61 | 1 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Go Live | No | No | Case Management Go Live | TEC_BAS_CON_ACMBO_PROS_CON
| 6.4.4 |  | Andrew Austerberry | Case Management Hyper Care | 61 | 5 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Hyper Care | No | No |  | TEC_BAS_CON_ACMBO_PROS_CON
| 6.4.5 |  | Est | Case Management Over to Support | 66 | 1 | Implementation/Support | 0 | 0 |  |  | 0 | No | Support | No | No |  | TEC_BAS_CON_ACMBO_PROS_CON
98 | 7 |  | Andrew Austerberry | Estates Lite |  | 36 |  | 22.5 |  | 3 |  | 3 | [5 empty] | TEC_PSE_CON_RELI_PROS_CON
98 | 7.1 |  |  | Work Package Management (EST LITE) |  |  | Implementation | 0 | 100 |  |  | 0 | No | Work Package Management | No | No |  | TEC_PSE_CON_RELI_PROS_CON
| 7.1.1 |  |  | Estates Lite WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 | 0 |  | 3 | 0 | No | Work Package Management | No | Yes |  | TEC_PSE_CON_RELI_PROS_CON
| 7.1.2 |  |  | Estates Lite Specification Agreed | 1 | 5 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | TEC_PSE_CON_RELI_PROS_CON
| 7.1.3 |  |  | Estates Lite Chat | 1 | 36 | Customer/Implementation/Project Manager | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | TEC_PSE_CON_RELI_PROS_CON
| 7.2 |  |  | Estates Lite Consultancy |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Consultancy | Yes | No |  | TEC_PSE_CON_RELI_PROS_CON
99 | 7.2.1 |  | Andrew Austerberry | Estates Lite Overview Session | 1 | 1 | Customer/Implementation | 0 | 0 | 0.5 |  | 0 | No | Consultancy | No | No | Estates Lite WP Start | TEC_PSE_CON_RELI_PROS_CON
| 7.3 |  | Andrew Austerberry | Estate Lite Data Management |  |  | Data Management/Implementation | 11h 15m | 50/50 |  |  | 1.5 | Yes | Data Management | Yes | No |  | TEC_PSE_CON_RELI_PROS_CON
100 | 7.3.1 |  | Andrew Austerberry | Estates Lite Test Data Collation | 2 | 10 | Customer | 0 |  |  |  | 0 | No | Data Management | No | No | Estates Lite Test Data Start | TEC_PSE_CON_RELI_PROS_CON
| 7.3.2 |  | Andrew Austerberry | Estate Lite Test Data Validation & Load |  |  |  | 0 | 0 |  |  |  | No | Data Management | No | No | Estates Lite Test Data End | TEC_PSE_CON_RELI_PROS_CON
104 | 7.3.2.1 |  | Andrew Austerberry | Estate Lite Load Test Data | 13 | 2 | Data Management | 0 | 0 | 0.5 |  | 0 | No | Data Management | No | No |  | TEC_PSE_CON_RELI_PROS_CON
105 | 7.3.2.2 |  | Andrew Austerberry | Estate Lite Test Data Playback Session | 16 | 1 | Customer/Implementation | 0 | 0 | 0.5 |  | 0 | No | Data Management | No | No |  | TEC_PSE_CON_RELI_PROS_CON
106 | 7.3.3 |  | Andrew Austerberry | Estate Lite Lite Full Data Collation | 16 | 5 | Customer | 0 | 0 |  |  |  | No | Data Management | No | No | Estates Lite - Data Start | TEC_PSE_CON_RELI_PROS_CON
| 7.3.4 |  | Andrew Austerberry | Estate Lite Final Data Validation & Load |  |  |  | 0 | 0 |  |  | 0 | No | Data Management | No | No | Estates Lite - Data End | TEC_PSE_CON_RELI_PROS_CON
110 | 7.3.4.1 |  | Andrew Austerberry | Estates Lite Data Load | 21 | 2 | Data Management | 0 | 0 | 0.5 |  | 0 | No | Data Management | No | Yes |  | TEC_PSE_CON_RELI_PROS_CON
| 7.4 |  |  | Estates Lite Data Playback Session | 24 | 1 | Customer/Implementation | 0 | 0 | 0.5 |  | 0 | No | Data Management | No | No |  | TEC_PSE_CON_RELI_PROS_CON
| 7.5 |  |  | Estates Lite Training |  |  | Product Enablement | 3h 45m | 100 |  |  | 0.5 | Yes | Training | Yes | No |  | TEC_PSE_CON_RELI_PROS_CON
112 | 7.5.1 |  | Andrew Austerberry | Estates Lite Training Session | 30 | 1 | Product Enablement/Customer | 0 | 0 |  |  | 0 | No | Training | No | No |  | TEC_PSE_CON_RELI_PROS_CON
| 7.6 |  |  | Estates Lite Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | TEC_PSE_CON_RELI_PROS_CON
113 | 7.6.1 |  | Andrew Austerberry | Estates Lite UAT | 31 | 5 | Customer/Implementation | 0 | 0 |  |  | 0 | No | UAT | No | No | Estates Lite UAT Start | TEC_PSE_CON_RELI_PROS_CON
116 | 7.6.2 |  | Andrew Austerberry | Estates Lite Sign Off | 36 | 1 | Customer/Project Manager | 0 | 0 | 0.5 |  |  | No | Sign Off | Yes | No | Estates Litet WP End | TEC_PSE_CON_RELI_PROS_CON
117 | 7.6.3 |  | Andrew Austerberry | Estates Lite Go Live | 37 | 1 | Customer/Implementation | 0 | 0 |  |  |  | No | Go Live | No | No | Estates Lite Go Live | TEC_PSE_CON_RELI_PROS_CON
| 7.6.4 |  | Andrew Austerberry | Estates Lite Hyper Care | 37 | 5 | Customer/Implementation | 0 | 0 |  |  |  | No | Hyper Care | No | No |  | TEC_PSE_CON_RELI_PROS_CON
| 7.6.5 |  | Est | Estates Hand Over to Support | 42 | 1 | Implementation/Support | 0 | 0 |  |  | 0 | No | Support | No | No |  | TEC_PSE_CON_RELI_PROS_CON
118 | 8 |  | Andrew Austerberry | CAFM Reactive |  | 42 |  | 48.75 |  | 8.5 |  | 6.5 | [5 empty] | TEC_BMA_CON_CAFMRE_PROS_CON
118 | 8.1 |  |  | Work Package Management (CAFM REACT) |  |  | Implementation | 0 | 0 |  |  | 0 | No | Work Package Management | No | Yes |  | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.1.1 |  |  | CAFM Reactive WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 | 0 |  | 6.5 | 0 | Yes | Work Package Management | No | Yes |  | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.1.2 |  |  | CAFM Reactive Specification Agreed | 1 | 5 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.1.3 |  |  | CAFM Reactive Chat | 1 | 42 | Customer/Implementation/Project Manager | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.2 |  |  | CAFM Reactive Consultancy |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Consultancy | Yes | No |  | TEC_BMA_CON_CAFMRE_PROS_CON
119 | 8.2.1 |  | Andrew Austerberry | CAFM Reactive Overview Session | 1 | 1 | Customer/Implementation |  |  | 0.5 |  |  | No | Consultancy | No | No | CAFM Reactive WP Start | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.3 |  | Andrew Austerberry | CAFM Reactive Data Management |  |  | Data Management/Implementation | 7h 30m | 80/20 |  |  | 1 | Yes | Data Management | Yes | No |  | TEC_BMA_CON_CAFMRE_PROS_CON
120 | 8.3.1 |  | Andrew Austerberry | Collate Reactive Data | 2 | 15 | Customer | 0 | 0 |  |  | 0 | No | Customer | No | No | CAFM Reactive Data Start | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.3.2 |  | Andrew Austerberry | Data Validation & Load (CAFMR) |  |  | Data Management | 0 | 0 | 1 |  | 0 | No | Data Management | No | No | CAFM Reactive Data End | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.3.2.1 |  | Andrew Austerberry | Load Data (CAFMR) | 17 | 2 | Data Management | 0 | 0 |  |  | 0 | Yes | Data Management | No | No |  | TEC_BMA_CON_CAFMRE_PROS_CON
123 | 8.4 |  | Andrew Austerberry | CAFM Reactive Configuration |  |  | Implementation | 22h 30m | 100 |  |  | 3 | Yes | Configuration | Yes | No |  | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.4.1 |  | Andrew Austerberry | Configure FixMy | 2 | 1 |  | 0 | 0 | 0.5 |  | 0 | No | Configuration | No | Yes |  | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.4.2 |  | Andrew Austerberry | Supplier Portal | 2 | 15 |  | 0 | 0 | 1 |  | 0 | No | Configuration | No | Yes |  | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.4.2.1 |  | Andrew Austerberry | Supplier Portal Config (Onboarded) |  |  |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.4.2.2 |  | Andrew Austerberry | AFP & Invoicing | 2 | 15 |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.4.2.3 |  | Andrew Austerberry | Supplier Portal Config (Non Onboarded) |  |  |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.4.3 |  | Andrew Austerberry | Helpdesk Actions | 2 | 15 |  | 0 | 0 | 0.5 |  | 0 | No | Configuration | No | Yes |  | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.4.4 |  | Andrew Austerberry | Testing & Playback |  |  |  | 0 | 0 | 0.5 |  | 0 | No | Configuration | No | Yes |  | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.4.4.1 |  | Andrew Austerberry | Peer Testing Config | 20 | 5 |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.4.4.2 |  | Andrew Austerberry | Amends from Peer testing | 25 | 5 |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.4.4.3 |  | Andrew Austerberry | Reactive Helpdesk Amends | 31 | 5 |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.4.5 |  | Andrew Austerberry | Reactive Helpdesk Playback | 30 | 1 | Customer/Implementation | 0 | 0 | 0.5 |  | 0 | No | Configuration | No | No |  | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.4.6 |  | Andrew Austerberry | Order Template |  |  |  | 0 | 0 | 0.5 |  | 0 | No | Configuration | No | Yes |  | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.4.6.1 |  | Andrew Austerberry | Amends to Order Template | 31 | 5 |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BMA_CON_CAFMRE_PROS_CON
178 | 8.4.7 |  | Andrew Austerberry | Projects Setup Lite |  |  | Implementation | 15h | 100 |  | 2 | 0 | No | Configuration | No | No |  | ?
| 8.4.7.1 |  | Andrew Austerberry | Project Templates | 2 | 15 |  | 0 | 0 | 1 |  | 0 | No | Configuration | No | Yes |  | ?
| 8.4.7.2 |  | Andrew Austerberry | Project Budgets | 2 | 15 |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | ?
| 8.4.7.3 |  | Andrew Austerberry | Test Projects | 2 | 15 |  | 0 | 0 | 1 |  | 0 | No | Configuration | No | Yes |  | ?
| 8.5 |  | Andrew Austerberry | CAFM Reactive Training |  |  | Product Enablement | 22h 30m | 100 |  |  | 1.5 | Yes | Training | Yes | No |  | TEC_BMA_CON_CAFMRE_PROS_CON
140 | 8.5.1 |  | Andrew Austerberry | Supplier Portal Training | 21 | 1 | Product Enablement/Customer | 0 | 0 | 0.5 |  | 0 | No | Training | No | No |  | TEC_BMA_CON_CAFMRE_PROS_CON
141 | 8.5.2 |  | Andrew Austerberry | Reactive Helpdesk Training | 36 | 1 | Product Enablement/Customer | 0 | 0 | 0.5 |  | 0 | No | Training | No | No |  | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.6 |  |  | CAFM Reactive Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | TEC_BMA_CON_CAFMRE_PROS_CON
143 | 8.6.1 |  | Andrew Austerberry | CAFM Reactive UAT | 37 | 5 | Customer/Implementation | 0 | 0 |  |  | 0 | No | UAT | No | No | CAFMR UAT Start | TEC_BMA_CON_CAFMRE_PROS_CON
145 | 8.6.2 |  | Andrew Austerberry | CAFM Reactive Sign Off | 42 | 1 | Customer/Project Manager | 0 | 0 | 0.5 |  | 0 | No | Sign Off | Yes | No | CAFM Reactive WP End | TEC_BMA_CON_CAFMRE_PROS_CON
146 | 8.6.3 |  | Andrew Austerberry | CAFM Reactive Go Live | 43 | 1 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Go Live | No | No | CAFM Reactive Go Live | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.6.4 |  | Andrew Austerberry | CAFM Reactive Hyper Care | 44 | 5 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Hyper Care | No | No |  | TEC_BMA_CON_CAFMRE_PROS_CON
| 8.6.5 |  | Est | CAFM Reactive Hand Over to Support | 49 | 1 | Implementation/Support | 0 | 0 |  |  | 0 | No | Support | No | No |  | TEC_BMA_CON_CAFMRE_PROS_CON
147 | 9 |  | Andrew Austerberry | CAFM Planned |  | 42 |  | 48.75 |  | 8.5 |  | 6.5 | [5 empty] | TEC_BCO_CON_CAFMPL_PROS_CON
147 | 9.1 |  |  | Work Package Management (CAFM PLAN) |  |  | Implementation | 0 | 0 |  |  | 0 | No | Work Package Management | No | Yes |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.1.1 |  |  | Core Data WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 | 0 |  | 6.5 | 0 | No | Work Package Management | No | Yes |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.1.2 |  |  | Case Management Specification Agreed | 1 | 5 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.1.3 |  |  | CAFM Planned Chat | 1 | 42 | Customer/Implementation/Project Manager | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.2 |  |  | CAFM Planned Consultancy |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Consultancy | Yes | No |  | TEC_BCO_CON_CAFMPL_PROS_CON
148 | 9.2.1 |  | Andrew Austerberry | PPM Overview Session | 1 | 1 | Customer/Implementation | 0 |  | 0.5 |  | 0 | No | Consultancy | No | No | CAFM Planned WP Start | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.3 |  | Andrew Austerberry | CAFM Planned Data Management |  |  | Data Management/Implementation | 15h 0m | 50/50 |  |  | 2 | Yes | Data Management | Yes | No |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.3.1 |  |  | CAFM Planned Data Mapping Session | 2 | 1 | Customer/Implementation | 0 |  | 1 |  |  |  | Data Management | No | No |  | TEC_BCO_CON_CAFMPL_PROS_CON
149 | 9.3.2 |  | Andrew Austerberry | Collate Planned Test Data | 2 | 15 | Customer | 0 | 0 |  |  | 0 | No | Customer | No | No | CAFM Planned Data Start | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.3.3 |  |  | Data Validation & Load (CAFMP) |  |  | Data Management | 0 | 0 | 1 |  | 0 |  | Data Management | No | No | CAFM Planned Data End | TEC_BCO_CON_CAFMPL_PROS_CON
155 | 9.3.3.1 |  | Andrew Austerberry | Load PPM Master Data & Link to SitesBlocksRooms | 16 | 2 |  | 0 | 0 |  |  | 0 | No | Data Management | No | Yes |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.3.3.2 |  | Andrew Austerberry | Load AssetEquipment Data | 16 | 2 |  | 0 | 0 |  |  | 0 | No | Data Management | No | Yes |  | TEC_BCO_CON_CAFMPL_PROS_CON
156 | 9.4 |  | Andrew Austerberry | CAFM Planned Configuration |  |  | Implementation | 15h 0m | 0 |  |  | 2.5 | Yes | Configuration | Yes | No |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.4.1 |  | Andrew Austerberry | Configure PPMs InternalExternal |  |  |  | 0 | 0 | 0.5 |  | 0 | No | Configuration | No | Yes |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.4.2 |  | Andrew Austerberry | Playback PPM Configuration | 2 | 1 | Implementation/Customer | 0 | 0 | 0.5 |  | 0 | No | Configuration | No | No |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.4.3 |  | Andrew Austerberry | Supplier Portal Configuration (Onboarded) |  |  |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.4.3.1 |  | Andrew Austerberry | Supplier Portal | 2 | 15 |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.4.3.2 |  | Andrew Austerberry | AFP & Invoicing | 2 | 15 |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.4.4 |  | Andrew Austerberry | Supplier Portal Configuration (Non Onboarded) |  |  |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.4.4.1 |  | Andrew Austerberry | Helpdesk Actions | 2 | 15 |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.4.5 |  | Andrew Austerberry | Testing & Playback | 20 | 5 | Implementation/Customer | 0 | 0 | 0.5 |  | 0 | No | Configuration | No | No |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.4.5.1 |  | Andrew Austerberry | Peer Testing Config | 25 | 5 |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.4.5.2 |  | Andrew Austerberry | Amends from Peer Testing | 30 | 1 |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.4.5.4 |  | Andrew Austerberry | Planned Helpdesk Amends | 31 | 5 |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.4.6 |  | Andrew Austerberry | Planned Helpdesk Playback | 36 | 1 | Implementation/Customer | 0 | 0 | 0.5 |  | 0 | No | Configuration | No | No |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.4.7 |  | Andrew Austerberry | Order Template |  |  |  | 0 | 0 | 0.5 |  | 0 | No | Configuration | No | Yes |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.4.7.1 |  | Andrew Austerberry | Amends to Order Template | 31 | 5 |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.4.7 |  | Andrew Austerberry | Projects Setup Lite |  | 1 | Implementation | 15h 0m | 0 |  | 2 | 0 | No | Configuration | No | No |  | ?
178 | 9.4.7.1 |  | Andrew Austerberry | Project Templates | 2 | 15 |  | 0 | 0 | 1 |  | 0 | No | Configuration | No | Yes |  | ?
| 9.4.7.2 |  | Andrew Austerberry | Project Budgets | 2 | 15 |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | ?
| 9.4.7.3 |  | Andrew Austerberry | Test Projects | 2 | 15 |  | 0 | 0 | 1 |  | 0 | No | Configuration | No | Yes |  | ?
| 9.5 |  | Andrew Austerberry | CAFM Planned Training |  | 2 | Product Enablement | 7h 30m | 100 |  |  | 1 | Yes | Training | Yes | No |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.5.1 |  | Andrew Austerberry | Supplier Portal Training | 21 | 1 | Product Enablement/Customer | 0 | 0 | 0.5 |  | 0 | No | Training | No | No |  | TEC_BCO_CON_CAFMPL_PROS_CON
169 | 9.5.2 |  | Andrew Austerberry | PPM Training | 36 | 1 | Product Enablement/Customer | 0 | 0 | 0.5 |  | 0 | No | Training | No | No |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.6 |  |  | CAFM Planned Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | TEC_BCO_CON_CAFMPL_PROS_CON
172 | 9.6.1 |  | Andrew Austerberry | CAFM Planned UAT | 37 | 5 | Customer/Implementation | 0 | 0 |  |  | 0 | No | 0 | No | No | CAFM Planned UAT Start | TEC_BCO_CON_CAFMPL_PROS_CON
175 | 9.6.2 |  | Andrew Austerberry | CAFM Planned Sign Off | 42 | 1 | Customer/Project Manager | 0 | 0 | 0.5 |  | 0 | No | Sign Off | Yes | No | CAFM Planned WP End | TEC_BCO_CON_CAFMPL_PROS_CON
176 | 9.6.3 |  | Andrew Austerberry | CAFM Planned Go Live | 43 | 1 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Go Live | No | No | CAFM Planned Go Live | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.6.4 |  | Andrew Austerberry | CAFM Planned Hyper Care | 44 | 5 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Hyper Care | No | No |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 9.6.5 |  | Est | CAFM Planned Hand Over to Support | 49 | 1 | Implementation/Support | 0 | 0 |  |  | 0 | No | Support | No | No |  | TEC_BCO_CON_CAFMPL_PROS_CON
| 10 |  | Andrew Austerberry | Finance Interface |  | 30 |  | 37.5 |  | 5 |  | 5 | [5 empty] | ?
| 10.1 |  | Finance Interface | Work Package Management (FIN INT) |  |  | OnBoarding | 0 | 0 |  |  | 0 | No | Work Package Management | No | Yes |  | ?
| 10.1.1 |  |  | Finance Interface WP Hardbooked and Budget | 1 | 1 | OnBoarding/Project Manager | 0 | 0 |  | 5 | 0 | No | Work Package Management | No | Yes |  | ?
| 10.1.2 |  |  | Finance Interface Chat | 1 | 30 | Customer/Implementation/Project Manager | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | ?
| 10.2 |  |  | Finance Interface Consultancy |  |  | OnBoarding | 11h 15m | 100 |  |  | 1.5 | Yes | Consultancy | Yes | No |  | ?
| 10.2.1 |  | Andrew Austerberry | Finance Interface Overview Session | 1 | 1 | Customer/OnBoarding | 0 | 0 | 0.5 |  | 0 | No | Consultancy | No | No | Finance Interface WP Start | ?
| 10.2.2 |  |  | Finance Interface ICD Creation | 2 | 10 | OnBoarding | 0 | 0 | 0.5 |  | 0 | No | Consultancy | No | No | Finance Interfacenance Interface Creation Start | ?
| 10.2.3 |  |  | Finance Interface ICD Sign Off | 12 | 1 | Customer/OnBoarding | 0 | 0 | 0.5 |  | 0 | No | Consultancy | No | No | Finance Interfacenance Interface Creation End | ?
| 10.3 |  |  | Finance Interface Development |  |  | Development | 22h 30m | 100 |  |  | 3 | Yes | Development | Yes | No |  | ?
| 10.3.1 |  | Andrew Austerberry | Finance Interface Build | 13 | 5 | Development | 0 | 0 | 1 |  | 0 | 0 | Development | No | Yes | Finance Interfacenance Interface Dev Start | ?
| 10.3.2 |  |  | Finance Interface Test | 18 | 5 | Development/OnBoarding | 0 | 0 | 1 |  | 0 | 0 | Development | No | Yes |  | ?
| 10.3.3 |  |  | Finance Interface Internal Sign Off | 23 | 1 | QA/OnBoarding | 0 | 0 | 1 |  | 0 | 0 | QA | No | Yes | Finance Interfacenance Interface Dev End | ?
| 10.4 |  |  | Finance Interface Close |  |  | OnBoarding | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | ?
| 10.4.1 |  | Andrew Austerberry | Finance Interface UAT | 24 | 5 | Customer/OnBoarding | 0 | 0 |  |  | 0 | No | UAT | No | No | Finance Interface UAT Start | ?
| 10.4.2 |  | Andrew Austerberry | Finance Interface Sign Off | 29 | 1 | Customer/Project Manager | 0 | 0 | 0.5 |  | 0 | No | Sign Off | Yes | No | Finance Interface WP End | ?
| 10.4.3 |  | Andrew Austerberry | Finance Interface Go Live | 30 | 1 | Customer/OnBoarding | 0 | 0 |  |  | 0 | No | Go Live | No | No | Finance Interface Go Live | ?
| 10.4.4 |  | Andrew Austerberry | Finance Interface Hyper Care | 30 | 5 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Hyper Care | No | No |  | ?
| 10.4.5 |  | Est | Finance Interface Hand Over to Support | 35 | 1 | Implementation/Support | 0 | 0 |  |  | 0 | No | Support | No | No
| 11 |  |  | Reporting |  | 32 |  | 15 |  | 2 |  | 2
| 11.1 |  |  | Work Package Management (Reporting) |  |  | Data Management | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | ?
| 11.1.1 |  |  | Reporting WP Hardbooked and Budget | 1 | 1 | Data Management/Project Manager | 0 | 0 |  | 2 | 0 | No | Work Package Management | No | Yes |  | ?
| 11.1.2 |  |  | Reporting Specification Agreed | 1 | 5 | Customer/Data Management | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | ?
| 11.1.3 |  |  | Reporting Chat | 1 | 32 | Customer/Data Management/Project Manager | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | ?
| 11.2 |  | Andrew Austerberry | Reporting Data Management |  |  | Data Management | 3h 45m | 100 |  |  | 0.5 | Yes | Data Management | Yes | No |  | ?
| 11.2.1 |  | Andrew Austerberry | Reporting Overview Session | 1 | 1 | Data Management | 0 | 0 | 0.5 |  | 0 | No | Data Management | No | No | Reporting WP Start | ?
| 11.2.2 |  |  | Collate Reporting Requirments |  | 20 | Customer | 0 | 0 |  |  | 0 | 0 | Data Management | 0 |  | Reporting Data Start | ?
| 11.2.3 |  | Andrew Austerberry | Project Budgets |  | 6 | Data Management | 0 | 0 |  |  | 0 | No | Data Management | No | No | Reporting Data End | ?
| 11.2.4 |  |  | Deliver Scripts/Reports/Dashboards |  | 5 | Data Management | 0 | 0 |  |  | 0 | 0 | Data Management | 0 |  |  | ?
| 11.3 |  | Andrew Austerberry | Reporting Training |  | 2 | Data Management | 7h 30m | 0 |  |  | 1 | Yes | Training | Yes | No |  | ?
| 11.3.1 |  | Andrew Austerberry | Training Session 1 |  | 1 | Data Management/Customer | 0 | 0 | 1 |  | 0 | No | Training | No | No |  | ?
| 11.4 |  |  | Reporting Close |  |  | Data Management | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | TEC_BAS_CON_PRPR_PROS_CON
| 11.4.1 |  | Andrew Austerberry | Reporting UAT | 24 | 5 | Customer/Data Management | 0 | 0 |  |  | 0 | No | UAT | No | No | Reporting UAT Start | ?
| 11.4.2 |  | Andrew Austerberry | Reporting Sign Off | 29 | 1 | Customer/Project Manager | 0 | 0 | 0.5 |  | 0 | No | Sign Off | Yes | No | Reporting WP End | ?
| 11.4.3 |  | Andrew Austerberry | Reporting Go Live | 30 | 1 | Customer/Data Management | 0 | 0 |  |  | 0 | No | Go Live | No | No | Reporting Go Live | ?
| 11.4.4 |  | Andrew Austerberry | Reporting Hyper Care | 30 | 5 | Customer/Data Management | 0 | 0 |  |  | 0 | No | Hyper Care | No | No |  | ?
| 11.4.5 |  | Est | Reporting Hand Over to Support | 35 | 1 | Data Management/Support | 0 | 0 |  |  | 0 | No | Support | No | No
| 12 |  |  | System Admin Training |  | 32 |  | 7.5 |  | 1 |  | 1 | 0 | 0 | 0
| 12.1 |  |  | Work Package Management (Sys Admin) |  |  | Data Management | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | ?
| 12.1.1 |  |  | System Admin WP Hardbooked and Budget | 1 | 1 | Data Management/Project Manager | 0 | 0 |  | 1 | 0 | No | Work Package Management | No | Yes |  | ?
| 12.2 |  |  | System Admin Specification Agreed | 1 | 5 | Customer/Data Management | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | ?
| 12.1.2 |  |  | System Admin Chat | 1 | 18 | Customer/Data Management/Project Manager | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | ?
| 12.2 |  | Andrew Austerberry | System Admin Training |  |  | Data Management | 7h 30m | 0 |  |  | 1 | Yes | Training | Yes | No |  | ?
| 12.2.1 |  | Andrew Austerberry | Training Session 1 | 7 | 1 | Data Management/Customer | 0 | 0 | 0.5 |  | 0 | No | Training | No | No |  | ?
| 12.3 |  | Andrew Austerberry | System Admin UAT | 8 | 5 | Customer/Data Management | 0 | 0 |  |  | 0 | No | UAT | No | No |  | ?
| 12.3.1 |  | Andrew Austerberry | System Admin Sign Off | 13 | 1 | Customer/Project Manager | 0 | 0 | 0.5 |  | 0 | No | Sign Off | Yes | No |  | ?
| 12.3.2 |  | Andrew Austerberry | System Admin Hyper Care | 13 | 5 | Customer/Data Management | 0 | 0 |  |  | 0 | No | Hyper Care | No | No |  | ?
| 12.3.3 |  | Est | P&P Full Hand Over to Support | 18 | 1 | Implementation/Support | 0 | 0 |  |  | 0 | No | Support | No | No |  | TEC_BAS_CON_PRPR_PROS_CON
183 | 13 |  | Andrew Austerberry | Projects & Programmes Full |  | 39 |  | 90 |  | 12 |  | 12 |  | 0 |  |  |  | TEC_BAS_CON_PRPR_PROS_CON
183 | 13.1 |  |  | Work Package Management (P&P Full) |  |  | Implementation | 0 |  |  |  |  | No | Work Package Management | No | No |  | TEC_BAS_CON_PRPR_PROS_CON
| 13.1.1 |  |  | Projects & Programmes Full WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 |  |  | 12 |  | No | Work Package Management | No | Yes |  | TEC_BAS_CON_PRPR_PROS_CON
| 13.1.2 |  |  | Projects & Programmes Full Specification Agreed | 1 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BAS_CON_PRPR_PROS_CON
| 13.1.3 |  |  | Projects & Programmes Full Chat | 1 | 39 | Customer/Implementation/Project Manager | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BAS_CON_PRPR_PROS_CON
| 13.2 |  |  | Projects & Programmes Full Consultancy |  |  | Implementation | 11h 15m | 100 |  |  | 1.5 | Yes | Consultancy | Yes | No |  | TEC_BAS_CON_PRPR_PROS_CON
184 | 13.2.1 |  | Andrew Austerberry | Projects Overview Session 1 | 1 | 1 | Customer/Implementation | 0 |  | 0.75 |  |  | No | Consultancy | No | No | P&P WP Start | TEC_BAS_CON_PRPR_PROS_CON
185 | 13.2.2 |  | Andrew Austerberry | Projects Overview Session 2 | 7 | 1 | Customer/Implementation | 0 |  | 0.75 |  |  | No | Consultancy | No | No |  | TEC_BAS_CON_PRPR_PROS_CON
| 13.3 |  | Andrew Austerberry | Projects & Programmes Full Configuration |  |  | Implementation | 37h 30m | 100 |  |  | 5 | Yes | Configuration | Yes | No |  | TEC_BAS_CON_PRPR_PROS_CON
186 | 13.3.1 |  | Andrew Austerberry | Projects Setup | 2 | 15 |  | 0 |  | 1 |  |  | No | Configuration | No | Yes |  | TEC_BAS_CON_PRPR_PROS_CON
| 13.3.2 |  | Andrew Austerberry | Projects Templates | 2 | 15 |  | 0 |  | 1 |  |  | No | Configuration | No | Yes |  | TEC_BAS_CON_PRPR_PROS_CON
| 13.3.3 |  | Andrew Austerberry | Projects Settings & Config | 2 | 15 |  | 0 |  | 1 |  |  | No | Configuration | No | Yes |  | TEC_BAS_CON_PRPR_PROS_CON
| 13.3.4 |  |  | Projects Config Playback | 18 | 1 |  | 0 |  | 2 |  |  | No | Configuration | No | No
| 13.4 |  | Andrew Austerberry | Projects & Programmes Full Data Management |  |  | Data Management | 15h 0m | 100 |  |  | 3 | Yes | Data Management | Yes | No |  | TEC_BAS_CON_PRPR_PROS_CON
190 | 13.4.1 |  | Andrew Austerberry | Client Collate Budget Data | 2 | 15 | Customer | 0 |  |  |  |  | No | Customer | No | No | P&P Budget Data Start | TEC_BAS_CON_PRPR_PROS_CON
191 | 13.4.2 |  | Andrew Austerberry | Load Budget Data |  |  | Data Management | 0 |  | 1.5 |  |  | No | Data Management | No | No |  | TEC_BAS_CON_PRPR_PROS_CON
193 | 13.4.3 |  | Andrew Austerberry | Client Collate Project Data | 16 | 15 | Customer | 0 |  |  |  |  | No | Customer | No | No | P&P Project Data Start | TEC_BAS_CON_PRPR_PROS_CON
194 | 13.4.4 |  | Andrew Austerberry | Load Project Data | 31 | 2 | Data Management | 0 |  | 1.5 |  |  | No | Data Management | No | No | P&P Project Data End | TEC_BAS_CON_PRPR_PROS_CON
| 13.5 |  | Andrew Austerberry | Projects & Programmes Full Training |  |  | Product Enablement | 15h 0m | 100 |  |  | 2 | Yes | Training | Yes | No |  | TEC_BAS_CON_PRPR_PROS_CON
196 | 13.5.1 |  | Andrew Austerberry | Training Session 1 | 22 | 1 | Product Enablement/Customer | 0 |  | 1 |  |  | No | Training | No | No |  | TEC_BAS_CON_PRPR_PROS_CON
197 | 13.5.2 |  | Andrew Austerberry | Training session 2 | 33 | 1 | Product Enablement/Customer | 0 |  | 1 |  |  | No | Training | No | No |  | TEC_BAS_CON_PRPR_PROS_CON
| 13.6 |  |  | Projects & Programmes Full Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | TEC_BAS_CON_PRPR_PROS_CON
198 | 13.6.1 |  | Andrew Austerberry | P&P Full UAT | 34 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | UAT | No | No | P&P Full UAT Start | TEC_BAS_CON_PRPR_PROS_CON
199 | 13.6.2 |  | Andrew Austerberry | P&P Full Sign Off | 39 | 1 | Customer/Project Manager | 0 |  | 0.5 |  | 0 | No | Sign Off | Yes | No | P&P Full WP End | TEC_BAS_CON_PRPR_PROS_CON
200 | 13.6.3 |  | Andrew Austerberry | P&P Full Go Live | 40 | 1 | Customer/Implementation | 0 |  |  |  | 0 | No | Go Live | No | No | P&P Full Go Live | TEC_BAS_CON_PRPR_PROS_CON
| 13.6.4 |  | Andrew Austerberry | P&P Full Hyper Care | 40 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Hyper Care | No | No |  | TEC_BAS_CON_PRPR_PROS_CON
| 13.6.5 |  | Est | P&P Full Hand Over to Support | 45 | 1 | Implementation/Support | 0 |  |  |  | 0 | No | Support | No | No |  | TEC_BAS_CON_PRPR_PROS_CON
| 14 |  | Andrew Austerberry | Permit To Work |  | 10 |  | 60 |  | 8 |  | 8 | [5 empty] | TEC_BCO_CON_PTW_PROS_CON
| 14.1 |  |  | Work Package Management (P2W) |  |  | Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_PTW_PROS_CON
| 14.1.1 |  |  | Permit To Work WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 |  |  | 8 | 0 | No | Work Package Management | No | Yes |  | TEC_BCO_CON_PTW_PROS_CON
| 14.1.2 |  |  | Permit To Work Specification Agreed | 1 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_PTW_PROS_CON
| 14.1.3 |  |  | Permit To Work Chat | 1 | 37 | Customer/Implementation/Project Manager | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_PTW_PROS_CON
| 14.2 |  |  | Permit To Work Consultancy |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Consultancy | Yes | No |  | TEC_BCO_CON_PTW_PROS_CON
| 14.2.2 |  | Andrew Austerberry | Permit To Work Overview Session | 1 | 1 | Customer/Implementation | 0 |  | 0.5 |  | 0 | No | Consultancy | No | No | P2W WP Start | TEC_BCO_CON_PTW_PROS_CON
| 14.3 |  | Andrew Austerberry | Permit to Work Data Management |  |  | Implementation | 15h | 100 |  |  | 2 | Yes | Data Management | Yes | No |  | TEC_BCO_CON_PTW_PROS_CON
| 14.3.1 |  | Andrew Austerberry | Collate Permit to Work Data | 2 | 10 | Customer | 0 |  |  |  | 0 | No | Data Management | No | No | P2W Data Start | TEC_BCO_CON_PTW_PROS_CON
| 14.3.2 |  | Andrew Austerberry | Permit to Work Data Validation & Load | 12 | 2 | Data Management | 0 |  | 2 |  | 0 | No | Data Management | No | No | P2W Data End | TEC_BCO_CON_PTW_PROS_CON
| 14.4 |  | Andrew Austerberry | Permit to Work Configuration | 13 | 5 | Implementation | 30h | 100 | 4 |  | 4 | Yes | Configuration | Yes | No |  | TEC_BCO_CON_PTW_PROS_CON
| 14.5 |  | Andrew Austerberry | Permit to Work Training |  |  | Product Enablement | 7h 30m |  |  |  | 1 | Yes | Training | Yes | No |  | TEC_BCO_CON_PTW_PROS_CON
| 14.5.1 |  | Andrew Austerberry | Training Session 1 | 20 | 1 | Product Enablement/Customer |  |  | 1 |  |  | No | Training | No | No |  | TEC_BCO_CON_PTW_PROS_CON
| 14.6 |  |  | Permit To Work Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | TEC_BCO_CON_PTW_PROS_CON
| 14.6.1 |  | Andrew Austerberry | Permit To Work UAT | 21 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | UAT | No | No | P2W UAT Start | TEC_BCO_CON_PTW_PROS_CON
| 14.6.2 |  | Andrew Austerberry | Permit To Work Sign Off | 26 | 1 | Customer/Project Manager | 0 |  | 0.5 |  | 0 | No | Sign Off | Yes | No | P2W WP End | TEC_BCO_CON_PTW_PROS_CON
| 14.6.3 |  | Andrew Austerberry | Permit To Work Go Live | 27 | 1 | Customer/Implementation | 0 |  |  |  | 0 | No | Go Live | No | No | P2W Go Live | TEC_BCO_CON_PTW_PROS_CON
| 14.6.4 |  | Andrew Austerberry | Permit To Work Hyper Care | 27 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Hyper Care | No | No |  | TEC_BCO_CON_PTW_PROS_CON
| 14.6.5 |  | Est | Permit To Work Hand Over to Support | 32 | 1 | Implementation/Support | 0 |  |  |  | 0 | No | Support | No | No |  | TEC_BCO_CON_PTW_PROS_CON
| 15 |  | Andrew Austerberry | Health & Safety |  | 18 |  | 22.5 |  | 3 |  | 3 | [5 empty] | TEC_BCO_CON_HSIE_PROS_CON
| 15.1 |  |  | Work Package Management (H&S) |  |  | Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_HSIE_PROS_CON
| 15.1.1 |  |  | H&S WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 |  |  | 3 | 0 | No | Work Package Management | No | Yes |  | TEC_BCO_CON_HSIE_PROS_CON
| 15.1.2 |  |  | H&S Specification Agreed | 1 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_HSIE_PROS_CON
| 15.1.3 |  |  | H&S Chat | 1 | 18 | Customer/Implementation/Project Manager | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_HSIE_PROS_CON
| 15.2 |  |  | H&S Consultancy |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Consultancy | Yes | No |  | TEC_BCO_CON_HSIE_PROS_CON
| 15.2.1 |  | Andrew Austerberry | H&S Overview Session | 1 | 1 |  | 0 |  | 0.5 |  |  | Yes | Consultancy | Yes | No | H&S WP Start | TEC_BCO_CON_HSIE_PROS_CON
| 15.4 |  | Andrew Austerberry | H&S Configuration |  |  | Implementation | 7h 30m | 100 |  |  | 1.5 | Yes | Configuration | Yes | No |  | TEC_BCO_CON_HSIE_PROS_CON
| 15.4.1 |  | Andrew Austerberry | Config Actions etc | 2 | 5 |  | 0 |  | 0.5 |  |  | No | Configuration | No | Yes |  | TEC_BCO_CON_HSIE_PROS_CON
| 15.4.2 |  | Andrew Austerberry | Playback | 8 | 1 | Implementation/Customer | 0 |  | 0.5 |  |  | No | Configuration | No | No |  | TEC_BCO_CON_HSIE_PROS_CON
| 15.4.3 |  | Andrew Austerberry | Amends | 10 | 5 |  | 0 |  |  |  |  | No | Configuration | No | Yes |  | TEC_BCO_CON_HSIE_PROS_CON
| 15.4.4 |  | Andrew Austerberry | Reporting | 16 | 1 | Implementation/Customer | 0 |  | 0.5 |  |  | No | Configuration | No | No |  | TEC_BCO_CON_HSIE_PROS_CON
| 15.5 |  | Andrew Austerberry | H&S Training |  |  | Product Enablement | 3h 45m | 100 |  |  | 0.5 | Yes | Training | Yes | No |  | TEC_BCO_CON_HSIE_PROS_CON
| 15.5.1 |  | Andrew Austerberry | Training Session 1 | 12 | 1 | Product Enablement/Customer | 0 |  | 0.5 |  |  | No | Training | No | No |  | TEC_BCO_CON_HSIE_PROS_CON
| 15.6 |  |  | H&S Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | TEC_BCO_CON_HSIE_PROS_CON
| 15.6.1 |  | Andrew Austerberry | H&S UAT | 13 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | UAT | No | No | H&S UAT Start | TEC_BCO_CON_HSIE_PROS_CON
| 15.6.2 |  | Andrew Austerberry | H&S Sign Off | 18 | 1 | Customer/Project Manager | 0 |  | 0.5 |  | 0 | No | Sign Off | Yes | No | H&S WP End | TEC_BCO_CON_HSIE_PROS_CON
| 15.6.3 |  | Andrew Austerberry | H&S Go Live | 19 | 1 | Customer/Implementation | 0 |  |  |  | 0 | No | Go Live | No | No | H&S Go Live | TEC_BCO_CON_HSIE_PROS_CON
| 15.6.4 |  | Andrew Austerberry | H&S Hyper Care | 19 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Hyper Care | No | No |  | TEC_BCO_CON_HSIE_PROS_CON
| 15.6.5 |  | Est | H&S Hand Over to Support | 24 | 1 | Implementation/Support | 0 |  |  |  | 0 | No | Support | No | No |  | TEC_BCO_CON_HSIE_PROS_CON
218 | 16 |  | Andrew Austerberry | Asbestos Surveys |  | 20 |  | 22.5 |  | 3 |  | 3 | [5 empty] | TEC_BCO_CON_SURAB_PROS_CON
| 16.1 |  |  | Work Package Management (Asbestos) |  |  | Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_SURAB_PROS_CON
| 16.1.1 |  |  | Asbestos WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 |  |  | 3 | 0 | No | Work Package Management | No | Yes |  | TEC_BCO_CON_SURAB_PROS_CON
| 16.1.2 |  |  | Asbestos Specification Agreed | 1 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_SURAB_PROS_CON
| 16.1.3 |  |  | Asbestos Chat | 1 | 20 | Customer/Implementation/Project Manager | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_SURAB_PROS_CON
| 16.2 |  |  | Asbestos Consultancy |  |  | Implementation | 7h 30m | 100 |  |  | 1 | Yes | Consultancy | Yes | No |  | TEC_BCO_CON_SURAB_PROS_CON
| 16.2.1 |  | Andrew Austerberry | Asbestos Overview Session | 1 | 1 | Customer/Implementation | 0 |  | 1 |  | 0 | No | Consultancy | No | No | Asbestos WP Start | TEC_BCO_CON_SURAB_PROS_CON
| 16.3 |  | Andrew Austerberry | Asbestos Configuration | 2 | 5 | Implementation | 3h 45m | 100 | 0.5 |  | 0.5 | Yes | Configuration | Yes | No |  | TEC_BCO_CON_SURAB_PROS_CON
| 16.4 |  | Andrew Austerberry | Asbestos Training |  |  | Product Enablement | 7h 30m |  |  |  | 1 | Yes | Training | Yes | No |  | TEC_BCO_CON_SURAB_PROS_CON
| 16.4.1 |  | Andrew Austerberry | Asbestos Importer Training | 7 | 1 | Product Enablement/Customer | 0 |  | 0.5 |  | 0 | No | Training | No | No |  | TEC_BCO_CON_SURAB_PROS_CON
| 16.4.2 |  | Andrew Austerberry | Asbestos Train the Trainer | 14 | 1 | Product Enablement/Customer | 0 |  | 0.5 |  | 0 | No | Training | No | No |  | TEC_BCO_CON_SURAB_PROS_CON
| 16.5 |  |  | Asbestos Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | TEC_BCO_CON_SURAB_PROS_CON
224 | 16.5.1 |  | Andrew Austerberry | Asbestos UAT | 15 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | UAT | No | No | Asbestos UAT Start | TEC_BCO_CON_SURAB_PROS_CON
227 | 16.5.2 |  | Andrew Austerberry | Asbestos Sign Off | 20 | 1 | Customer/Project Manager | 0 |  | 0.5 |  | 0 | No | Sign Off | Yes | No | Asbestos WP End | TEC_BCO_CON_SURAB_PROS_CON
228 | 16.5.3 |  | Andrew Austerberry | Asbestos Go Live | 21 | 1 | Customer/Implementation | 0 |  |  |  | 0 | No | Go Live | No | No | Asbestos Go Live | TEC_BCO_CON_SURAB_PROS_CON
| 16.5.4 |  | Andrew Austerberry | Asbestos Hyper Care | 21 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Hyper Care | No | No |  | TEC_BCO_CON_SURAB_PROS_CON
| 16.5.5 |  | Est | Asbestos Hand Over to Support | 26 | 1 | Implementation/Support | 0 |  |  |  | 0 | No | Support | No | No |  | TEC_BCO_CON_SURAB_PROS_CON
| 17 |  | Andrew Austerberry | Assurance Module |  | 28 |  | 22.5 |  | 3 |  | 3 | [5 empty] | TEC_BCO_CON_ASSUR_PROS_CON
| 17.1 |  |  | Work Package Management (Assurance) |  |  | Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_ASSUR_PROS_CON
| 17.1.1 |  |  | Assurance WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 |  |  | 3 | 0 | No | Work Package Management | No | Yes |  | TEC_BCO_CON_ASSUR_PROS_CON
| 17.1.2 |  |  | Assurance Specification Agreed | 1 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_ASSUR_PROS_CON
| 17.1.3 |  |  | Assurance Chat | 1 | 28 | Customer/Implementation/Project Manager | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_ASSUR_PROS_CON
| 17.2 |  |  | Assurance Consultancy |  |  | Implementation | 7h 30m | 100 |  |  | 1 | Yes | Consultancy | Yes | No |  | TEC_BCO_CON_ASSUR_PROS_CON
| 17.2.1 |  | Andrew Austerberry | Kick Off / System spin up | 1 | 1 | Implementation | 0 |  |  |  | 0 | No | Consultancy | No | Yes |  | TEC_BCO_CON_ASSUR_PROS_CON
| 17.2.2 |  | Andrew Austerberry | Assurance Overview Session | 1 | 1 | Customer/Implementation | 0 |  | 1 |  | 0 | No | Consultancy | No | No | Assurance Full WP Start | TEC_BCO_CON_ASSUR_PROS_CON
| 17.3 |  | Andrew Austerberry | Assurance Data Management |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Data Management | Yes | No |  | TEC_BCO_CON_ASSUR_PROS_CON
| 17.3.1 |  | Andrew Austerberry | Collate Assurance Data | 2 | 10 | Customer | 0 |  |  |  | 0 | No | Data Management | No | No | Assurance Data Start | TEC_BCO_CON_ASSUR_PROS_CON
| 17.4 |  | Andrew Austerberry | Assurance Configuration |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Configuration | Yes | No | Assurance Data End | TEC_BCO_CON_ASSUR_PROS_CON
| 17.4.1 |  |  | Users | 12 | 5 |  | 0 |  |  |  | 0 | No | Configuration | No | Yes |  | TEC_BCO_CON_ASSUR_PROS_CON
| 17.4.2 |  |  | Roles | 12 | 5 |  | 0 |  |  |  | 0 | No | Configuration | No | Yes |  | TEC_BCO_CON_ASSUR_PROS_CON
| 17.4.3 |  |  | Assurance Playback & Admin Session | 21 | 1 | Implementation/Customer | 0 |  | 1 |  | 0 | No | Configuration | No | No |  | TEC_BCO_CON_ASSUR_PROS_CON
| 17.5 |  | Andrew Austerberry | Assurance Training |  |  | Product Enablement | 3h 45m | 100 |  |  | 0.5 | Yes | Training | Yes | No |  | TEC_BCO_CON_ASSUR_PROS_CON
| 17.5.1 |  | Andrew Austerberry | Assurance End User Training | 22 | 1 | Product Enablement/Customer | 0 |  | 0.5 |  | 0 | No | Training | No | No |  | TEC_BCO_CON_ASSUR_PROS_CON
| 17.6 |  |  | Assurance Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | TEC_BCO_CON_ASSUR_PROS_CON
| 17.6.1 |  | Andrew Austerberry | Assuarance UAT | 23 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | UAT | No | No | Assurance UAT Start | TEC_BCO_CON_ASSUR_PROS_CON
| 17.6.2 |  | Andrew Austerberry | Assurance Sign Off | 28 | 1 | Customer/Project Manager | 0 |  | 0.5 |  | 0 | No | Sign Off | Yes | No | Assurance WP End | TEC_BCO_CON_ASSUR_PROS_CON
| 17.6.3 |  | Andrew Austerberry | Assurance Go Live | 29 | 1 | Customer/Implementation | 0 |  |  |  | 0 | No | Go Live | No | No | Assurance Go Live | TEC_BCO_CON_ASSUR_PROS_CON
| 17.6.4 |  | Andrew Austerberry | Assurance Hyper Care | 29 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Hyper Care | No | No |  | TEC_BCO_CON_ASSUR_PROS_CON
| 17.6.5 |  | Est | Assurance Hand Over to Support | 34 | 1 | Implementation/Support | 0 |  |  |  | 0 | No | Support | No | No |  | TEC_BCO_CON_ASSUR_PROS_CON
| 18 |  | Andrew Austerberry | Fire Risk Assessment |  | 23 |  | 22.5 |  | 3 |  | 3 | [5 empty] | TEC_BCO_CON_SURFI_PROS_CON
| 18.1 |  |  | Work Package Management (FRA) |  |  | Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_SURFI_PROS_CON
| 18.1.1 |  |  | Fire Risk Assessment WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 |  |  | 3 | 0 | No | Work Package Management | No | Yes |  | TEC_BCO_CON_SURFI_PROS_CON
| 18.1.2 |  |  | Fire Risk Assessment Specification Agreed | 1 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_SURFI_PROS_CON
| 18.1.3 |  |  | Fire Risk Assessment Chat | 1 | 23 | Customer/Implementation/Project Manager | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_SURFI_PROS_CON
| 18.2 |  |  | Fire Risk Assessment Consultancy |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Consultancy | Yes | No |  | TEC_BCO_CON_SURFI_PROS_CON
| 18.2.1 |  | Andrew Austerberry | Fire Risk Assessment Overview Session | 1 | 1 | Customer/Implementation | 0 |  | 0.5 |  | 0 | No | Consultancy | No | No | FRA WP Start | TEC_BCO_CON_SURFI_PROS_CON
| 18.3 |  | Andrew Austerberry | Fire Risk Assessment Data Management |  |  | Implementation | 7h 30m | 100 |  |  | 1 | Yes | Data Management | Yes | No |  | TEC_BCO_CON_SURFI_PROS_CON
| 18.3.1 |  | Andrew Austerberry | Collate Fire Risk Assessment Data | 2 | 10 | Customer | 0 |  |  |  | 0 | 0 | Customer | No | No | FRA Data Start | TEC_BCO_CON_SURFI_PROS_CON
| 18.3.2 |  | Andrew Austerberry | Fire Risk Assessment Data Validation & Load | 12 | 2 | Data Management | 0 |  | 1 |  | 0 | 0 | Data Management | No | No | FRA Data End | TEC_BCO_CON_SURFI_PROS_CON
| 18.4 |  | Andrew Austerberry | Fire Risk Assessment Configuration | 11 | 5 | Implementation | 3h 45m | 100 | 0.5 |  | 0.5 | Yes | Configuration | Yes | No |  | TEC_BCO_CON_SURFI_PROS_CON
| 18.5 |  | Andrew Austerberry | Fire Risk Assessment Training |  |  | Product Enablement | 3h 45m | 100 |  |  | 0.5 | Yes | Training | Yes | No |  | TEC_BCO_CON_SURFI_PROS_CON
| 18.5.1 |  | Andrew Austerberry | Fire Risk Assessment Training Session 1 | 16 | 1 | Product Enablement/Customer | 0 |  | 0.5 |  | 0 | No | Training | No | No |  | TEC_BCO_CON_SURFI_PROS_CON
| 18.6 |  |  | Fire Risk Assessment Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | TEC_BCO_CON_SURFI_PROS_CON
| 18.6.1 |  | Andrew Austerberry | Fire Risk Assessment UAT | 17 | 5 | Customer/OnBoarding | 0 |  |  |  | 0 | No | UAT | No | No | FRA UAT Start | TEC_BCO_CON_SURFI_PROS_CON
| 18.6.2 |  | Andrew Austerberry | Fire Risk Assessment Sign Off | 22 | 1 | Customer/Project Manager | 0 |  | 0.5 |  | 0 | No | Sign Off | Yes | No | FRA WP End | TEC_BCO_CON_SURFI_PROS_CON
| 18.6.3 |  | Andrew Austerberry | Fire Risk Assessment Go Live | 23 | 1 | Customer/OnBoarding | 0 |  |  |  | 0 | No | Go Live | No | No | FRA Go Live | TEC_BCO_CON_SURFI_PROS_CON
| 18.6.4 |  | Andrew Austerberry | Fire Risk Assessment Hyper Care | 23 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Hyper Care | No | No |  | TEC_BCO_CON_SURFI_PROS_CON
| 18.6.5 |  | Est | Fire Risk Assessment Hand Over to Support | 28 | 1 | Implementation/Support | 0 |  |  |  | 0 | No | Support | No | No |  | TEC_BCO_CON_SURFI_PROS_CON
| 19 |  | Andrew Austerberry | Water Monitoring |  | 24 |  | 37.5 |  | 5 |  | 5 | [5 empty] | TEC_BCO_CON_SURWM_PROS_CON
| 19.1 |  |  | Work Package Management (WM) |  |  | Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_SURWM_PROS_CON
| 19.1.1 |  |  | Water Monitoring WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 |  |  | 5 | 0 | No | Work Package Management | No | Yes |  | TEC_BCO_CON_SURWM_PROS_CON
| 19.1.2 |  |  | Water Monitoring Specification Agreed | 1 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_SURWM_PROS_CON
| 19.1.3 |  |  | Water Monitoring Chat | 1 | 24 | Customer/Implementation/Project Manager | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BCO_CON_SURFI_PROS_CON
| 19.2 |  |  | Water Monitoring Consultancy |  |  | Implementation | 7h 30m | 100 |  |  | 1 | Yes | Consultancy | Yes | No |  | TEC_BCO_CON_SURWM_PROS_CON
| 19.2.1 |  | Andrew Austerberry | Water Monitoring Overview Session | 1 | 1 | Customer/Implementation | 0 |  | 1 |  | 0 | No | Consultancy | No | No | Water Monitor WP Start | TEC_BCO_CON_SURWM_PROS_CON
| 19.3 |  | Andrew Austerberry | Water Monitoring Data Management |  |  | Implementation | 15h | 100 |  |  | 2 | Yes | Data Management | Yes | No |  | TEC_BCO_CON_SURWM_PROS_CON
| 19.3.1 |  | Andrew Austerberry | Collate Water Mintoring Data | 1 | 10 | Customer | [5 empty] | No | Customer | No | No | Water Monitor Data Start | TEC_BCO_CON_SURWM_PROS_CON
| 19.3.2 |  | Andrew Austerberry | Water Mintoring Data Validation & Load | 11 | 1 | Data Management |  |  | 2 |  |  | No | Data Management | No | No | Water Monitor Data End | TEC_BCO_CON_SURWM_PROS_CON
| 19.4 |  | Andrew Austerberry | Water Monitoring Configuration | 12 | 5 | Implementation | 7h 30m | 100 | 1 |  | 1 | Yes | Configuration | Yes | No |  | TEC_BCO_CON_SURWM_PROS_CON
| 19.5 |  | Andrew Austerberry | Water Monitoring Training |  |  | Product Enablement | 3h 45m | 100 |  |  | 0.5 | Yes | Training | Yes | No |  | TEC_BCO_CON_SURWM_PROS_CON
| 19.5.1 |  | Andrew Austerberry | Water Monitoring Train the Trainer | 18 | 1 | Product Enablement/Customer |  |  | 0.5 |  |  | No | Training | No | No |  | TEC_BCO_CON_SURWM_PROS_CON
| 19.6 |  |  | Water Monitoring Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | TEC_BCO_CON_SURWM_PROS_CON
| 19.6.1 |  | Andrew Austerberry | Water Monitoring UAT | 19 | 5 | Customer/OnBoarding | 0 |  |  |  | 0 | No | UAT | No | No | Water Monitor UAT Start | TEC_BCO_CON_SURWM_PROS_CON
| 19.6.2 |  | Andrew Austerberry | Water Monitoring Sign Off | 24 | 1 | Customer/Project Manager | 0 |  | 0.5 |  | 0 | No | Sign Off | Yes | No | Water Monitor WP End | TEC_BCO_CON_SURWM_PROS_CON
| 19.6.3 |  | Andrew Austerberry | Water Monitoring Go Live | 25 | 1 | Customer/OnBoarding | 0 |  |  |  | 0 | No | Go Live | No | No | Water Monitor Go Live | TEC_BCO_CON_SURWM_PROS_CON
| 19.6.4 |  | Andrew Austerberry | Water Monitoring Hyper Care | 25 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Hyper Care | No | No |  | TEC_BCO_CON_SURWM_PROS_CON
| 19.6.5 |  | Est | Water Monitoring Hand Over to Support | 53 | 1 | Implementation/Support | 0 |  |  |  | 0 | No | Support | No | No |  | TEC_BCO_CON_SURWM_PROS_CON
| 20 |  | Andrew Austerberry | Key Manager |  | 22 |  | 26.25 |  | 3.5 |  | 3.5 | [5 empty] | TEC_BAS_CON_KEYM_PROS_CON
| 20.1 |  |  | Work Package Management (KM) |  |  | Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BAS_CON_KEYM_PROS_CON
| 20.1.1 |  |  | Key Manager WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 |  |  | 3.5 | 0 | No | Work Package Management | No | Yes |  | TEC_BAS_CON_KEYM_PROS_CON
| 20.1.2 |  |  | Key Manager Specification Agreed | 1 | 7 | Customer/Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BAS_CON_KEYM_PROS_CON
| 20.1.3 |  |  | Key Manager Chat | 1 | 22 | Customer/Implementation/Project Manager | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BAS_CON_KEYM_PROS_CON
| 20.2 |  |  | Key Manager Consultancy |  |  | Implementation | 7h 30m | 100 |  |  | 1 | Yes | Consultancy | Yes | No |  | TEC_BAS_CON_KEYM_PROS_CON
| 17.2.1 |  | Andrew Austerberry | Key Manager Overview Session | 1 | 1 | Customer/Implementation | 0 |  | 1 |  | 0 | No | Consultancy | No | No | Key Manager WP Start | TEC_BAS_CON_KEYM_PROS_CON
| 20.3 |  | Andrew Austerberry | Key Manager Data Management |  |  | Implementation | 7h 30 m | 100 |  |  | 1 | Yes | Data Management | Yes | No |  | TEC_BAS_CON_KEYM_PROS_CON
| 20.3.1 |  | Andrew Austerberry | Collate Key Manager Data | 2 | 10 | Customer | 0 |  |  |  | 0 | 0 | Customer | No | No | Key Manager Data Start | TEC_BAS_CON_KEYM_PROS_CON
| 20.3.2 |  | Andrew Austerberry | Key Manager Data Validation & Load | 12 | 2 | Data Management | 0 |  | 1 |  | 0 | 0 | Data Management | No | No | Key ManageData End | TEC_BAS_CON_KEYM_PROS_CON
| 20.4 |  | Andrew Austerberry | Key Manager Configuration | 13 | 2 | Implementation | 3h 45m | 100 | 0.5 |  | 0.5 | Yes | Configuration | Yes | No |  | TEC_BAS_CON_KEYM_PROS_CON
| 20.5 |  | Andrew Austerberry | Key Manager Training |  |  | Product Enablement | 3h 45m | 100 |  |  | 0.5 | Yes | Training | Yes | No |  | TEC_BAS_CON_KEYM_PROS_CON
| 20.5.1 |  | Andrew Austerberry | Key Manager Training Session 1 | 15 | 1 | Product Enablement/Customer | 0 |  | 0.5 |  | 0 | No | Training | No | No |  | TEC_BAS_CON_KEYM_PROS_CON
| 20.6 |  |  | Key Manager Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | TEC_BAS_CON_KEYM_PROS_CON
| 20.6.1 |  | Andrew Austerberry | Key Manager UAT | 17 | 5 | Customer/OnBoarding | 0 |  |  |  | 0 | No | UAT | No | No | Key Manager UAT Start | TEC_BAS_CON_KEYM_PROS_CON
| 20.6.2 |  | Andrew Austerberry | Key Manager Sign Off | 22 | 1 | Customer/Project Manager | 0 |  | 0.5 |  | 0 | No | Sign Off | Yes | No | Key Manager WP End | TEC_BAS_CON_KEYM_PROS_CON
| 20.6.3 |  | Andrew Austerberry | Key Manager Go Live | 23 | 1 | Customer/OnBoarding | 0 |  |  |  | 0 | No | Go Live | No | No | Key Manager Go Live | TEC_BAS_CON_KEYM_PROS_CON
| 20.6.4 |  | Andrew Austerberry | Key Manager Hyper Care | 23 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Hyper Care | No | No |  | TEC_BAS_CON_KEYM_PROS_CON
| 20.6.5 |  | Est | Key Manager Hand Over to Support | 53 | 1 | Implementation/Support | 0 |  |  |  | 0 | No | Support | No | No |  | TEC_BAS_CON_KEYM_PROS_CON
| 21 |  | Andrew Austerberry | CAFM Stock |  | 27 |  | 30 |  | 4 |  | 4 | [5 empty] | TEC_BMA_CON_CAFMST_PROS_CON
| 21.1 |  |  | Work Package Management (CAFM Stock) |  |  | Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 21.1.1 |  |  | CAFM Stock WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 |  |  | 4 | 0 | No | Work Package Management | No | Yes |  | TEC_BMA_CON_CAFMST_PROS_CON
| 21.1.2 |  |  | CAFM Stock Specification Agreed | 1 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 21.1.3 |  |  | CAFM Stock Chat | 1 | 27 | Customer/Implementation/Project Manager | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 21.2 |  |  | CAFM Stock Consultancy |  |  | Implementation | 11h 15m |  |  |  | 1.5 | Yes | Consultancy | Yes | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 21.2.1 |  | Andrew Austerberry | CAFM Stock Overview Session | 1 | 1 | Customer/Implementation | 0 |  | 1.5 |  | 0 | No | Consultancy | No | No | CAFM Stock WP Start | TEC_BMA_CON_CAFMST_PROS_CON
| 21.3 |  | Andrew Austerberry | CAFM Stock Data Management |  |  | Implementation | 7h 30 m |  |  |  | 1 | Yes | Data Management | Yes | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 21.3.1 |  | Andrew Austerberry | Collate CAFM Stock Data | 2 | 10 | Customer | 0 |  |  |  | 0 | 0 | Customer | No | No | CAFM Stock Data Start | TEC_BMA_CON_CAFMST_PROS_CON
| 21.3.2 |  | Andrew Austerberry | CAFM Stock Data Validation & Load | 12 | 2 | Data Management | 0 |  | 1 |  | 0 | 0 | Data Management | No | No | CAFM Stock Data End | TEC_BMA_CON_CAFMST_PROS_CON
| 21.4 |  | Andrew Austerberry | CAFM Stock Configuration | 11 | 5 | Implementation | 3h 45m |  | 0.5 |  | 0.5 | Yes | Configuration | Yes | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 21.5 |  | Andrew Austerberry | CAFM Stock Training |  |  | Product Enablement | 3h 45m |  |  |  | 0.5 | Yes | Training | Yes | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 21.5.1 |  | Andrew Austerberry | CAFM Stock Training Session 1 | 20 | 1 | Product Enablement/Customer | 0 |  | 0.5 |  | 0 | No | Training | No | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 21.6 |  |  | CAFM Stock Close |  |  | Implementation | 3h 45m |  |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 21.6.1 |  | Andrew Austerberry | CAFM Stock UAT | 21 | 5 | Customer/OnBoarding | 0 |  |  |  | 0 | No | UAT | No | No | CAFM Stock UAT Start | TEC_BMA_CON_CAFMST_PROS_CON
| 21.6.2 |  | Andrew Austerberry | CAFM Stock Sign Off | 26 | 1 | Customer/Project Manager | 0 |  | 0.5 |  | 0 | No | Sign Off | Yes | No | CAFM Stock WP End | TEC_BMA_CON_CAFMST_PROS_CON
| 21.6.3 |  | Andrew Austerberry | CAFM Stock Go Live | 27 | 1 | Customer/OnBoarding | 0 |  |  |  | 0 | No | Go Live | No | No | CAFM Stock Go Live | TEC_BMA_CON_CAFMST_PROS_CON
| 21.6.4 |  | Andrew Austerberry | CAFM Stock Hyper Care | 27 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Hyper Care | No | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 21.6.5 |  | Est | CAFM Stock Hand Over to Support | 32 | 1 | Implementation/Support | 0 |  |  |  | 0 | No | Support | No | No |  | TEC_BMA_CON_CAFMST_PROS_CON
201 | 22 |  | Andrew Austerberry | Condition Surveys |  | 57 |  | 60 |  | 8 |  | 8 | 1
201 | 22.1 |  |  | Work Package Management (Con Surv) |  |  | Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | Yes |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.1.1 |  |  | Condition Surveys WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 |  |  | 8 |  | No | Work Package Management |  | Yes |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.1.2 |  |  | Condition Surveys Specification Agreed | 1 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.1.3 |  |  | Condition Surveys Chat | 1 | 57 | Customer/Implementation/Project Manager | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.2 |  |  | Condition Surveys Consultancy |  |  | Implementation | 18h 45m | 100 |  |  | 2.5 | Yes | Consultancy | Yes | No |  | TEC_BMA_CON_CAFMST_PROS_CON
202 | 22.2.1 |  | Andrew Austerberry | Condition Surveys Overview Session | 1 | 1 | Customer/Implementation | 0 | 0 | 2.5 |  | 0 | No | Consultancy | No | No | Condition Surveys WP Start | TEC_BMA_CON_CAFMST_PROS_CON
| 22.3 |  | Andrew Austerberry | Condition Surveys Data Management |  |  | Implementation | 30h | 0 |  |  | 4 | Yes | Data Management | Yes | No |  | TEC_BMA_CON_CAFMST_PROS_CON
203 | 22.3.1 |  |  | Element List |  |  |  | 0 | 0 | 1 |  | 0 |  |  |  | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.3.1.1 |  | Andrew Austerberry | Collate element list | 1 | 5 | Customer | 0 | 0 |  |  | 0 | 0 | 1 | 0 | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.3.1.2 |  | Andrew Austerberry | Review Import element list | 6 | 2 | Data Management | 0 | 0 |  |  | 0 | 0 | 0 | 0 | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.3.1.3 |  | Andrew Austerberry | Client Review imported element list | 8 | 2 | Data Management | 0 | 0 |  |  | 0 | 0 | 0 | 0 | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.3.1.4 |  | Andrew Austerberry | Sign off element list | 10 | 1 | Customer/Implementation | 0 | 0 |  |  | 0 | 0 | 0 | 1 | No |  | TEC_BMA_CON_CAFMST_PROS_CON
208 | 22.3.2 |  | Andrew Austerberry | Sample |  |  |  | 0 | 0 | 1 |  | 0 | 1 | 0 | 0 | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.3.2.1 |  | Andrew Austerberry | Collate sample condition survey data | 10 | 10 | Customer | 0 | 0 |  |  | 0 | 0 | 1 | 0 | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.3.2.2 |  | Andrew Austerberry | Review import condition survey data | 20 | 2 | Data Management | 0 | 0 |  |  | 0 | 0 | 0 | 0 | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.3.2.3 |  | Andrew Austerberry | Review imported condition survey data and feedback | 22 | 5 | Data Management | 0 | 0 |  |  | 0 | 0 | 0 | 0 | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.3.2.4 |  | Andrew Austerberry | Client Sign off condition survey data | 27 | 1 | Customer | 0 | 0 |  |  | 0 | 0 | 0 | 1 | No |  | TEC_BMA_CON_CAFMST_PROS_CON
213 | 22.3.3 |  | Andrew Austerberry | Full |  |  |  | 0 | 0 | 2 |  | 0 | 1 | 0 | 0 | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.3.3.1 |  | Andrew Austerberry | Provide full condition survey data | 28 | 10 | Customer | 0 | 0 |  |  | 0 | 0 | 1 | 0 | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.3.3.2 |  | Andrew Austerberry | ReviewImport full condition survey data | 39 | 2 | Data Management | 0 | 0 |  |  | 0 | 0 | 0 | 0 | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.3.3.3 |  | Andrew Austerberry | Review full condition survey data and feedback | 41 | 1 | Data Management | 0 | 0 |  |  | 0 | 0 | 0 | 0 | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.4 |  | Andrew Austerberry | Condition Surveys Configuration | 42 | 5 | Implementation | 3h 45m | 100 | 0.5 |  | 0.5 | Yes | Configuration | Yes | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.5 |  | Andrew Austerberry | Condition Surveys Training |  |  | Product Enablement | 3h 45m | 100 |  |  | 0.5 | Yes | Training | Yes | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.5.1 |  | Andrew Austerberry | Condition Surveys Training Session 1 | 50 | 1 | Product Enablement/Customer | 0 |  | 0.5 |  | 0 | No | Training | No | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.6 |  |  | Condition Surveys Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | TEC_BMA_CON_CAFMST_PROS_CON
216 | 22.6.1 |  | Andrew Austerberry | Condition Surveys UAT | 52 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | UAT | 0 | No | Condition Surveys UAT Start | TEC_BMA_CON_CAFMST_PROS_CON
217 | 22.6.2 |  | Andrew Austerberry | Condition Surveys Sign Off | 57 | 1 | Customer/Project Manager | 0 |  | 0.5 |  | 0 | No | Sign Off | Yes | No | Condition Surveys WP End | TEC_BMA_CON_CAFMST_PROS_CON
| 22.6.3 |  | Andrew Austerberry | Condition Surveys Go Live | 57 | 1 | Customer/Implementation | 0 |  |  |  | 0 | No | Go Live | 0 | No | Condition Surveys Go Live | TEC_BMA_CON_CAFMST_PROS_CON
| 22.6.4 |  | Andrew Austerberry | Condition Surveys Hyper Care | 57 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Hyper Care | 0 | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 22.6.5 |  | Est | Condition Surveys Hand Over to Support | 62 | 1 | Implementation/Support | 0 |  |  |  | 0 | No | Support | No | No |  | TEC_BMA_CON_CAFMST_PROS_CON
| 23 |  | Andrew Austerberry | Facet Surveys |  | 43 |  | 22.5 |  | 3 |  | 3
| 23.1 |  |  | Work Package Management (Fac Surv) |  |  | Implementation | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.1.1 |  |  | Facet Surveys WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 | 0 |  | 3 | 0 | No | Work Package Management | No | Yes |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.1.2 |  |  | Facet Surveys Specification Agreed | 1 | 5 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.1.3 |  |  | Condition Surveys Chat | 1 | 43 | Customer/Implementation/Project Manager | 0 | 0 |  |  | 0 | No | Work Package Management | No | No |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.2 |  |  | Condition Surveys Consultancy |  |  | Implementation | 3h 45m | 100 | 0.5 |  | 0.5 | Yes | Consultancy | Yes | No |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.2.1 |  | Andrew Austerberry | Condition Surveys Overview Session | 1 | 1 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Consultancy | No | No | Facet Surveys WP Start | TEC_BAS_CON_SURFS_PROS_CON
| 23.3 |  | Andrew Austerberry | Facet Surveys Data Management |  |  | Implementation | 7h 30 m | 100 |  |  | 1 | No | Data Management | Yes | No |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.3.1 |  | Andrew Austerberry | Collate Facet Surveys Data | 2 | 10 | Customer | 0 |  |  |  | 0 | No | Customer | No | No | Facet Survey Data Start | TEC_BAS_CON_SURFS_PROS_CON
| 23.3.2 |  | Andrew Austerberry | Facet Surveys Data Validation & Load |  |  | Data Management | 0 | 0 | 0.5 |  | 0 | No | Data Management | No | No | Facet Survey Data End | TEC_BAS_CON_SURFS_PROS_CON
| 23.3.2.1 |  | Andrew Austerberry | Test Load | 14 | 2 | Data Management | 0 | 0 |  |  | 0 | No | Data Management | No | No |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.3.3 |  | Andrew Austerberry | Facet Surveys Playback Session | 18 | 1 | Customer/Implementation | 0 | 0 |  |  | 0 | No | Data Management | No | No |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.3.4 |  |  | Full Load | 24 | 2 | Data Management | 0 | 0 | 0.5 |  | 0 | No | Data Management | No | No |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.3.4.1 |  |  | Physical Condition |  |  |  | 0 | 0 |  |  | 0 | No | Data Management | No | Yes |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.3.4.2 |  | Andrew Austerberry | Functional Suitability |  |  |  | 0 | 0 |  |  | 0 | No | Data Management | No | Yes |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.3.4.3 |  | Andrew Austerberry | Space Utilisation |  |  |  | 0 | 0 |  |  | 0 | No | Data Management | No | Yes |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.3.4.4 |  | Andrew Austerberry | Quality |  |  |  | 0 | 0 |  |  | 0 | No | Data Management | No | Yes |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.3.4.5 |  | Andrew Austerberry | Statutory Requirements |  |  |  | 0 | 0 |  |  | 0 | No | Data Management | No | Yes |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.3.4.6 |  | Andrew Austerberry | Environmental Management |  |  |  | 0 | 0 |  |  | 0 | No | Data Management | No | Yes |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.4 |  | Andrew Austerberry | Facet Surveys Configuration | 26 | 5 | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Configuration | Yes | No |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.4.1.1 |  |  | Physical Condition |  |  |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.4.1.2 |  | Andrew Austerberry | Functional Suitability |  |  |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.4.1.3 |  | Andrew Austerberry | Space Utilisation |  |  |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.4.1.4 |  | Andrew Austerberry | Quality |  |  |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.4.1.5 |  | Andrew Austerberry | Statutory Requirements |  |  |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.4.1.6 |  | Andrew Austerberry | Environmental Management |  |  |  | 0 | 0 |  |  | 0 | No | Configuration | No | Yes |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.4.2 |  |  | Facet Survey Playback |  |  |  | 0 | 0 | 0.5
| 23.5 |  | Andrew Austerberry | Facet Surveys Training |  |  | Product Enablement | 3h 45m | 100 |  |  | 0.5 | Yes | Training | Yes | No |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.5.1 |  | Andrew Austerberry | Facet Surveys Training Session 1 | 31 | 1 | Product Enablement/Customer | 0 |  | 0.5 |  | 0 | No | Training | No | No |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.6 |  |  | Facet Surveys Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.6.1 |  | Andrew Austerberry | Facet Surveys UAT | 32 | 5 | Customer/OnBoarding | 0 |  |  |  | 0 | No | UAT | No | No | Facet Surveys UAT Start | TEC_BAS_CON_SURFS_PROS_CON
| 23.6.2 |  | Andrew Austerberry | Facet Surveys Sign Off | 37 | 1 | Customer/Project Manager | 0 |  | 0.5 |  | 0 | No | Sign Off | Yes | No | Facet Surveys WP End | TEC_BAS_CON_SURFS_PROS_CON
| 23.6.3 |  | Andrew Austerberry | Facet Surveys Go Live | 38 | 1 | Customer/OnBoarding | 0 |  |  |  | 0 | No | Go Live | No | No | Facet Surveys Go Live | TEC_BAS_CON_SURFS_PROS_CON
| 23.6.4 |  | Andrew Austerberry | Facet Surveys Hyper Care | 38 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Hyper Care | No | No |  | TEC_BAS_CON_SURFS_PROS_CON
| 23.6.5 |  | Est | Facet Surveys Hand Over to Support | 43 | 1 | Implementation/Support | 0 |  |  |  | 0 | No | Support | No | No |  | TEC_BAS_CON_SURFS_PROS_CON
| 24 |  | Andrew Austerberry | Mobile Surveys |  | 27 |  | 26.25 |  | 3.5 |  | 3.5
| 24.1 |  |  | Work Package Management (Mob Surveys) |  |  | Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | ?
| 24.1.1 |  |  | Mobile Surveys WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 |  |  | 3.5 | 0 | No | Work Package Management | No | Yes |  | ?
| 24.1.2 |  |  | Mobile Surveys Specification Agreed | 1 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | ?
| 24.1.3 |  |  | Mobile Surveys Chat | 1 | 27 | Customer/Implementation/Project Manager | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | ?
| 24.2 |  |  | Mobile Surveys Consultancy |  |  | Implementation | 7h 30m | 100 |  |  | 1 | Yes | Consultancy | Yes | No |  | ?
| 24.2.1 |  | Andrew Austerberry | Mobile Surveys Overview Session | 1 | 1 | Customer/Implementation | 0 |  | 1 |  | 0 | No | Consultancy | No | No | Mobile Surveys WP Start | ?
| 24.3 |  | Andrew Austerberry | Mobile Surveys Data Management |  |  | Implementation | 7h 30 m | 100 |  |  | 1 | Yes | Data Management | Yes | No |  | ?
| 24.3.1 |  | Andrew Austerberry | Collate Mobile Surveys Data | 2 | 10 | Customer | 0 |  |  |  | 0 | 0 | Customer | No | No | Mobile Survey Data Start | ?
| 24.3.2 |  | Andrew Austerberry | Mobile Surveys Data Validation & Load | 12 | 2 | Data Management | 0 |  | 1 |  | 0 | 0 | Data Management | No | No | Mobile Survey Data End | ?
| 24.4 |  | Andrew Austerberry | Mobile Surveys Configuration | 11 | 5 | Implementation | 3h 45m | 100 | 0.5 |  | 0.5 | Yes | Configuration | Yes | No |  | ?
| 24.5 |  | Andrew Austerberry | Mobile Surveys Training |  |  | Product Enablement | 3h 45m | 100 |  |  | 0.5 | Yes | Training | Yes | No |  | ?
| 24.5.1 |  | Andrew Austerberry | Mobile Surveys Training Session 1 | 20 | 1 | Product Enablement/Customer | 0 |  | 0.5 |  | 0 | No | Training | No | No |  | ?
| 24.6 |  |  | Mobile Surveys Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | ?
| 24.6.1 |  | Andrew Austerberry | Mobile Surveys UAT | 21 | 5 | Customer/OnBoarding | 0 |  |  |  | 0 | No | UAT | No | No | Mobile Surveys UAT Start | ?
| 24.6.2 |  | Andrew Austerberry | Mobile Surveys Sign Off | 26 | 1 | Customer/Project Manager | 0 |  | 0.5 |  | 0 | No | Sign Off | Yes | No | Mobile Surveys WP End | ?
| 24.6.3 |  | Andrew Austerberry | Mobile Surveys Go Live | 27 | 1 | Customer/OnBoarding | 0 |  |  |  | 0 | No | Go Live | No | No | Mobile Surveys Go Live | ?
| 24.6.4 |  | Andrew Austerberry | Mobile Surveys Hyper Care | 27 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Hyper Care | No | No |  | ?
| 24.6.5 |  | Est | Mobile Surveys Hand Over to Support | 32 | 1 | Implementation/Support | 0 |  |  |  | 0 | No | Support | No | No |  | ?
| 25 |  | Andrew Austerberry | Asset Insights |  | 27 |  | 26.25 |  | 3.5 |  | 3.5 | [5 empty] | ?
| 25.1 |  |  | Work Package Management (Asset Ins) |  |  | Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | ?
| 25.1.1 |  |  | Asset Insights WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 |  |  | 3.5 | 0 | No | Work Package Management | No | Yes |  | ?
| 25.1.2 |  |  | Asset Insights Specification Agreed | 1 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | ?
| 25.1.3 |  |  | Asset Insights Chat | 1 | 27 | Customer/Implementation/Project Manager | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | ?
| 25.2 |  |  | Asset Insights Consultancy |  |  | Implementation | 7h 30m | 100 |  |  | 1 | Yes | Consultancy | Yes | No |  | ?
| 25.2.1 |  | Andrew Austerberry | Asset Insights Overview Session | 1 | 1 | Customer/Implementation | 0 |  | 1 |  | 0 | No | Consultancy | No | No | Asset Insights WP Start | ?
| 25.3 |  | Andrew Austerberry | Asset Insights Data Management |  |  | Implementation | 7h 30 m | 100 |  |  | 1 | Yes | Data Management | Yes | No |  | ?
| 25.3.1 |  | Andrew Austerberry | Collate Asset Insights Data | 2 | 10 | Customer | 0 |  |  |  | 0 | 0 | Customer | No | No | Mobile Survey Data Start | ?
| 25.3.2 |  | Andrew Austerberry | Asset Insights Data Validation & Load | 12 | 2 | Data Management | 0 |  | 1 |  | 0 | 0 | Data Management | No | No | Mobile Survey Data End | ?
| 25.4 |  | Andrew Austerberry | Asset Insights Configuration | 11 | 5 | Implementation | 3h 45m | 100 | 0.5 |  | 0.5 | Yes | Configuration | Yes | No |  | ?
| 25.5 |  | Andrew Austerberry | Asset Insights Training |  |  | Product Enablement | 3h 45m | 100 |  |  | 0.5 | Yes | Training | Yes | No |  | ?
| 25.5.1 |  | Andrew Austerberry | Asset Insights Training Session 1 | 20 | 1 | Product Enablement/Customer | 0 |  | 0.5 |  | 0 | No | Training | No | No |  | ?
| 25.6 |  |  | Asset Insights Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | ?
| 25.6.1 |  | Andrew Austerberry | Asset Insights UAT | 21 | 5 | Customer/OnBoarding | 0 |  |  |  | 0 | No | UAT | No | No | Asset Insights UAT Start | ?
| 25.6.2 |  | Andrew Austerberry | Asset Insights Sign Off | 26 | 1 | Customer/Project Manager | 0 |  | 0.5 |  | 0 | No | Sign Off | Yes | No | Asset Insights WP End | ?
| 25.6.3 |  | Andrew Austerberry | Asset Insights Go Live | 27 | 1 | Customer/OnBoarding | 0 |  |  |  | 0 | No | Go Live | No | No | Asset Insights Go Live | ?
| 25.6.4 |  | Andrew Austerberry | Asset Insights Hyper Care | 27 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Hyper Care | No | No |  | ?
| 25.6.5 |  | Est | Asset Insights Hand Over to Support | 32 | 1 | Implementation/Support | 0 |  |  |  | 0 | No | Support | No | No |  | ?
| 26 |  | Andrew Austerberry | Service Master |  | 27 |  | 26.25 |  | 3.5 |  | 3.5 | [5 empty] | ?
| 26.1 |  |  | Work Package Management (Serv Mast) |  |  | Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | ?
| 26.1.1 |  |  | Service Master WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 |  |  | 3.5 | 0 | No | Work Package Management | No | Yes |  | ?
| 26.1.2 |  |  | Service Master Specification Agreed | 1 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | ?
| 26.1.3 |  |  | Service Master Chat | 1 | 27 | Customer/Implementation/Project Manager | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | ?
| 26.2 |  |  | Service Master Consultancy |  |  | Implementation | 7h 30m | 100 |  |  | 1 | Yes | Consultancy | Yes | No |  | ?
| 26.2.1 |  | Andrew Austerberry | Service Master Overview Session | 1 | 1 | Customer/Implementation | 0 |  | 1 |  | 0 | No | Consultancy | No | No | Service Master WP Start | ?
| 26.3 |  | Andrew Austerberry | Service Master Data Management |  |  | Implementation | 7h 30 m | 100 |  |  | 1 | Yes | Data Management | Yes | No |  | ?
| 26.3.1 |  | Andrew Austerberry | Collate Service Master Data | 2 | 10 | Customer | 0 |  |  |  | 0 | 0 | Customer | No | No | Mobile Survey Data Start | ?
| 26.3.2 |  | Andrew Austerberry | Service Master Data Validation & Load | 12 | 2 | Data Management | 0 |  | 1 |  | 0 | 0 | Data Management | No | No | Mobile Survey Data End | ?
| 26.4 |  | Andrew Austerberry | Service Master Configuration | 11 | 5 | Implementation | 3h 45m | 100 | 0.5 |  | 0.5 | Yes | Configuration | Yes | No |  | ?
| 26.5 |  | Andrew Austerberry | Service Master Training |  |  | Product Enablement | 3h 45m | 100 |  |  | 0.5 | Yes | Training | Yes | No |  | ?
| 26.5.1 |  | Andrew Austerberry | Service Master Training Session 1 | 20 | 1 | Product Enablement/Customer | 0 |  | 0.5 |  | 0 | No | Training | No | No |  | ?
| 26.6 |  |  | Service Master Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | ?
| 26.6.1 |  | Andrew Austerberry | Service Master UAT | 21 | 5 | Customer/OnBoarding | 0 |  |  |  | 0 | No | UAT | No | No | Service Master UAT Start | ?
| 26.6.2 |  | Andrew Austerberry | Service Master Sign Off | 26 | 1 | Customer/Project Manager | 0 |  | 0.5 |  | 0 | No | Sign Off | Yes | No | Service Master WP End | ?
| 26.6.3 |  | Andrew Austerberry | Service Master Go Live | 27 | 1 | Customer/OnBoarding | 0 |  |  |  | 0 | No | Go Live | No | No | Service Master Go Live | ?
| 26.6.4 |  | Andrew Austerberry | Service Master Hyper Care | 27 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Hyper Care | No | No |  | ?
| 26.6.5 |  | Est | Service Master Hand Over to Support | 32 | 1 | Implementation/Support | 0 |  |  |  | 0 | No | Support | No | No |  | ?
| 27 |  | Andrew Austerberry | Wiggle Desk |  | 27 |  | 26.25 |  | 3.5 |  | 3.5 | [5 empty] | TEC_PSE_WIG_WIGD_PROS_SUP
| 27.1 |  |  | Work Package Management (Wiggle Desk) |  |  | Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_PSE_WIG_WIGD_PROS_SUP
| 27.1.1 |  |  | Wiggle Desk WP Hardbooked and Budget | 1 | 1 | Implementation/Project Manager | 0 |  |  | 3.5 | 0 | No | Work Package Management | No | Yes |  | TEC_PSE_WIG_WIGD_PROS_SUP
| 27.1.2 |  |  | Wiggle Desk Specification Agreed | 1 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_PSE_WIG_WIGD_PROS_SUP
| 27.1.3 |  |  | Wiggle Desk Chat | 1 | 27 | Customer/Implementation/Project Manager | 0 |  |  |  | 0 | No | Work Package Management | No | No |  | TEC_PSE_WIG_WIGD_PROS_SUP
| 27.2 |  |  | Wiggle Desk Consultancy |  |  | Implementation | 7h 30m | 100 |  |  | 1 | Yes | Consultancy | Yes | No |  | TEC_PSE_WIG_WIGD_PROS_SUP
| 27.2.1 |  | Andrew Austerberry | Wiggle Desk Overview Session | 1 | 1 | Customer/Implementation | 0 |  | 1 |  | 0 | No | Consultancy | No | No | Wiggle Desk WP Start | TEC_PSE_WIG_WIGD_PROS_SUP
| 27.3 |  | Andrew Austerberry | Wiggle Desk Data Management |  |  | Implementation | 7h 30 m | 100 |  |  | 1 | Yes | Data Management | Yes | No |  | TEC_PSE_WIG_WIGD_PROS_SUP
| 27.3.1 |  | Andrew Austerberry | Collate Wiggle Desk Data | 2 | 10 | Customer | 0 |  |  |  | 0 | 0 | Customer | No | No | Wiggle Desk Data Start | TEC_PSE_WIG_WIGD_PROS_SUP
| 27.3.2 |  | Andrew Austerberry | Wiggle Desk Data Validation & Load | 12 | 2 | Data Management | 0 |  | 1 |  | 0 | 0 | Data Management | No | No | Wiggle Desk Data End | TEC_PSE_WIG_WIGD_PROS_SUP
| 27.4 |  | Andrew Austerberry | Wiggle Desk Configuration | 11 | 5 | Implementation | 3h 45m | 100 | 0.5 |  | 0.5 | Yes | Configuration | Yes | No |  | TEC_PSE_WIG_WIGD_PROS_SUP
| 27.5 |  | Andrew Austerberry | Wiggle Desk Training |  |  | Product Enablement | 3h 45m | 100 |  |  | 0.5 | Yes | Training | Yes | No |  | TEC_PSE_WIG_WIGD_PROS_SUP
| 27.5.1 |  | Andrew Austerberry | Wiggle Desk Training Session 1 | 20 | 1 | Product Enablement/Customer | 0 |  | 0.5 |  | 0 | No | Training | No | No |  | TEC_PSE_WIG_WIGD_PROS_SUP
| 27.6 |  |  | Wiggle Desk Close |  |  | Implementation | 3h 45m | 100 |  |  | 0.5 | Yes | Work Package Management | Yes | No |  | TEC_PSE_WIG_WIGD_PROS_SUP
| 27.6.1 |  | Andrew Austerberry | Wiggle Desk UAT | 21 | 5 | Customer/OnBoarding | 0 |  |  |  | 0 | No | UAT | No | No | Wiggle Desk UAT Start | TEC_PSE_WIG_WIGD_PROS_SUP
| 27.6.2 |  | Andrew Austerberry | Wiggle Desk Sign Off | 26 | 1 | Customer/Project Manager | 0 |  | 0.5 |  | 0 | No | Sign Off | Yes | No | Wiggle Desk WP End | TEC_PSE_WIG_WIGD_PROS_SUP
| 27.6.3 |  | Andrew Austerberry | Wiggle Desk Go Live | 27 | 1 | Customer/OnBoarding | 0 |  |  |  | 0 | No | Go Live | No | No | Wiggle Desk Go Live | TEC_PSE_WIG_WIGD_PROS_SUP
| 27.6.4 |  | Andrew Austerberry | Wiggle Desk Hyper Care | 27 | 5 | Customer/Implementation | 0 |  |  |  | 0 | No | Hyper Care | No | No |  | TEC_PSE_WIG_WIGD_PROS_SUP
| 27.6.5 |  | Est | Wiggle Desk Hand Over to Support | 32 | 1 | Implementation/Support | 0 |  |  |  | 0 | No | Support | No | No |  | TEC_PSE_WIG_WIGD_PROS_SUP

## PMO WIP
Task ID | RL ID | RL Name | Phase | Level | Type | Item | Start Date | Duration | Assignee | Effort (Hours) | Effort Split | Task Value | Phase Value | Effort Days | Billable | Category | Milestone | Private | Key Event | Dynamic Trigger
1 |  |  | Project Mobilisation | Phase |  | Project Mobilisation
1.1 | 1.1.1 | Project Mobilisation | Project Mobilisation | Task | Description | Assign a Project Team to oversee delivery based on capacity and capabilities |  |  | PMO Lead
1.2 | 1.1.3 | Contract Review | Project Mobilisation | Task | Description | PM review the contract, tender, bid documentation, Statement of Work (SOW) and complete contract specifics document. |  |  | PM
1.3 | 1.1.3 | Contract Review | Project Mobilisation | Task | Description | PL review the contract, tender, bid documentation, and Statement of Work (SOW) to ensure full understanding of scope, deliverables, and commercial terms. |  |  | PL
1.4 | 1.1.4 | Internal Sales Handover | Project Mobilisation | Task | Task | Conduct an Internal Sales Handover to capture all contextual information, client nuances, and non-documented expectations from the sales team. |  |  | PM/PL
2 |  |  | Customer Handover | Phase |  | Customer Handover
2.1 | 1.1.5 | Remote Customer Handover | Customer Handover | Task | Task | Schedule and facilitate a remote Customer Handover Meeting involving the Sales Representative, PM, and PL. |  |  | PM/PL
2.2 | 1.1.6 | SOW Agreed | Customer Handover | Task | Task | Review the SOW in detail to ensure all parties are aligned on scope.
3 |  |  | Professional Services Preparation | Phase |  | Professional Services Preparation
3.1 | 1.1.8 | Professional Services Review | Professional Services Preparation | Task |  | Review all speculative product development items; confirm which are now required and request delivery timeframes.
3.2 | 1.1.8 | Release Projecy Inititaion Pack | Professional Services Preparation | Task | Space | Issue the Project Initiation Pack to the customer, including:
3.2.1 | 1.3.2 |  | Professional Services Preparation | Subtask | Template | - Standardised initiation documents
3.2.2 | 1.3.2 |  | Professional Services Preparation | Subtask | Project Plan | - A recommended project plan with key milestones, dates, and stakeholders
4 |  |  | Design Phase | Phase |  | Design Phase
4.1 | 1.5.1 |  | Design Phase | Task | Task | Book a face-to-face onsite kick-off meeting.
4.2 | 1.5.1 |  | Design Phase | Task | Description | Kick off meeting will cover the following
4.2.1 | 1.5.1 |  | Design Phase | Subtask | Description | - An overview of purchased solution areas.
4.2.2 | 1.5.1 |  | Design Phase | Subtask | Description | - Introduction to Core Data.
4.2.3 | 2.1 | Work Packages Booked | Design Phase | Subtask |  | - Confirm all future meeting dates with the Project Manager.
4.2.4 | 1.6 |  | Design Phase | Subtask |  | - Finalise the end-to-end project plan.
5 |  |  | Delivery Phase | Phase |  | Delivery Phase
5.1 | *.1.1 (WP) | WP Hardbooked and Budget | Delivery Phase | Task | Task | Send calendar invitations for all sessions and deadlines, with cancellation terms included.
5.2 | 2.5.5 |  | Delivery Phase | Task | Automated Form | Send Customer Satisfaction (CSAT) surveys monthly.
5.3 | 2.5.6 |  | Delivery Phase | Task | Automated Form | Send Net Promoter Score (NPS) surveys quarterly.
5.4 | 2.2.1 |  | Delivery Phase | Task | Auto Task / Space | Hold monthly project review meetings with Project Lead, Project Manager and Customer
5.5 | 2.2.1 |  | Delivery Phase | Task | Form Template | During each review:
5.5.1 | 2.2.1 |  | Delivery Phase | Subtask | Form Template | - Compare delivered scope vs. SOW.
5.5.2 | 2.2.1 |  | Delivery Phase | Subtask | Form Template | - Review budget and timeline.
5.5.3 | 2.2.1 |  | Delivery Phase | Subtask | Form Template | - Identify and raise risks/issues.
5.6 |  |  | Delivery Phase | Task | Project Update | Send a status report to the customer after each review meeting.
8 |  |  | Close Out | Phase |  | Close Out
8.1 |  | Not Built yet | Close Out | Task |  | Hold a project close-out meeting with Customer, Professional Services, Support and Customer Success Manager
8.2 |  |  | Close Out | Task |  | Demonstrate how to raise support tickets.
8.3 |  |  | Close Out | Task |  | Customer Success Manager schedules 30, 60, and 90-day check-ins.
8.4 |  |  | Close Out | Task |  | Package and share all project documentation with Customer, Support team and Customer Success Manager
8.5 |  |  | Close Out | Task |  | Invite the customer to a retrospective meeting with Professional Services to gather feedback and lessons learned.
6 |  |  | User Acceptance Testing (UAT) & Training | Phase |  | User Acceptance Testing (UAT) & Training
6.1 | *.5.1 |  | User Acceptance Testing (UAT) & Training | Task | Task and Form | Manage the UAT phase, ensuring all acceptance criteria are tested and signed off formally by the customer.
6.2 | *.4.1 |  | User Acceptance Testing (UAT) & Training | Task | Task and Form | Deliver end-user training sessions, obtaining documented sign-off on completion.
6.3 |  |  | User Acceptance Testing (UAT) & Training | Task | Automated Form | Send a CSAT survey after training.
6.4 |  |  | User Acceptance Testing (UAT) & Training | Task |  | Record and store names of all trained learners in project documentation.
7 |  |  | Go Live | Phase |  | Go Live
7.1 |  |  | Go Live | Task |  | Attend the customer site on go-live day.
7.2 | *.5.4 |  | Go Live | Task | Task | Commence a two-week Hypercare period, during which:
7.2.1 |  |  | Go Live | Subtask | Description | - Only advice and guidance are provided (no new change requests).
7.2.2 |  |  | Go Live | Subtask | Description | - System stability and adoption are monitored.
7.3 | *.5.4.1 | Hyper Care Complete | Go Live | Task | Task and Form | Obtain formal Hypercare Completion Sign-off from the customer