# Concerto Work Package Catalogue

Status: derived knowledge asset

Canonical source: Rocketlane Project Plan Template v2

Source file ID: 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A

Source tab: Rocketlane

Created for: Bellrock Master Project / Project ManagAIr

Processing date: 2026-07-09

## Parsing Rule

Column B `Phase/Task ID` is the hierarchy key:

- Whole number = Work Package / Phase

- x.x = Task

- x.x.x or deeper = Subtask

Project ManagAIr must resolve requested work package numbers from this catalogue before reading detail files. Do not load the full Rocketlane source sheet for normal project generation.

## Work Package Catalogue

| WP ID | Work Package | Duration Days | Effort Hours | Effort Days | Trigger Code | Detail File |

|---:|---|---:|---:|---:|---|---|

| 1 | Mobilisation & Initiation | — | — | — | TEC_BMA_CON_ECPS_PROS_CON | WP-001 Mobilisation & Initiation |

| 2 | Project Management & Consultancy | 365 | 135 | 18 | TEC_BMA_CON_ECPS_PROS_CON | WP-002 Project Management & Consultancy |

| 3 | Core Data | 49 | 52.5 | 7 | TEC_BAS_CON_CDPS_PROS_CON | WP-003 Core Data |

| 4 | Advanced Authentication | 22 | 22.5 | 3 | TEC_BAS_CON_ADAU_PROS_CON | WP-004 Advanced Authentication |

| 5 | Estates Full | 48 | 56.25 | 7.5 | TEC_PSE_CON_RE_PROS_CON | WP-005 Estates Full |

| 6 | Case Management | 8 | 15 | 2 | TEC_BAS_CON_ACMBO_PROS_CON | WP-006 Case Management |

| 7 | Estates Lite | 36 | 22.5 | 3 | TEC_PSE_CON_RELI_PROS_CON | WP-007 Estates Lite |

| 8 | CAFM Reactive | 42 | 48.75 | 6.5 | TEC_BMA_CON_CAFMRE_PROS_CON | WP-008 CAFM Reactive |

| 9 | CAFM Planned | 42 | 48.75 | 6.5 | TEC_BCO_CON_CAFMPL_PROS_CON | WP-009 CAFM Planned |

| 10 | Finance Interface | 30 | 37.5 | 5 | TBD_SOURCE_VALUE_QUESTION_MARK | WP-010 Finance Interface |

| 11 | Reporting | 32 | 15 | 2 | TBD_SOURCE_VALUE_MIXED | WP-011 Reporting |

| 12 | System Admin Training | 32 | 7.5 | 1 | TBD_SOURCE_VALUE_QUESTION_MARK | WP-012 System Admin Training |

| 13 | Projects & Programmes Full | 39 | 90 | 12 | TEC_BAS_CON_PRPR_PROS_CON | WP-013 Projects & Programmes Full |

| 14 | Permit To Work | 10 | 60 | 8 | TEC_BCO_CON_PTW_PROS_CON | WP-014 Permit To Work |

| 15 | Health & Safety | 18 | 22.5 | 3 | TEC_BCO_CON_HSIE_PROS_CON | WP-015 Health & Safety |

| 16 | Asbestos Surveys | 20 | 22.5 | 3 | TEC_BCO_CON_SURAB_PROS_CON | WP-016 Asbestos Surveys |

| 17 | Assurance Module | 28 | 22.5 | 3 | TEC_BCO_CON_ASSUR_PROS_CON | WP-017 Assurance Module |

| 18 | Fire Risk Assessment | 23 | 22.5 | 3 | TEC_BCO_CON_SURFI_PROS_CON | WP-018 Fire Risk Assessment |

| 19 | Water Monitoring | 24 | 37.5 | 5 | TEC_BCO_CON_SURWM_PROS_CON | WP-019 Water Monitoring |

| 20 | Key Manager | 22 | 26.25 | 3.5 | TEC_BAS_CON_KEYM_PROS_CON | WP-020 Key Manager |

| 21 | CAFM Stock | 27 | 30 | 4 | TEC_BMA_CON_CAFMST_PROS_CON | WP-021 CAFM Stock |

| 22 | Condition Surveys | 57 | 60 | 8 | REVIEW_SOURCE_APPEARS_COPIED_FROM_STOCK | WP-022 Condition Surveys |

| 23 | Facet Surveys | 43 | 22.5 | 3 | TEC_BAS_CON_SURFS_PROS_CON | WP-023 Facet Surveys |

| 24 | Mobile Surveys | 27 | 26.25 | 3.5 | TBD_SOURCE_VALUE_QUESTION_MARK | WP-024 Mobile Surveys |

| 25 | Asset Insights | 27 | 26.25 | 3.5 | TBD_SOURCE_VALUE_QUESTION_MARK | WP-025 Asset Insights |

| 26 | Service Master | 27 | 26.25 | 3.5 | TBD_SOURCE_VALUE_QUESTION_MARK | WP-026 Service Master |

| 27 | Wiggle Desk | 27 | 26.25 | 3.5 | TEC_PSE_WIG_WIGD_PROS_SUP | WP-027 Wiggle Desk |

## Project ManagAIr Usage

When asked to create a new project with selected work packages, Project ManagAIr must:

1. Read this catalogue.

2. Resolve requested WP IDs into names and detail files.

3. Read only the selected work package detail files.

4. Apply the PMO Governance Overlay.

5. Generate project plans and registers with Work Package ID, Work Package Name, Source Task ID and Source Task Name columns.

6. Flag unknown work package IDs instead of inventing scope.

## Known Data Quality Flags

- Several trigger code values in the source are `?` and have been marked as TBD rather than invented.

- Some rows contain copied labels from related work packages.

- Some source spelling and spacing errors are preserved in the immutable source but normalised in derived assets where safe.

- Named individuals in the source should be treated as historical allocation, not default role ownership, unless explicitly confirmed.