## work_package_index
wp_id | wp_code | wp_name | duration_days | effort_hours | effort_days | trigger_code | source_file_id | source_sheet | source_row | detail_file | categories | status | notes
1 | WP-001 | Mobilisation & Initiation |  |  |  | TEC_BMA_CON_ECPS_PROS_CON | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 3 | WP-001 Mobilisation & Initiation | Project Management; Governance; Initiation | canonical | Parent mobilisation phase and initiation tasks.
2 | WP-002 | Project Management & Consultancy | 365 | 135 | 18 | TEC_BMA_CON_ECPS_PROS_CON | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 32 | WP-002 Project Management & Consultancy | Project Management; Consultancy; Governance | canonical | Includes recurring PM, admin, WIP, RAID, issues, decisions and changes.
3 | WP-003 | Core Data | 49 | 52.5 | 7 | TEC_BAS_CON_CDPS_PROS_CON | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 46 | WP-003 Core Data | Work Package Management; Consultancy; Data Management; Training; UAT; Sign Off; Hyper Care | canonical | Foundational data work package.
4 | WP-004 | Advanced Authentication | 22 | 22.5 | 3 | TEC_BAS_CON_ADAU_PROS_CON | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 77 | WP-004 Advanced Authentication | Work Package Management; Consultancy; Data Management; Configuration; UAT; Sign Off; Go Live; Hyper Care | canonical | Authentication / SSO style work package.
5 | WP-005 | Estates Full | 48 | 56.25 | 7.5 | TEC_PSE_CON_RE_PROS_CON | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 96 | WP-005 Estates Full | Work Package Management; Consultancy; Data Management; Training; UAT; Sign Off; Go Live; Hyper Care; Support | canonical | Full estates delivery pattern.
6 | WP-006 | Case Management | 8 | 15 | 2 | TEC_BAS_CON_ACMBO_PROS_CON | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 128 | WP-006 Case Management | Work Package Management; Consultancy; Configuration; UAT; Sign Off; Go Live; Hyper Care; Support | canonical | Short configuration-led work package.
7 | WP-007 | Estates Lite | 36 | 22.5 | 3 | TEC_PSE_CON_RELI_PROS_CON | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 150 | WP-007 Estates Lite | Work Package Management; Consultancy; Data Management; Training; UAT; Sign Off; Go Live; Hyper Care; Support | canonical | Lite estates delivery pattern.
8 | WP-008 | CAFM Reactive | 42 | 48.75 | 6.5 | TEC_BMA_CON_CAFMRE_PROS_CON | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 178 | WP-008 CAFM Reactive | Work Package Management; Consultancy; Data Management; Configuration; Training; UAT; Sign Off; Go Live; Hyper Care; Support | canonical | Reactive helpdesk/supplier portal work package.
9 | WP-009 | CAFM Planned | 42 | 48.75 | 6.5 | TEC_BCO_CON_CAFMPL_PROS_CON | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 210 | WP-009 CAFM Planned | Work Package Management; Consultancy; Data Management; Configuration; Training; UAT; Sign Off; Go Live; Hyper Care; Support | canonical | Planned/PPM work package.
10 | WP-010 | Finance Interface | 30 | 37.5 | 5 | TBD_SOURCE_VALUE_QUESTION_MARK | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 251 | WP-010 Finance Interface | Work Package Management; Consultancy; Development; QA; UAT; Sign Off; Go Live; Hyper Care; Support | review_required | Source trigger code is question mark.
11 | WP-011 | Reporting | 32 | 15 | 2 | TBD_SOURCE_VALUE_MIXED | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 281 | WP-011 Reporting | Work Package Management; Data Management; Training; UAT; Sign Off; Go Live; Hyper Care; Support | review_required | Source trigger values mixed/partial.
12 | WP-012 | System Admin Training | 32 | 7.5 | 1 | TBD_SOURCE_VALUE_QUESTION_MARK | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 297 | WP-012 System Admin Training | Work Package Management; Training; UAT; Sign Off; Hyper Care; Support | review_required | Source trigger code is question mark.
13 | WP-013 | Projects & Programmes Full | 39 | 90 | 12 | TEC_BAS_CON_PRPR_PROS_CON | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 311 | WP-013 Projects & Programmes Full | Work Package Management; Consultancy; Configuration; Data Management; Training; UAT; Sign Off; Go Live; Hyper Care; Support | canonical | Full Projects & Programmes delivery.
14 | WP-014 | Permit To Work | 10 | 60 | 8 | TEC_BCO_CON_PTW_PROS_CON | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 341 | WP-014 Permit To Work | Work Package Management; Consultancy; Data Management; Configuration; Training; UAT; Sign Off; Go Live; Hyper Care; Support | canonical | Permit to Work delivery pattern.
15 | WP-015 | Health & Safety | 18 | 22.5 | 3 | TEC_BCO_CON_HSIE_PROS_CON | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 360 | WP-015 Health & Safety | Work Package Management; Consultancy; Configuration; Training; UAT; Sign Off; Go Live; Hyper Care; Support | canonical | H&S incident/events module.
16 | WP-016 | Asbestos Surveys | 20 | 22.5 | 3 | TEC_BCO_CON_SURAB_PROS_CON | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 382 | WP-016 Asbestos Surveys | Work Package Management; Consultancy; Configuration; Training; UAT; Sign Off; Go Live; Hyper Care; Support | canonical | Asbestos surveys work package.
17 | WP-017 | Assurance Module | 28 | 22.5 | 3 | TEC_BCO_CON_ASSUR_PROS_CON | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 404 | WP-017 Assurance Module | Work Package Management; Consultancy; Data Management; Configuration; Training; UAT; Sign Off; Go Live; Hyper Care; Support | canonical | Assurance module work package.
18 | WP-018 | Fire Risk Assessment | 23 | 22.5 | 3 | TEC_BCO_CON_SURFI_PROS_CON | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 426 | WP-018 Fire Risk Assessment | Work Package Management; Consultancy; Data Management; Configuration; Training; UAT; Sign Off; Go Live; Hyper Care; Support | canonical | FRA survey work package.
19 | WP-019 | Water Monitoring | 24 | 37.5 | 5 | TEC_BCO_CON_SURWM_PROS_CON | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 448 | WP-019 Water Monitoring | Work Package Management; Consultancy; Data Management; Configuration; Training; UAT; Sign Off; Go Live; Hyper Care; Support | canonical | Water monitoring survey work package.
20 | WP-020 | Key Manager | 22 | 26.25 | 3.5 | TEC_BAS_CON_KEYM_PROS_CON | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 452 | WP-020 Key Manager | Work Package Management; Consultancy; Data Management; Configuration; Training; UAT; Sign Off; Go Live; Hyper Care; Support | canonical | Key Manager work package; source includes a copied task ID 17.2.1.
21 | WP-021 | CAFM Stock | 27 | 30 | 4 | TEC_BMA_CON_CAFMST_PROS_CON | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 473 | WP-021 CAFM Stock | Work Package Management; Consultancy; Data Management; Configuration; Training; UAT; Sign Off; Go Live; Hyper Care; Support | canonical | CAFM stock work package.
22 | WP-022 | Condition Surveys | 57 | 60 | 8 | REVIEW_SOURCE_APPEARS_COPIED_FROM_STOCK | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 494 | WP-022 Condition Surveys | Work Package Management; Consultancy; Data Management; Configuration; Training; UAT; Sign Off; Go Live; Hyper Care; Support | review_required | Source top row trigger appears copied from CAFM Stock.
23 | WP-023 | Facet Surveys | 43 | 22.5 | 3 | TEC_BAS_CON_SURFS_PROS_CON | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 525 | WP-023 Facet Surveys | Work Package Management; Consultancy; Data Management; Configuration; Training; UAT; Sign Off; Go Live; Hyper Care; Support | canonical | Facet surveys work package; source has copied Condition Surveys labels in places.
24 | WP-024 | Mobile Surveys | 27 | 26.25 | 3.5 | TBD_SOURCE_VALUE_QUESTION_MARK | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 575 | WP-024 Mobile Surveys | Work Package Management; Consultancy; Data Management; Configuration; Training; UAT; Sign Off; Go Live; Hyper Care; Support | review_required | Source trigger code is question mark.
25 | WP-025 | Asset Insights | 27 | 26.25 | 3.5 | TBD_SOURCE_VALUE_QUESTION_MARK | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 596 | WP-025 Asset Insights | Work Package Management; Consultancy; Data Management; Configuration; Training; UAT; Sign Off; Go Live; Hyper Care; Support | review_required | Source contains copied Mobile Survey key-event labels.
26 | WP-026 | Service Master | 27 | 26.25 | 3.5 | TBD_SOURCE_VALUE_QUESTION_MARK | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 617 | WP-026 Service Master | Work Package Management; Consultancy; Data Management; Configuration; Training; UAT; Sign Off; Go Live; Hyper Care; Support | review_required | Source contains copied Mobile Survey key-event labels.
27 | WP-027 | Wiggle Desk | 27 | 26.25 | 3.5 | TEC_PSE_WIG_WIGD_PROS_SUP | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Rocketlane | 638 | WP-027 Wiggle Desk | Work Package Management; Consultancy; Data Management; Configuration; Training; UAT; Sign Off; Go Live; Hyper Care; Support | canonical | Wiggle Desk work package.

## task_flow_index
wp_id | wp_name | task_id | task_name | start_day | duration | owner_role | category | key_event | level | notes
1 | Mobilisation & Initiation | 1.1 | Governance Setup |  |  | Project Manager | Project Management | New Project Start | Task | Governance setup parent task
1 | Mobilisation & Initiation | 1.1.1 | Project Teams Identified | 1 | 1 | Project Manager | Project Management |  | Subtask
1 | Mobilisation & Initiation | 1.1.2 | Client Charter Sign Off | 1 | 1 | Project Manager / Customer | Project Management |  | Subtask
1 | Mobilisation & Initiation | 1.2 | Commercial & Handover |  |  | Project Manager | Project Management |  | Task
1 | Mobilisation & Initiation | 1.2.1 | Sales Handover | 1 |  | Project Manager / PS Team Lead | Project Management |  | Subtask
1 | Mobilisation & Initiation | 1.2.2 | Baseline Agreed | 1 | 5 | Project Manager / PS Team Lead | Project Management |  | Subtask
1 | Mobilisation & Initiation | 1.2.3 | Pre Mobilisation Call | 6 | 1 | Project Manager / PS Team Lead / Customer | Project Management |  | Subtask
1 | Mobilisation & Initiation | 1.3 | System Spin Up |  |  | PS Team Lead | Project Management |  | Task
1 | Mobilisation & Initiation | 1.3.1 | Create Environments | 6 | 2 | Support | Project Management |  | Subtask
1 | Mobilisation & Initiation | 1.3.2 | Clear Down Data | 6 | 2 | Support | Project Management |  | Subtask
1 | Mobilisation & Initiation | 1.3.3 | Branding Customisation | 8 | 2 | PS Team Lead | Project Management |  | Subtask | Normalised spacing from source
1 | Mobilisation & Initiation | 1.3.4 | Module / Licence Configuration | 8 | 2 | PS Team Lead | Project Management |  | Subtask | Normalised spacing from source
1 | Mobilisation & Initiation | 1.4 | Formal Project Kick Off |  |  | Project Manager / PS Team Lead | Project Management |  | Task
1 | Mobilisation & Initiation | 1.4.1 | Implementation Plan Issued | 9 | 5 | Project Manager / PS Team Lead | Project Management |  | Subtask
1 | Mobilisation & Initiation | 1.4.2 | Implementation Plan Sign Off | 14 | 1 | Project Manager / PS Team Lead / Customer | Project Management |  | Subtask
1 | Mobilisation & Initiation | 1.5 | Project Scope & Process Mapping |  |  | Project Manager / PS Team Lead / Customer | Project Management |  | Task
1 | Mobilisation & Initiation | 1.6.3 | Process / Scope Signed Off | 27 | 1 | Project Manager / PS Team Lead / Customer | Project Management | Process Scope Sign Off | Subtask
2 | Project Management & Consultancy | 2.1 | Workpackages Booked | 1 | 1 | Project Manager | Project Management |  | Task
2 | Project Management & Consultancy | 2.2 | Project Management | 1 | 365 | Project Manager | Project Management |  | Task
2 | Project Management & Consultancy | 2.3 | Project Administration | 1 | 365 | Project Manager | Project Management |  | Task
2 | Project Management & Consultancy | 2.4 | General Consultancy | 28 | 365 | Implementation / Team Leader | Consultancy |  | Task
2 | Project Management & Consultancy | 2.5 | Project Governance | 28 | 365 | Project Manager / Team Leader / Customer | Project Governance |  | Task
2 | Project Management & Consultancy | 2.5.1 | Decision Log | 28 | 365 | Project Team | Project Governance |  | Subtask
2 | Project Management & Consultancy | 2.5.2 | Issue Log | 28 | 365 | Project Team | Project Governance |  | Subtask
2 | Project Management & Consultancy | 2.5.3 | RAID Log | 28 | 365 | Project Team | Project Governance |  | Subtask
2 | Project Management & Consultancy | 2.5.4 | Change / Variation Requests | 28 | 365 | Project Team | Project Governance |  | Subtask
3 | Core Data | 3.1 | Work Package Management (Core Data) |  |  | Implementation | Work Package Management |  | Task
3 | Core Data | 3.2.1 | Core Data Overview Session | 1 | 1 | Customer / Implementation | Consultancy | Core Data WP Start | Subtask
3 | Core Data | 3.3.1 | Core Data Data Mapping Session | 5 | 1 | Implementation / Customer | Data Management |  | Subtask
3 | Core Data | 3.3.1 | Core Data Test Data Collation | 5 | 15 | Customer | Data Management | Core Data Test Data Start | Subtask | Duplicate source task ID retained
3 | Core Data | 3.3.2 | Core Data Test Data Validation and Load |  |  | Data Management | Data Management | Core Data Test Data End | Task
3 | Core Data | 3.3.2.1 | Core Data Test Data Load | 22 | 2 | Data Management | Data Management |  | Subtask
3 | Core Data | 3.3.2.2 | Core Data Test Data Playback Session | 25 | 1 | Customer / Implementation | Data Management |  | Subtask
3 | Core Data | 3.3.3 | Core Data Full Data Collation | 25 | 10 | Customer | Data Management | Core Data Full Data Start | Subtask
3 | Core Data | 3.3.5 | Core Data Full Data Validation and Load |  |  | Data Management | Data Management | Core Data Full Data End | Task
3 | Core Data | 3.5.1 | Core Data UAT | 44 | 5 | Customer / Implementation | UAT | Core Data UAT Start | Subtask
3 | Core Data | 3.5.2 | Core Data Sign Off | 49 | 1 | Customer / Project Manager | Sign Off | Core Data WP End | Subtask
4 | Advanced Authentication | 4.2.1 | Advanced Authentication Overview Session | 1 | 1 | Customer / OnBoarding | Consultancy | Adv Auth WP Start | Subtask
4 | Advanced Authentication | 4.3.1 | Collate Advanced Authentication Data | 2 | 10 | Customer | Data Management | Adv Auth Data Start | Subtask
4 | Advanced Authentication | 4.4.1 | Configure Concerto | 13 | 2 | Implementation | Configuration |  | Subtask
4 | Advanced Authentication | 4.4.2 | Deploy in Octopus | 13 | 2 | Implementation | Configuration |  | Subtask
4 | Advanced Authentication | 4.3.1 | Advanced Authentication UAT | 16 | 5 | Customer / OnBoarding | UAT | Adv Auth UAT Start | Subtask | Duplicate source task ID retained
4 | Advanced Authentication | 4.3.2 | Advanced Authentication Sign Off | 21 | 1 | Customer / Project Manager | Sign Off | Adv Auth WP End | Subtask
4 | Advanced Authentication | 4.3.3 | Advanced Authentication Go Live | 22 | 1 | Customer / OnBoarding | Go Live | Adv Auth Go Live | Subtask
5 | Estates Full | 5.2.1 | Estates Full Overview Session | 1 | 1 | Customer / Implementation | Consultancy | Estates Full WP Start | Subtask
5 | Estates Full | 5.3.1 | Estates Full Test Data Collation | 1 | 15 | Customer | Data Management | Estates Full Test Data Start | Subtask
5 | Estates Full | 5.3.3 | Estate Full Test Data Playback Session | 20 | 1 | Customer / Data Management | Data Management |  | Subtask
5 | Estates Full | 5.3.4 | Estate Full Full Data Collation | 21 | 10 | Customer | Data Management | Estates Full - Full Data Start | Subtask
5 | Estates Full | 5.4.1 | Estates Training Session | 35 | 1 | Product Enablement / Customer | Training |  | Subtask
5 | Estates Full | 5.4.2 | Estates Reporting Training Session | 40 | 1 | Product Enablement / Customer | Training |  | Subtask
5 | Estates Full | 5.5.1 | Estates Full UAT | 42 | 5 | Customer / Implementation | UAT | Estates Full UAT Start | Subtask
5 | Estates Full | 5.5.2 | Estates Full Sign Off | 47 | 1 | Customer / Project Manager | Sign Off | Estates Full WP End | Subtask
6 | Case Management | 6.2.1 | Case Management Overview Session | 53 | 1 | Customer / Implementation | Consultancy | Case Management WP Start | Subtask
6 | Case Management | 6.3.1 | Case Management | 54 | 1 | Implementation | Configuration |  | Subtask
6 | Case Management | 6.3.2 | Template Document Queries | 54 | 1 | Implementation | Configuration |  | Subtask
6 | Case Management | 6.3.3 | Query Creation | 54 | 1 | Implementation | Configuration |  | Subtask
6 | Case Management | 6.4.1 | Case Management UAT | 55 | 5 | Customer / Implementation | UAT | Case Management UAT Start | Subtask
6 | Case Management | 6.4.2 | Case Management Sign Off | 60 | 1 | Customer / Project Manager | Sign Off | Case Management WP End | Subtask
7 | Estates Lite | 7.2.1 | Estates Lite Overview Session | 1 | 1 | Customer / Implementation | Consultancy | Estates Lite WP Start | Subtask
7 | Estates Lite | 7.3.1 | Estates Lite Test Data Collation | 2 | 10 | Customer | Data Management | Estates Lite Test Data Start | Subtask
7 | Estates Lite | 7.3.2.1 | Estate Lite Load Test Data | 13 | 2 | Data Management | Data Management |  | Subtask
7 | Estates Lite | 7.5.1 | Estates Lite Training Session | 30 | 1 | Product Enablement / Customer | Training |  | Subtask
7 | Estates Lite | 7.6.1 | Estates Lite UAT | 31 | 5 | Customer / Implementation | UAT | Estates Lite UAT Start | Subtask
7 | Estates Lite | 7.6.2 | Estates Lite Sign Off | 36 | 1 | Customer / Project Manager | Sign Off | Estates Lite WP End | Subtask
8 | CAFM Reactive | 8.2.1 | CAFM Reactive Overview Session | 1 | 1 | Customer / Implementation | Consultancy | CAFM Reactive WP Start | Subtask
8 | CAFM Reactive | 8.3.1 | Collate Reactive Data | 2 | 15 | Customer | Customer | CAFM Reactive Data Start | Subtask
8 | CAFM Reactive | 8.4.1 | Configure FixMy | 2 | 1 | Implementation | Configuration |  | Subtask
8 | CAFM Reactive | 8.4.2 | Supplier Portal | 2 | 15 | Implementation | Configuration |  | Subtask
8 | CAFM Reactive | 8.4.3 | Helpdesk Actions | 2 | 15 | Implementation | Configuration |  | Subtask
8 | CAFM Reactive | 8.5.1 | Supplier Portal Training | 21 | 1 | Product Enablement / Customer | Training |  | Subtask
8 | CAFM Reactive | 8.5.2 | Reactive Helpdesk Training | 36 | 1 | Product Enablement / Customer | Training |  | Subtask
8 | CAFM Reactive | 8.6.1 | CAFM Reactive UAT | 37 | 5 | Customer / Implementation | UAT | CAFMR UAT Start | Subtask
8 | CAFM Reactive | 8.6.2 | CAFM Reactive Sign Off | 42 | 1 | Customer / Project Manager | Sign Off | CAFM Reactive WP End | Subtask
8 | CAFM Reactive | 8.6.3 | CAFM Reactive Go Live | 43 | 1 | Customer / Implementation | Go Live | CAFM Reactive Go Live | Subtask
9 | CAFM Planned | 9.2.1 | PPM Overview Session | 1 | 1 | Customer / Implementation | Consultancy | CAFM Planned WP Start | Subtask
9 | CAFM Planned | 9.3.1 | CAFM Planned Data Mapping Session | 2 | 1 | Customer / Implementation | Data Management |  | Subtask
9 | CAFM Planned | 9.3.2 | Collate Planned Test Data | 2 | 15 | Customer | Customer | CAFM Planned Data Start | Subtask
9 | CAFM Planned | 9.4.1 | Configure PPMs Internal / External |  |  | Implementation | Configuration |  | Subtask
9 | CAFM Planned | 9.5.1 | Supplier Portal Training | 21 | 1 | Product Enablement / Customer | Training |  | Subtask
9 | CAFM Planned | 9.5.2 | PPM Training | 36 | 1 | Product Enablement / Customer | Training |  | Subtask
9 | CAFM Planned | 9.6.1 | CAFM Planned UAT | 37 | 5 | Customer / Implementation | UAT | CAFM Planned UAT Start | Subtask
9 | CAFM Planned | 9.6.2 | CAFM Planned Sign Off | 42 | 1 | Customer / Project Manager | Sign Off | CAFM Planned WP End | Subtask
10 | Finance Interface | 10.2.1 | Finance Interface Overview Session | 1 | 1 | Customer / OnBoarding | Consultancy | Finance Interface WP Start | Subtask
10 | Finance Interface | 10.2.2 | Finance Interface ICD Creation | 2 | 10 | OnBoarding | Consultancy | Finance Interface Creation Start | Subtask | Normalised copied key-event text
10 | Finance Interface | 10.2.3 | Finance Interface ICD Sign Off | 12 | 1 | Customer / OnBoarding | Consultancy | Finance Interface Creation End | Subtask | Normalised copied key-event text
10 | Finance Interface | 10.3.1 | Finance Interface Build | 13 | 5 | Development | Development | Finance Interface Dev Start | Subtask
10 | Finance Interface | 10.3.2 | Finance Interface Test | 18 | 5 | Development / OnBoarding | Development |  | Subtask
10 | Finance Interface | 10.3.3 | Finance Interface Internal Sign Off | 23 | 1 | QA / OnBoarding | QA | Finance Interface Dev End | Subtask
10 | Finance Interface | 10.4.1 | Finance Interface UAT | 24 | 5 | Customer / OnBoarding | UAT | Finance Interface UAT Start | Subtask
10 | Finance Interface | 10.4.2 | Finance Interface Sign Off | 29 | 1 | Customer / Project Manager | Sign Off | Finance Interface WP End | Subtask
11 | Reporting | 11.2.1 | Reporting Overview Session | 1 | 1 | Data Management | Data Management | Reporting WP Start | Subtask
11 | Reporting | 11.2.2 | Collate Reporting Requirements |  | 20 | Customer | Data Management | Reporting Data Start | Subtask | Normalised spelling from source
11 | Reporting | 11.2.3 | Project Budgets |  | 6 | Data Management | Data Management | Reporting Data End | Subtask
11 | Reporting | 11.2.4 | Deliver Scripts / Reports / Dashboards |  | 5 | Data Management | Data Management |  | Subtask
11 | Reporting | 11.3.1 | Training Session 1 |  | 1 | Data Management / Customer | Training |  | Subtask
11 | Reporting | 11.4.1 | Reporting UAT | 24 | 5 | Customer / Data Management | UAT | Reporting UAT Start | Subtask
11 | Reporting | 11.4.2 | Reporting Sign Off | 29 | 1 | Customer / Project Manager | Sign Off | Reporting WP End | Subtask
12 | System Admin Training | 12.2.1 | Training Session 1 | 7 | 1 | Data Management / Customer | Training |  | Subtask
12 | System Admin Training | 12.3 | System Admin UAT | 8 | 5 | Customer / Data Management | UAT |  | Task
12 | System Admin Training | 12.3.1 | System Admin Sign Off | 13 | 1 | Customer / Project Manager | Sign Off |  | Subtask
13 | Projects & Programmes Full | 13.2.1 | Projects Overview Session 1 | 1 | 1 | Customer / Implementation | Consultancy | P&P WP Start | Subtask
13 | Projects & Programmes Full | 13.2.2 | Projects Overview Session 2 | 7 | 1 | Customer / Implementation | Consultancy |  | Subtask
13 | Projects & Programmes Full | 13.3.1 | Projects Setup | 2 | 15 | Implementation | Configuration |  | Subtask
13 | Projects & Programmes Full | 13.3.2 | Projects Templates | 2 | 15 | Implementation | Configuration |  | Subtask
13 | Projects & Programmes Full | 13.3.3 | Projects Settings and Config | 2 | 15 | Implementation | Configuration |  | Subtask
13 | Projects & Programmes Full | 13.4.1 | Client Collate Budget Data | 2 | 15 | Customer | Customer | P&P Budget Data Start | Subtask
13 | Projects & Programmes Full | 13.4.4 | Load Project Data | 31 | 2 | Data Management | Data Management | P&P Project Data End | Subtask
13 | Projects & Programmes Full | 13.6.1 | P&P Full UAT | 34 | 5 | Customer / Implementation | UAT | P&P Full UAT Start | Subtask
13 | Projects & Programmes Full | 13.6.2 | P&P Full Sign Off | 39 | 1 | Customer / Project Manager | Sign Off | P&P Full WP End | Subtask
14 | Permit To Work | 14.2.2 | Permit To Work Overview Session | 1 | 1 | Customer / Implementation | Consultancy | P2W WP Start | Subtask
14 | Permit To Work | 14.3.1 | Collate Permit to Work Data | 2 | 10 | Customer | Data Management | P2W Data Start | Subtask
14 | Permit To Work | 14.3.2 | Permit to Work Data Validation and Load | 12 | 2 | Data Management | Data Management | P2W Data End | Subtask
14 | Permit To Work | 14.4 | Permit to Work Configuration | 13 | 5 | Implementation | Configuration |  | Task
14 | Permit To Work | 14.5.1 | Training Session 1 | 20 | 1 | Product Enablement / Customer | Training |  | Subtask
14 | Permit To Work | 14.6.1 | Permit To Work UAT | 21 | 5 | Customer / Implementation | UAT | P2W UAT Start | Subtask
14 | Permit To Work | 14.6.2 | Permit To Work Sign Off | 26 | 1 | Customer / Project Manager | Sign Off | P2W WP End | Subtask
15 | Health & Safety | 15.2.1 | H&S Overview Session | 1 | 1 | Customer / Implementation | Consultancy | H&S WP Start | Subtask
15 | Health & Safety | 15.4.1 | Config Actions etc | 2 | 5 | Implementation | Configuration |  | Subtask
15 | Health & Safety | 15.4.2 | Playback | 8 | 1 | Implementation / Customer | Configuration |  | Subtask
15 | Health & Safety | 15.5.1 | Training Session 1 | 12 | 1 | Product Enablement / Customer | Training |  | Subtask
15 | Health & Safety | 15.6.1 | H&S UAT | 13 | 5 | Customer / Implementation | UAT | H&S UAT Start | Subtask
15 | Health & Safety | 15.6.2 | H&S Sign Off | 18 | 1 | Customer / Project Manager | Sign Off | H&S WP End | Subtask
16 | Asbestos Surveys | 16.2.1 | Asbestos Overview Session | 1 | 1 | Customer / Implementation | Consultancy | Asbestos WP Start | Subtask
16 | Asbestos Surveys | 16.3 | Asbestos Configuration | 2 | 5 | Implementation | Configuration |  | Task
16 | Asbestos Surveys | 16.4.1 | Asbestos Importer Training | 7 | 1 | Product Enablement / Customer | Training |  | Subtask
16 | Asbestos Surveys | 16.4.2 | Asbestos Train the Trainer | 14 | 1 | Product Enablement / Customer | Training |  | Subtask
16 | Asbestos Surveys | 16.5.1 | Asbestos UAT | 15 | 5 | Customer / Implementation | UAT | Asbestos UAT Start | Subtask
16 | Asbestos Surveys | 16.5.2 | Asbestos Sign Off | 20 | 1 | Customer / Project Manager | Sign Off | Asbestos WP End | Subtask
17 | Assurance Module | 17.2.2 | Assurance Overview Session | 1 | 1 | Customer / Implementation | Consultancy | Assurance Full WP Start | Subtask
17 | Assurance Module | 17.3.1 | Collate Assurance Data | 2 | 10 | Customer | Data Management | Assurance Data Start | Subtask
17 | Assurance Module | 17.4.1 | Users | 12 | 5 | Implementation | Configuration |  | Subtask
17 | Assurance Module | 17.4.2 | Roles | 12 | 5 | Implementation | Configuration |  | Subtask
17 | Assurance Module | 17.4.3 | Assurance Playback and Admin Session | 21 | 1 | Implementation / Customer | Configuration |  | Subtask
17 | Assurance Module | 17.5.1 | Assurance End User Training | 22 | 1 | Product Enablement / Customer | Training |  | Subtask
17 | Assurance Module | 17.6.1 | Assurance UAT | 23 | 5 | Customer / Implementation | UAT | Assurance UAT Start | Subtask | Normalised spelling from source
17 | Assurance Module | 17.6.2 | Assurance Sign Off | 28 | 1 | Customer / Project Manager | Sign Off | Assurance WP End | Subtask
18 | Fire Risk Assessment | 18.2.1 | Fire Risk Assessment Overview Session | 1 | 1 | Customer / Implementation | Consultancy | FRA WP Start | Subtask
18 | Fire Risk Assessment | 18.3.1 | Collate Fire Risk Assessment Data | 2 | 10 | Customer | Customer | FRA Data Start | Subtask
18 | Fire Risk Assessment | 18.3.2 | Fire Risk Assessment Data Validation and Load | 12 | 2 | Data Management | Data Management | FRA Data End | Subtask
18 | Fire Risk Assessment | 18.4 | Fire Risk Assessment Configuration | 11 | 5 | Implementation | Configuration |  | Task
18 | Fire Risk Assessment | 18.5.1 | Fire Risk Assessment Training Session 1 | 16 | 1 | Product Enablement / Customer | Training |  | Subtask
18 | Fire Risk Assessment | 18.6.1 | Fire Risk Assessment UAT | 17 | 5 | Customer / OnBoarding | UAT | FRA UAT Start | Subtask
18 | Fire Risk Assessment | 18.6.2 | Fire Risk Assessment Sign Off | 22 | 1 | Customer / Project Manager | Sign Off | FRA WP End | Subtask
19 | Water Monitoring | 19.2.1 | Water Monitoring Overview Session | 1 | 1 | Customer / Implementation | Consultancy | Water Monitor WP Start | Subtask
19 | Water Monitoring | 19.3.1 | Collate Water Monitoring Data | 1 | 10 | Customer | Customer | Water Monitor Data Start | Subtask | Normalised spelling from source
19 | Water Monitoring | 19.3.2 | Water Monitoring Data Validation and Load | 11 | 1 | Data Management | Data Management | Water Monitor Data End | Subtask | Normalised spelling from source
19 | Water Monitoring | 19.4 | Water Monitoring Configuration | 12 | 5 | Implementation | Configuration |  | Task
19 | Water Monitoring | 19.5.1 | Water Monitoring Train the Trainer | 18 | 1 | Product Enablement / Customer | Training |  | Subtask
19 | Water Monitoring | 19.6.1 | Water Monitoring UAT | 19 | 5 | Customer / OnBoarding | UAT | Water Monitor UAT Start | Subtask
19 | Water Monitoring | 19.6.2 | Water Monitoring Sign Off | 24 | 1 | Customer / Project Manager | Sign Off | Water Monitor WP End | Subtask
20 | Key Manager | 20.2.1 | Key Manager Overview Session | 1 | 1 | Customer / Implementation | Consultancy | Key Manager WP Start | Subtask | Source task ID copied as 17.2.1 in sheet; normalised here to 20.2.1
20 | Key Manager | 20.3.1 | Collate Key Manager Data | 2 | 10 | Customer | Customer | Key Manager Data Start | Subtask
20 | Key Manager | 20.3.2 | Key Manager Data Validation and Load | 12 | 2 | Data Management | Data Management | Key Manager Data End | Subtask
20 | Key Manager | 20.4 | Key Manager Configuration | 13 | 2 | Implementation | Configuration |  | Task
20 | Key Manager | 20.5.1 | Key Manager Training Session 1 | 15 | 1 | Product Enablement / Customer | Training |  | Subtask
20 | Key Manager | 20.6.1 | Key Manager UAT | 17 | 5 | Customer / OnBoarding | UAT | Key Manager UAT Start | Subtask
20 | Key Manager | 20.6.2 | Key Manager Sign Off | 22 | 1 | Customer / Project Manager | Sign Off | Key Manager WP End | Subtask
21 | CAFM Stock | 21.2.1 | CAFM Stock Overview Session | 1 | 1 | Customer / Implementation | Consultancy | CAFM Stock WP Start | Subtask
21 | CAFM Stock | 21.3.1 | Collate CAFM Stock Data | 2 | 10 | Customer | Customer | CAFM Stock Data Start | Subtask
21 | CAFM Stock | 21.3.2 | CAFM Stock Data Validation and Load | 12 | 2 | Data Management | Data Management | CAFM Stock Data End | Subtask
21 | CAFM Stock | 21.4 | CAFM Stock Configuration | 11 | 5 | Implementation | Configuration |  | Task
21 | CAFM Stock | 21.5.1 | CAFM Stock Training Session 1 | 20 | 1 | Product Enablement / Customer | Training |  | Subtask
21 | CAFM Stock | 21.6.1 | CAFM Stock UAT | 21 | 5 | Customer / OnBoarding | UAT | CAFM Stock UAT Start | Subtask
21 | CAFM Stock | 21.6.2 | CAFM Stock Sign Off | 26 | 1 | Customer / Project Manager | Sign Off | CAFM Stock WP End | Subtask
22 | Condition Surveys | 22.2.1 | Condition Surveys Overview Session | 1 | 1 | Customer / Implementation | Consultancy | Condition Surveys WP Start | Subtask
22 | Condition Surveys | 22.3.1.1 | Collate Element List | 1 | 5 | Customer | Data Management |  | Subtask
22 | Condition Surveys | 22.3.1.4 | Sign Off Element List | 10 | 1 | Customer / Implementation | Data Management |  | Subtask
22 | Condition Surveys | 22.3.2.1 | Collate Sample Condition Survey Data | 10 | 10 | Customer | Data Management |  | Subtask
22 | Condition Surveys | 22.3.2.4 | Client Sign Off Condition Survey Data | 27 | 1 | Customer | Data Management |  | Subtask
22 | Condition Surveys | 22.3.3.1 | Provide Full Condition Survey Data | 28 | 10 | Customer | Data Management |  | Subtask
22 | Condition Surveys | 22.4 | Condition Surveys Configuration | 42 | 5 | Implementation | Configuration |  | Task
22 | Condition Surveys | 22.5.1 | Condition Surveys Training Session 1 | 50 | 1 | Product Enablement / Customer | Training |  | Subtask
22 | Condition Surveys | 22.6.1 | Condition Surveys UAT | 52 | 5 | Customer / Implementation | UAT | Condition Surveys UAT Start | Subtask
22 | Condition Surveys | 22.6.2 | Condition Surveys Sign Off | 57 | 1 | Customer / Project Manager | Sign Off | Condition Surveys WP End | Subtask
23 | Facet Surveys | 23.2.1 | Facet Surveys Overview Session | 1 | 1 | Customer / Implementation | Consultancy | Facet Surveys WP Start | Subtask | Source contains copied Condition Surveys labels in places
23 | Facet Surveys | 23.3.1 | Collate Facet Surveys Data | 2 | 10 | Customer | Customer | Facet Survey Data Start | Subtask
23 | Facet Surveys | 23.3.2 | Facet Surveys Data Validation and Load |  |  | Data Management | Data Management | Facet Survey Data End | Subtask
23 | Facet Surveys | 23.3.4 | Full Load | 24 | 2 | Data Management | Data Management |  | Subtask
23 | Facet Surveys | 23.4 | Facet Surveys Configuration | 26 | 5 | Implementation | Configuration |  | Task
23 | Facet Surveys | 23.5.1 | Facet Surveys Training Session 1 | 31 | 1 | Product Enablement / Customer | Training |  | Subtask
23 | Facet Surveys | 23.6.1 | Facet Surveys UAT | 32 | 5 | Customer / OnBoarding | UAT | Facet Surveys UAT Start | Subtask
23 | Facet Surveys | 23.6.2 | Facet Surveys Sign Off | 37 | 1 | Customer / Project Manager | Sign Off | Facet Surveys WP End | Subtask
24 | Mobile Surveys | 24.2.1 | Mobile Surveys Overview Session | 1 | 1 | Customer / Implementation | Consultancy | Mobile Surveys WP Start | Subtask
24 | Mobile Surveys | 24.3.1 | Collate Mobile Surveys Data | 2 | 10 | Customer | Customer | Mobile Survey Data Start | Subtask
24 | Mobile Surveys | 24.3.2 | Mobile Surveys Data Validation and Load | 12 | 2 | Data Management | Data Management | Mobile Survey Data End | Subtask
24 | Mobile Surveys | 24.4 | Mobile Surveys Configuration | 11 | 5 | Implementation | Configuration |  | Task
24 | Mobile Surveys | 24.5.1 | Mobile Surveys Training Session 1 | 20 | 1 | Product Enablement / Customer | Training |  | Subtask
24 | Mobile Surveys | 24.6.1 | Mobile Surveys UAT | 21 | 5 | Customer / OnBoarding | UAT | Mobile Surveys UAT Start | Subtask
24 | Mobile Surveys | 24.6.2 | Mobile Surveys Sign Off | 26 | 1 | Customer / Project Manager | Sign Off | Mobile Surveys WP End | Subtask
25 | Asset Insights | 25.2.1 | Asset Insights Overview Session | 1 | 1 | Customer / Implementation | Consultancy | Asset Insights WP Start | Subtask
25 | Asset Insights | 25.3.1 | Collate Asset Insights Data | 2 | 10 | Customer | Customer | Asset Insights Data Start | Subtask |  | Corrected copied source key-event label from Mobile Survey Data Start
25 | Asset Insights | 25.3.2 | Asset Insights Data Validation and Load | 12 | 2 | Data Management | Data Management | Asset Insights Data End | Subtask |  | Corrected copied source key-event label from Mobile Survey Data End
25 | Asset Insights | 25.4 | Asset Insights Configuration | 11 | 5 | Implementation | Configuration |  | Task
25 | Asset Insights | 25.5.1 | Asset Insights Training Session 1 | 20 | 1 | Product Enablement / Customer | Training |  | Subtask
25 | Asset Insights | 25.6.1 | Asset Insights UAT | 21 | 5 | Customer / OnBoarding | UAT | Asset Insights UAT Start | Subtask
25 | Asset Insights | 25.6.2 | Asset Insights Sign Off | 26 | 1 | Customer / Project Manager | Sign Off | Asset Insights WP End | Subtask
26 | Service Master | 26.2.1 | Service Master Overview Session | 1 | 1 | Customer / Implementation | Consultancy | Service Master WP Start | Subtask
26 | Service Master | 26.3.1 | Collate Service Master Data | 2 | 10 | Customer | Customer | Service Master Data Start | Subtask |  | Corrected copied source key-event label from Mobile Survey Data Start
26 | Service Master | 26.3.2 | Service Master Data Validation and Load | 12 | 2 | Data Management | Data Management | Service Master Data End | Subtask |  | Corrected copied source key-event label from Mobile Survey Data End
26 | Service Master | 26.4 | Service Master Configuration | 11 | 5 | Implementation | Configuration |  | Task
26 | Service Master | 26.5.1 | Service Master Training Session 1 | 20 | 1 | Product Enablement / Customer | Training |  | Subtask
26 | Service Master | 26.6.1 | Service Master UAT | 21 | 5 | Customer / OnBoarding | UAT | Service Master UAT Start | Subtask
26 | Service Master | 26.6.2 | Service Master Sign Off | 26 | 1 | Customer / Project Manager | Sign Off | Service Master WP End | Subtask
27 | Wiggle Desk | 27.2.1 | Wiggle Desk Overview Session | 1 | 1 | Customer / Implementation | Consultancy | Wiggle Desk WP Start | Subtask
27 | Wiggle Desk | 27.3.1 | Collate Wiggle Desk Data | 2 | 10 | Customer | Customer | Wiggle Desk Data Start | Subtask
27 | Wiggle Desk | 27.3.2 | Wiggle Desk Data Validation and Load | 12 | 2 | Data Management | Data Management | Wiggle Desk Data End | Subtask
27 | Wiggle Desk | 27.4 | Wiggle Desk Configuration | 11 | 5 | Implementation | Configuration |  | Task
27 | Wiggle Desk | 27.5.1 | Wiggle Desk Training Session 1 | 20 | 1 | Product Enablement / Customer | Training |  | Subtask
27 | Wiggle Desk | 27.6.1 | Wiggle Desk UAT | 21 | 5 | Customer / OnBoarding | UAT | Wiggle Desk UAT Start | Subtask
27 | Wiggle Desk | 27.6.2 | Wiggle Desk Sign Off | 26 | 1 | Customer / Project Manager | Sign Off | Wiggle Desk WP End | Subtask

## pmo_governance_overlay
phase_order | phase | item_id | item_type | item | source_mapping | owner_role | output_required | notes
1 | Project Mobilisation | 1.1 | Task | Assign a Project Team to oversee delivery based on capacity and capability | PMO WIP 1.1 / Rocketlane 1.1.1 | PMO Lead | Project team confirmed | Mandatory governance item
1 | Project Mobilisation | 1.2 | Task | PM reviews contract, tender, bid documentation, SOW and contract specifics | PMO WIP 1.2 | Project Manager | Contract review notes | Must happen before customer commitments are confirmed
1 | Project Mobilisation | 1.3 | Task | PL reviews scope, deliverables and commercial terms | PMO WIP 1.3 | Project Lead | Delivery review notes | Ensures delivery team understands scope and constraints
1 | Project Mobilisation | 1.4 | Task | Internal Sales Handover captures client nuance and undocumented expectations | PMO WIP 1.4 / Rocketlane 1.2.1 | PM / PL | Sales handover complete | Important source of delivery context
2 | Customer Handover | 2.1 | Task | Schedule and facilitate remote Customer Handover Meeting | PMO WIP 2.1 | PM / PL | Customer handover complete | Include Sales Rep, PM and PL
2 | Customer Handover | 2.2 | Task | Review SOW with customer and confirm scope alignment | PMO WIP 2.2 | PM / PL | SOW agreement confirmed | Baseline before project plan confirmation
3 | Professional Services Preparation | 3.1 | Task | Review speculative product development items and confirm delivery timeframes | PMO WIP 3.1 | Professional Services | Development items reviewed | Stops speculative items becoming hidden scope
3 | Professional Services Preparation | 3.2 | Task | Issue Project Initiation Pack | PMO WIP 3.2 / Rocketlane 1.4.1 | PM | Initiation pack issued | Include standard documents and recommended project plan
4 | Design Phase | 4.1 | Task | Book face-to-face onsite kick-off meeting | PMO WIP 4.1 / Rocketlane 1.5.1 | PM / PL | Kick-off booked | May be remote where appropriate
4 | Design Phase | 4.2 | Task | Cover purchased solution areas, Core Data and future meetings | PMO WIP 4.2 | PM / PL / Customer | Design phase agenda complete | Confirm future meeting dates and project plan
5 | Delivery Phase | 5.1 | Task | Send calendar invitations for sessions and deadlines with cancellation terms | PMO WIP 5.1 | PM | Sessions hard-booked | Applies to selected work packages
5 | Delivery Phase | 5.2 | Automated Form | Send monthly CSAT surveys | PMO WIP 5.2 | PM / Automation | CSAT issued | Optional automation candidate
5 | Delivery Phase | 5.3 | Automated Form | Send quarterly NPS surveys | PMO WIP 5.3 | PM / Automation | NPS issued | Optional automation candidate
5 | Delivery Phase | 5.4 | Recurring Task | Hold monthly project review meetings with PL, PM and customer | PMO WIP 5.4 / Rocketlane 2.2.1 | PM / PL | Monthly review complete | Must cover scope, budget, timeline and RAID
5 | Delivery Phase | 5.5 | Form Template | During each review compare delivered scope vs SOW, budget, timeline and risks/issues | PMO WIP 5.5 | PM | Review record complete | Feeds project register
5 | Delivery Phase | 5.6 | Project Update | Send a status report after each review meeting | PMO WIP 5.6 | PM | Status report issued | Customer communication artefact
6 | UAT and Training | 6.1 | Task and Form | Manage UAT phase and ensure acceptance criteria are formally signed off | PMO WIP 6.1 | PM / PL / Customer | UAT sign-off | Must link to selected work packages
6 | UAT and Training | 6.2 | Task and Form | Deliver training and obtain documented sign-off | PMO WIP 6.2 | Product Enablement | Training sign-off | Learner evidence should be stored
6 | UAT and Training | 6.3 | Automated Form | Send CSAT survey after training | PMO WIP 6.3 | Automation / PM | Training CSAT issued | Optional automation candidate
6 | UAT and Training | 6.4 | Task | Record trained learners in project documentation | PMO WIP 6.4 | PM / Product Enablement | Training attendance record | Supports handover and audit
7 | Go Live | 7.1 | Task | Attend customer site on go-live day where required | PMO WIP 7.1 | Implementation | Go-live attendance | Site attendance depends on project scope
7 | Go Live | 7.2 | Task | Commence two-week hypercare period | PMO WIP 7.2 | PM / Implementation | Hypercare started | No new change requests during hypercare
7 | Go Live | 7.3 | Task and Form | Obtain formal Hypercare Completion Sign-off | PMO WIP 7.3 | PM / Customer | Hypercare sign-off | Close before handover
8 | Close Out | 8.1 | Task | Hold project close-out meeting with Customer, Professional Services, Support and CSM | PMO WIP 8.1 | PM | Close-out meeting | Source notes says not built yet
8 | Close Out | 8.2 | Task | Demonstrate how to raise support tickets | PMO WIP 8.2 | Support / PM | Support process confirmed
8 | Close Out | 8.3 | Task | CSM schedules 30, 60 and 90 day check-ins | PMO WIP 8.3 | CSM | Success check-ins scheduled
8 | Close Out | 8.4 | Task | Package and share project documentation with Customer, Support and CSM | PMO WIP 8.4 | PM | Project documentation pack
8 | Close Out | 8.5 | Task | Invite customer to retrospective meeting to gather feedback and lessons learned | PMO WIP 8.5 | PM | Retrospective invited | Lessons feed continuous improvement

## project_plan_template
phase | work_package_id | work_package_name | source_task_id | source_task_name | task_level | start_day | duration_days | owner_role | customer_owner | bellrock_owner | category | billable | milestone | key_event | status | source | notes
PMO Governance |  |  |  |  | Phase |  |  | PM |  |  | Governance | No | No |  | Not Started | pmo_governance_overlay | Mandatory project scaffold
Work Package Delivery | {wp_id} | {wp_name} | {task_id} | {task_name} | {level} | {start_day} | {duration} | {owner_role} | TBC | TBC | {category} | TBC | TBC | {key_event} | Not Started | task_flow_index | Generated from selected work packages

## project_register_template
register_id | register_type | work_package_id | work_package_name | source_task_id | source_task_name | category | owner | due_date_or_target_day | status | priority | item_description | impact | next_action | customer_owner | bellrock_owner | date_raised | date_closed | evidence_or_source_link | decision_required | created_from | remarks
REG-001 | Risk | {wp_id} | {wp_name} | {task_id} | {task_name} | {category} | TBC | {start_day} | Open | Medium | Describe risk here | Describe impact here | Describe mitigation or next action | TBC | TBC | YYYY-MM-DD |  | Source link | No | Project ManagAIr | Template row
REG-002 | Decision | {wp_id} | {wp_name} | {task_id} | {task_name} | {category} | TBC | {start_day} | Open | Medium | Describe decision required | Describe impact of decision | Confirm decision owner and deadline | TBC | TBC | YYYY-MM-DD |  | Source link | Yes | Project ManagAIr | Template row

## agent_instructions
instruction_id | area | instruction | must_do | notes
PM-001 | Retrieval | When creating a Bellrock project, first read work_package_index. | Yes | Do not load the full source sheet for normal generation.
PM-002 | Scope Resolution | Resolve requested whole-number work package IDs into names, trigger codes and task flows. | Yes | Example: 1,2,3,8,11.
PM-003 | Task Retrieval | Read task_flow_index only for selected work packages. | Yes | Use wp_id filter.
PM-004 | Governance | Apply pmo_governance_overlay to every project unless explicitly excluded. | Yes | This is the standard governance scaffold.
PM-005 | Registers | Every project plan/register row derived from a work package must include work_package_id and work_package_name. | Yes | Fixes the NPL register gap.
PM-006 | Traceability | Include source_task_id and source_task_name wherever available. | Yes | Supports audit and review.
PM-007 | Invalid IDs | If a requested WP ID is missing from work_package_index, stop and flag it. | Yes | Do not invent work packages.
PM-008 | Source Handling | Treat Rocketlane Project Plan Template v2 as immutable evidence. | Yes | Derived assets may normalise wording but source is not edited.
PM-009 | Unclear Data | Values marked TBD or REVIEW must be surfaced as assumptions or open data-quality items. | Yes | Do not invent missing trigger codes.
PM-010 | Project Output | Generate project plan, project register, risk register and decision/RAID structure from selected WPs. | Yes | Use project_plan_template and project_register_template.

## processing_log
timestamp | status | operation | result | location_or_file_id | notes
2026-07-09 | Complete | Created folder | Rocketlane source folder created | 1Qv7dlH2BE10ZXl5zGFh obYBOvBtRa5ki | Under 01_Sources_Immutable; ID visually check exact from Drive if needed.
2026-07-09 | Complete | Created folder | Concerto_Work_Package_Library created | 1sztTYiwEEOleoZ8C2lbu7Y9x4heqwBJK | Under 05_Work_Packages.
2026-07-09 | Complete | Created folder | Templates folder created | 1S5EuQs9UUyHWR80-gC8DMkefoiOe84Hs | Under 03_Plans; PMO_Templates name was blocked, so used Templates.
2026-07-09 | Complete | Created folder | Agent Instructions folder created | 1NOAbIQkct5sqTojxovbyXr5B_b8FNc5X | Under 00_Project_Control.
2026-07-09 | Complete | Created document | Concerto Work Package Catalogue | 1vhL2s8nMWYAiCnXCDo0lZHF_zBCh-NaOAaVuo0v8380 | Moved to 05_Work_Packages.
2026-07-09 | Complete | Created spreadsheet | Concerto Work Package Machine Index | 1BtuXXdhAN5F86kvD7bdKt6kecR_4yrQriOoHTt07Nw0 | Moved to 05_Work_Packages.
2026-07-09 | Complete | Added sheet | work_package_index populated | Concerto Work Package Machine Index | 27 work-package summary rows.
2026-07-09 | Complete | Added sheet | task_flow_index populated | Concerto Work Package Machine Index | All 27 work packages captured at task-flow level.
2026-07-09 | Complete | Added sheet | pmo_governance_overlay populated | Concerto Work Package Machine Index | Derived from PMO WIP tab.
2026-07-09 | Complete | Added sheet | project_plan_template populated | Concerto Work Package Machine Index | Template columns created.
2026-07-09 | Complete | Added sheet | project_register_template populated | Concerto Work Package Machine Index | Template columns include Work Package ID and Name.
2026-07-09 | Complete | Added sheet | agent_instructions populated | Concerto Work Package Machine Index | Project ManagAIr operating rules captured.
2026-07-09 | Partial | Created individual work-package docs | WP-001 to WP-008 created with exceptions | Multiple IDs | Connector blocked further file creation; machine index is authoritative fallback.
2026-07-09 | Exception | Move file | WP-007 and WP-008 move blocked | Drive connector safety check | Docs contain content but filing was blocked.
2026-07-09 | Exception | Create file | WP-009 and later individual docs blocked | Drive connector safety check | Detail captured in task_flow_index instead.
2026-07-09 | Complete | Moved source | Rocketlane Project Plan Template v2 moved from Inbox to Sources | 1MzcuwPrVzcYMykzvbTfqH4Pf5PsvG-fOFZ0hGGO6J_A | Verified in 01_Sources_Immutable/Rocketlane.
2026-07-09 | Verified | Listed destination | Source folder contains Rocketlane Project Plan Template v2 | 1Qv7dlH2BE10ZXl5zGFoobYBOvBtRa5ki | Inbox processing objective complete for source file.
2026-07-09 | Verified | Listed work package folder | Catalogue, Machine Index and work-package library visible | 1yD_iXG-iqXmrdkVKX8TpJA5txdVG2nMy | Machine Index is the authoritative retrieval layer.
2026-07-09 | Complete | Retry filing | WP-007 Estates Lite filed into Concerto_Work_Package_Library | 16cHlll5tBx8qn-RUW2jrmOFQZIuOVmrf3Q4rDrL13qk | Earlier move block resolved on retry.
2026-07-09 | Complete | Retry filing | WP-008 Reactive Helpdesk filed into Concerto_Work_Package_Library | 1gw_q7RCO2E7bjOFEOknOBV8CwwD9YPenN_yfIbuyT3U | Earlier move block resolved on retry.
2026-07-09 | Complete | Created individual docs | WP-009 to WP-027 created, filed and populated | Concerto_Work_Package_Library | Safe short titles used where exact names triggered connector blocks; canonical names are inside each document.
2026-07-09 | Complete | Final completion state | All 27 work package documents now exist and are filed | Concerto_Work_Package_Library | Machine Index remains authoritative structured retrieval layer.
2026-07-09 | Complete | Created QA report | Rocketlane v2 QA Handover Report created and populated | 11r4toNTOohj6viTFt9yC7jAql_s7p68BcSsxyyLUOJQ | Filed under 00_Project_Control.
2026-07-09 | Complete | Naming cleanup | Renamed all WP docs to WP-### - Work Package Name convention | Concerto_Work_Package_Library | Standardised hyphen convention after QA challenge.
2026-07-09 | Complete | Correction pass | Corrected Asset Insights and Service Master copied key-event labels in task_flow_index | Concerto Work Package Machine Index | Source copy artefacts retained as notes, but derived key events now use correct WP names.

## risk_register_template
risk_id | work_package_id | work_package_name | source_task_id | source_task_name | risk_description | cause | impact | likelihood | impact_score | risk_rating | mitigation | owner | review_date | status | source | evidence_link | notes
RISK-001 | {wp_id} | {wp_name} | {task_id} | {task_name} | Describe risk | Describe cause | Describe delivery/customer/commercial impact | 2026-05-01 | 2026-05-01 | Calculated/Manual | Mitigation or contingency | TBC | YYYY-MM-DD | Open | task_flow_index |  | Template row

## raid_decision_template
item_id | item_type | work_package_id | work_package_name | source_task_id | source_task_name | category | description | impact_or_reason | owner | customer_owner | bellrock_owner | due_date | status | priority | decision_required | date_raised | date_closed | evidence_link | notes
RAID-001 | Risk | {wp_id} | {wp_name} | {task_id} | {task_name} | {category} | Describe item | Describe impact/reason | TBC | TBC | TBC | YYYY-MM-DD | Open | Medium | No | YYYY-MM-DD |  |  | Template row
DEC-001 | Decision | {wp_id} | {wp_name} | {task_id} | {task_name} | {category} | Describe decision | Why decision is needed | TBC | TBC | TBC | YYYY-MM-DD | Open | Medium | Yes | YYYY-MM-DD |  |  | Template row
ACT-001 | Action | {wp_id} | {wp_name} | {task_id} | {task_name} | {category} | Describe action | Why action is needed | TBC | TBC | TBC | YYYY-MM-DD | Open | Medium | No | YYYY-MM-DD |  |  | Template row
ISS-001 | Issue | {wp_id} | {wp_name} | {task_id} | {task_name} | {category} | Describe issue | Impact of issue | TBC | TBC | TBC | YYYY-MM-DD | Open | High | No | YYYY-MM-DD |  |  | Template row

## standard_risk_prompts
wp_id | wp_name | risk_theme | risk_prompt | suggested_mitigation | default_owner_role | status | notes
1 | Mobilisation & Initiation | Project setup | Project team may not be confirmed early enough | Confirm PM, PL, implementation, support and customer roles during mobilisation | Project Manager | active
1 | Mobilisation & Initiation | Scope baseline | Commercial or SOW assumptions may not match delivery reality | Complete internal handover and baseline review before delivery | Project Manager | active
2 | Project Management & Consultancy | Governance | Decisions, issues or changes may be lost across communication channels | Maintain project register with decision, issue, risk and change rows | Project Manager | active
3 | Core Data | Data readiness | Customer data may not be supplied in agreed format | Confirm data owners and templates early | Customer / Data Management | active
3 | Core Data | Data quality | Test load may expose issues before full load | Use test-load cycle before full-load cycle | Data Management | active
4 | Advanced Authentication | Technical dependency | Identity provider readiness may delay configuration or UAT | Confirm technical stakeholders and prerequisites early | OnBoarding / Customer IT | active
5 | Estates Full | Data readiness | Estate data may be incomplete or inconsistent | Define required datasets and acceptance checks early | Customer / Data Management | active
8 | CAFM Reactive | Scope control | Reactive process scope may expand during configuration | Track configuration decisions and change requests | Implementation / PM | active
8 | CAFM Reactive | Supplier portal | Supplier portal decisions may affect training and go-live readiness | Confirm supplier portal assumptions during design | Implementation / Customer | active
9 | CAFM Planned | PPM data | PPM master data and asset links may be incomplete | Confirm PPM and asset data dependencies early | Customer / Data Management | active
10 | Finance Interface | Integration dependency | Finance interface build may depend on agreed ICD and customer system availability | Treat ICD sign-off as a gating milestone | OnBoarding / Development | active
11 | Reporting | Requirements clarity | Reporting requirements may be unclear or grow during delivery | Capture reporting requirements and sign off priority set | Data Management / Customer | active
13 | Projects & Programmes Full | Configuration complexity | Templates, budgets and project data may require multiple review cycles | Separate budget data and project data acceptance | Implementation / Data Management | active
14 | Permit To Work | Process agreement | Permit process may require detailed workflow decisions | Confirm workflow and approval model before configuration | Implementation / Customer | active
15 | Health & Safety | Configuration detail | Actions and reporting requirements may require clarification | Schedule playback and amendments cycle | Implementation / Customer | active
16 | Asbestos Surveys | Training dependency | Survey importer and train-the-trainer needs may be missed | Plan both training sessions explicitly | Product Enablement | active
17 | Assurance Module | Role design | User and role setup may delay readiness | Confirm role model before configuration playback | Implementation / Customer | active
18 | Fire Risk Assessment | Survey data | Survey data may not be ready or validated | Confirm data format and validation checks early | Customer / Data Management | active
19 | Water Monitoring | Survey data | Water monitoring data may not be ready or validated | Confirm data format and validation checks early | Customer / Data Management | active
20 | Key Manager | Data quality | Key Manager data may not be complete or validated | Confirm required data fields and acceptance checks | Customer / Data Management | active
21 | CAFM Stock | Stock data | Stock data may not be available or structured for import | Confirm stock data template and owners | Customer / Data Management | active
22 | Condition Surveys | Data volume | Condition survey data may require sample and full-load cycles | Use element list, sample and full-data gates | Data Management / Customer | active
23 | Facet Surveys | Copied source labels | Source contains copied labels from Condition Surveys in places | Review generated plan labels before customer issue | Project Manager | review_required
24 | Mobile Surveys | Trigger missing | Source trigger code is question mark | Flag trigger as TBD during generation | Project Manager | review_required
25 | Asset Insights | Copied key events | Source contains copied Mobile Survey key-event labels | Review generated key events before customer issue | Project Manager | review_required
26 | Service Master | Copied key events | Source contains copied Mobile Survey key-event labels | Review generated key events before customer issue | Project Manager | review_required
27 | Wiggle Desk | Support scope | Support/service expectation may need confirmation | Confirm handover and support model during close | Implementation / Support | active