# WP-001 — Mobilisation & Initiation

Status: derived work-package reference

Canonical source: Rocketlane Project Plan Template v2

Source tab: Rocketlane

Source Phase/Task ID: 1

Source row: 3

Dynamic trigger: TEC_BMA_CON_ECPS_PROS_CON

## Purpose

Mobilisation & Initiation provides the project-start framework for Bellrock Concerto implementations, including governance setup, commercial handover, environment spin-up, formal kick-off, scope/process mapping and scoping documentation.

## Use by Project ManagAIr

Use this work package when creating any Bellrock Concerto implementation project unless explicitly excluded. Register rows created from this work package must include Work Package ID `1` and Work Package Name `Mobilisation & Initiation`.

## Task Template

| Source Task ID | Task | Start Day | Duration | Owner Role | Category | Private | Key Event |

|---|---|---:|---:|---|---|---|---|

| 1.1 | Governance Setup | — | — | Project Manager | Project Management | No | New Project Start |

| 1.1.1 | Project Teams Identified | 1 | 1 | Project Manager | Project Management | Yes | — |

| 1.1.2 | Client Charter Sign Off | 1 | 1 | Project Manager / Customer | Project Management | No | — |

| 1.2 | Commercial & Handover | — | — | Project Manager | Project Management | Yes | — |

| 1.2.1 | Sales Handover | 1 | — | Project Manager / PS Team Lead | Project Management | Yes | — |

| 1.2.2 | Baseline Agreed | 1 | 5 | Project Manager / PS Team Lead | Project Management | Yes | — |

| 1.2.3 | Pre Mobilisation Call | 6 | 1 | Project Manager / PS Team Lead / Customer | Project Management | No | — |

| 1.3 | System Spin Up | — | — | PS Team Lead | Project Management | No | — |

| 1.3.1 | Create Environments | 6 | 2 | Support | Project Management | Yes | — |

| 1.3.2 | Clear down data | 6 | 2 | Support | Project Management | Yes | — |

| 1.3.3 | Branding Customisation | 8 | 2 | PS Team Lead | Project Management | Yes | — |

| 1.3.4 | Module / Licence Configuration | 8 | 2 | PS Team Lead | Project Management | Yes | — |

| 1.4 | Formal Project Kick Off | — | — | Project Manager / PS Team Lead | Project Management | Yes | — |

| 1.4.1 | Implementation Plan Issued | 9 | 5 | Project Manager / PS Team Lead | Project Management | Yes | — |

| 1.4.2 | Implementation Plan Sign Off | 14 | 1 | Project Manager / PS Team Lead / Customer | Project Management | No | — |

| 1.5 | Project Scope & Process Mapping | — | — | Project Manager / PS Team Lead / Customer | Project Management | No | — |

| 1.5.1 | Onsite Process Mapping | — | — | Project Manager / PS Team Lead / Customer | Project Management | No | — |

| 1.5.1.1 | Core Data | 15 | 5 | Customer / Implementation | Project Management | Yes | — |

| 1.5.1.2 | Reactive | 15 | 5 | Customer / Implementation | Project Management | Yes | — |

| 1.5.1.3 | Planned | 15 | 5 | Customer / Implementation | Project Management | Yes | — |

| 1.5.1.4 | Projects & Programmes | 15 | 5 | Customer / Implementation | Project Management | Yes | — |

| 1.5.1.5 | Supplier Portal | 15 | 5 | Customer / Implementation | Project Management | Yes | — |

| 1.5.1.6 | Surveys | 15 | 5 | Customer / Implementation | Project Management | Yes | — |

| 1.6 | Scoping Documentation | — | — | Project Manager / PS Team Lead | Project Management | No | — |

| 1.6.1 | Scope & High-Level Processes Issued | 21 | 1 | Project Manager / PS Team Lead | Project Management | Yes | — |

| 1.6.2 | Processes Reviewed | 22 | 5 | Project Manager / PS Team Lead / Customer | Project Management | Yes | — |

| 1.6.3 | Process / Scope Signed Off | 27 | 1 | Project Manager / PS Team Lead / Customer | Project Management | Yes | Process Scope Sign Off |

## Standard Risks

| Risk | Suggested Mitigation |

|---|---|

| Project team is not confirmed early enough. | Confirm PM, PL, implementation, support and customer roles during mobilisation. |

| Commercial/SOW assumptions do not match delivery reality. | Complete internal sales handover and baseline agreement before formal delivery. |

| Environments are not ready before discovery/design activity. | Treat environment spin-up as an early gated activity. |

| Scope/process mapping is incomplete. | Require process/scope sign-off before work-package delivery is treated as stable. |

## Register Tags

- work_package_id: 1

- work_package_name: Mobilisation & Initiation

- source_file: Rocketlane Project Plan Template v2

- source_sheet: Rocketlane