# WP-004 — Advanced Authentication

Status: derived work-package reference

Canonical source: Rocketlane Project Plan Template v2

Source tab: Rocketlane

Source Phase/Task ID: 4

Source row: 77

Dynamic trigger: TEC_BAS_CON_ADAU_PROS_CON

Default duration: 22 days

Default effort: 22.5 hours / 3 days

## Purpose

Advanced Authentication covers onboarding, specification, configuration, UAT, sign-off, go-live and hypercare for authentication-related Concerto scope.

## Core Task Flow

- 4.1 Work Package Management (Advanced Authentication)

- 4.1.1 Advanced Authentication WP Hardbooked and Budget

- 4.1.2 Advanced Authentication Specification Agreed

- 4.1.3 Advanced Authentication Chat

- 4.2.1 Advanced Authentication Overview Session

- 4.3.1 Collate Advanced Authentication Data

- 4.4.1 Configure Concerto

- 4.4.2 Deploy in Octopus

- 4.3.1 Advanced Authentication UAT

- 4.3.2 Advanced Authentication Sign Off

- 4.3.3 Advanced Authentication Go Live

- 4.3.4 Advanced Authentication Hyper Care

## Register Guidance

Project outputs must include Work Package ID `4`, Work Package Name `Advanced Authentication`, and source task references where applicable.

## Standard Risk Prompts

- Authentication requirements may not be agreed early enough.

- Deployment activity may depend on external identity-provider readiness.

- UAT may require customer technical stakeholder availability.