# WP-005 — Estates Full

Status: derived work-package reference

Canonical source: Rocketlane Project Plan Template v2

Source tab: Rocketlane

Source Phase/Task ID: 5

Source row: 96

Dynamic trigger: TEC_PSE_CON_RE_PROS_CON

Default duration: 48 days

Default effort: 56.25 hours / 7.5 days

## Purpose

Estates Full covers full estates delivery including overview, data collation, data load, playback, reporting training, UAT, sign-off, go-live, hypercare and support handover.

## Core Task Flow

- 5.1 Work Package Management (Estates Full)

- 5.1.1 Estates Full WP Hardbooked and Budget

- 5.1.2 Estates Full Specification Agreed

- 5.1.3 Estates Full Chat

- 5.2.1 Estates Full Overview Session

- 5.3.1 Estates Full Test Data Collation

- 5.3.2 Estates Full Test Data Validation and Load

- 5.3.2.1 Transaction Party Data

- 5.3.2.2 Occupation Data

- 5.3.2.3 Rentable Units Data

- 5.3.2.4 Ownership Data

- 5.3.2.5 Disposals Data

- 5.3.2.6 Valuation Data

- 5.3.2.7 Rateable Values

- 5.3.3 Estates Full Test Data Playback Session

- 5.3.4 Estates Full Full Data Collation

- 5.3.5 Estates Full Final Data Validation and Load

- 5.3.5.1 Estates Full Data Load

- 5.3.6 Full Data Playback Session

- 5.4.1 Estates Training Session

- 5.4.2 Estates Reporting Training Session

- 5.5.1 Estates Full UAT

- 5.5.2 Estates Full Sign Off

- 5.5.3 Estates Full Go Live

- 5.5.4 Estates Full Hyper Care

- 5.5.5 Estates Full Hand Over to Support

## Register Guidance

Use Work Package ID `5` and Work Package Name `Estates Full` on all related plan, risk, issue, action and decision rows.

## Standard Risk Prompts

- Customer estate data may be incomplete or inconsistent.

- Reporting training may be missed if treated as optional.

- Go-live readiness depends on full data acceptance and customer owner availability.