# WP-007 — Estates Lite

Status: derived work-package reference

Canonical source: Rocketlane Project Plan Template v2

Source tab: Rocketlane

Source Phase/Task ID: 7

Source row: 150

Dynamic trigger: TEC_PSE_CON_RELI_PROS_CON

Default duration: 36 days

Default effort: 22.5 hours / 3 days

## Purpose

Estates Lite is a reduced estates delivery work package covering overview, test data, full data, playback, training, UAT, sign-off, go-live, hypercare and support handover.

## Core Task Flow

- 7.1 Work Package Management (Estates Lite)

- 7.1.1 Estates Lite WP Hardbooked and Budget

- 7.1.2 Estates Lite Specification Agreed

- 7.1.3 Estates Lite Chat

- 7.2.1 Estates Lite Overview Session

- 7.3.1 Estates Lite Test Data Collation

- 7.3.2 Estate Lite Test Data Validation and Load

- 7.3.2.1 Estate Lite Load Test Data

- 7.3.2.2 Estate Lite Test Data Playback Session

- 7.3.3 Estate Lite Full Data Collation

- 7.3.4 Estate Lite Final Data Validation and Load

- 7.3.4.1 Estates Lite Data Load

- 7.4 Estates Lite Data Playback Session

- 7.5.1 Estates Lite Training Session

- 7.6.1 Estates Lite UAT

- 7.6.2 Estates Lite Sign Off

- 7.6.3 Estates Lite Go Live

- 7.6.4 Estates Lite Hyper Care

- 7.6.5 Estates Hand Over to Support

## Register Guidance

Use Work Package ID `7` and Work Package Name `Estates Lite` on all generated plan and register rows.

## Standard Risk Prompts

- Customer estate data may not be ready in time.

- Lite scope may be confused with full estates scope.

- Go-live may be delayed if full data playback is not accepted.