# WP-008 — CAFM Reactive

Status: derived work-package reference

Canonical source: Rocketlane Project Plan Template v2

Source tab: Rocketlane

Source Phase/Task ID: 8

Source row: 178

Dynamic trigger: TEC_BMA_CON_CAFMRE_PROS_CON

Default duration: 42 days

Default effort: 48.75 hours / 6.5 days

## Purpose

CAFM Reactive covers reactive helpdesk delivery including overview, data collation, data load, configuration, supplier portal elements, training, UAT, sign-off, go-live, hypercare and support handover.

## Core Task Flow

- 8.1 Work Package Management (CAFM Reactive)

- 8.1.1 CAFM Reactive WP Hardbooked and Budget

- 8.1.2 CAFM Reactive Specification Agreed

- 8.1.3 CAFM Reactive Chat

- 8.2.1 CAFM Reactive Overview Session

- 8.3.1 Collate Reactive Data

- 8.3.2 Data Validation and Load (Reactive)

- 8.3.2.1 Load Data (Reactive)

- 8.4 CAFM Reactive Configuration

- 8.4.1 Configure FixMy

- 8.4.2 Supplier Portal

- 8.4.2.2 AFP and Invoicing

- 8.4.3 Helpdesk Actions

- 8.4.4 Testing and Playback

- 8.4.5 Reactive Helpdesk Playback

- 8.4.6 Order Template

- 8.4.7 Projects Setup Lite

- 8.5.1 Supplier Portal Training

- 8.5.2 Reactive Helpdesk Training

- 8.6.1 CAFM Reactive UAT

- 8.6.2 CAFM Reactive Sign Off

- 8.6.3 CAFM Reactive Go Live

- 8.6.4 CAFM Reactive Hyper Care

- 8.6.5 CAFM Reactive Hand Over to Support

## Register Guidance

Use Work Package ID `8` and Work Package Name `CAFM Reactive` on all generated plan and register rows.

## Standard Risk Prompts

- Reactive process scope may expand during configuration.

- Supplier portal decisions may affect training and go-live readiness.

- Order template requirements may require extra customer review.