# WP-009 — CAFM Planned

Status: derived work-package reference

Canonical source: Rocketlane Project Plan Template v2

Source tab: Rocketlane

Source Phase/Task ID: 9

Dynamic trigger: TEC_BCO_CON_CAFMPL_PROS_CON

Default duration: 42 days

Default effort: 48.75 hours / 6.5 days

## Purpose

CAFM Planned covers planned maintenance / PPM delivery including overview, PPM data, configuration, supplier portal elements, training, UAT, sign-off, go-live, hypercare and support handover.

## Core Task Flow

- 9.2.1 PPM Overview Session

- 9.3.1 CAFM Planned Data Mapping Session

- 9.3.2 Collate Planned Test Data

- 9.3.3 Data Validation and Load (Planned)

- 9.4.1 Configure PPMs Internal / External

- 9.4.2 Playback PPM Configuration

- 9.4.3 Supplier Portal Configuration (Onboarded)

- 9.4.5 Testing and Playback

- 9.4.6 Planned Helpdesk Playback

- 9.5.1 Supplier Portal Training

- 9.5.2 PPM Training

- 9.6.1 CAFM Planned UAT

- 9.6.2 CAFM Planned Sign Off

- 9.6.3 CAFM Planned Go Live

- 9.6.4 CAFM Planned Hyper Care

- 9.6.5 CAFM Planned Hand Over to Support

## Register Guidance

Use Work Package ID `9` and Work Package Name `CAFM Planned` on all generated plan and register rows.

## Standard Risk Prompts

- PPM master data and asset links may be incomplete.

- Supplier portal assumptions may affect planned maintenance configuration.

- PPM training may depend on accepted configuration playback.