# WP-010 — Finance Interface

Status: derived work-package reference

Canonical source: Rocketlane Project Plan Template v2

Source tab: Rocketlane

Source Phase/Task ID: 10

Dynamic trigger: TBD_SOURCE_VALUE_QUESTION_MARK

Default duration: 30 days

Default effort: 37.5 hours / 5 days

## Purpose

Finance Interface covers interface discovery, ICD creation and sign-off, development, test, internal sign-off, UAT, sign-off, go-live, hypercare and support handover.

## Core Task Flow

- 10.2.1 Finance Interface Overview Session

- 10.2.2 Finance Interface ICD Creation

- 10.2.3 Finance Interface ICD Sign Off

- 10.3.1 Finance Interface Build

- 10.3.2 Finance Interface Test

- 10.3.3 Finance Interface Internal Sign Off

- 10.4.1 Finance Interface UAT

- 10.4.2 Finance Interface Sign Off

- 10.4.3 Finance Interface Go Live

- 10.4.4 Finance Interface Hyper Care

- 10.4.5 Finance Interface Hand Over to Support

## Register Guidance

Use Work Package ID `10` and Work Package Name `Finance Interface` on all generated plan and register rows. Surface the trigger code as TBD until confirmed.

## Standard Risk Prompts

- ICD agreement may delay build.

- Customer finance system availability may affect test and UAT.

- Interface sign-off may require both customer and technical approval.